## Arch. & ID
Sr/No | Drawing Number | Rev. No. | Description | Discipline | Trade | Activity / Package
1665 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010108_PDF | 0 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-H SHEET 8 of 9 | AR | ARchitecture | Details
1663 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010107_PDF | 0 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-H SHEET 7 of 9 | AR | ARchitecture | Details
1664 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010107_PDF | 1 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-H SHEET 7 of 9 | AR | ARchitecture | Details
1657 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010103_PDF | 0 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-H SHEET 3 of 9 | AR | ARchitecture | Details
1658 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010103_PDF | 1 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-H SHEET 3 of 9 | AR | ARchitecture | Details
1661 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010106_PDF | 0 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-D SHEET 6 of 9 | AR | ARchitecture | Details
1662 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010106 | 1 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-D SHEET 6 of 9 | AR | ARchitecture | Details
1659 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010105_PDF | 0 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-D SHEET 5 of 9 | AR | ARchitecture | Details
1660 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010105_PDF | 1 | WS-687-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-D SHEET 5 of 9 | AR | ARchitecture | Details
1656 | WS-WSH-687-3230-UBJ-SDW-AR-2L0-0010107_PDF | 0 | WS-687-Faena Hotel - Lower Ground Floor Plan-Part G, Sheet 7 of 9 | AR | ARchitecture | Details
1670 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010102_PDF | 0 | WS-687-Faena Hotel - FLOOR PLAN BASEMENT 1 HOTEL PART-B SHEET 2 of 9 | AR | ARchitecture | Details
1671 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010102_PDF | 1 | WS-687-Faena Hotel - FLOOR PLAN BASEMENT 1 HOTEL PART-B SHEET 2 of 9 | AR | ARchitecture | Details
1668 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010101_PDF | 0 | WS-687-Faena Hotel - FLOOR PLAN BASEMENT 1 HOTEL PART-A SHEET 1 of 9 | AR | ARchitecture | Details
1669 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010101_PDF | 1 | WS-687-Faena Hotel - FLOOR PLAN BASEMENT 1 HOTEL PART-A SHEET 1 of 9 | AR | ARchitecture | Details
1666 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010100_PDF | 0 | WS-687-Faena Hotel - FLOOR PLAN BASEMENT 1 HOTEL MASTER PLAN | AR | ARchitecture | Details
1667 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010100_PDF | 1 | WS-687-Faena Hotel - FLOOR PLAN BASEMENT 1 HOTEL MASTER PLAN | AR | ARchitecture | Details
1653 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010104_PDF | 0 | WS-687:SDW-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-D SHEET 1 of 9 | AR | ARchitecture | Details
1655 | WS-WSH-687-3230-UBJ-SDW-AR-2B1-0010104 | 0 | WS-687:SDW-FAENA HOTEL- FLOOR PLAN BASEMENT 1 HOTEL PART-D SHEET 1 of 9 | AR | ARchitecture | Details
1654 | WS-WSH-687-3230-UBJ-SDW-AR-2L0-0010104_PDF | 0 | WS-687 : FAENA HOTEL- Lower Ground Floor Plan-Part D, Sheet- 4 of 9 | AR | ARchitecture | Details
682 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | WASTE STORAGE ROOM - DETAILED PLAN & SECTIONS | AR | Architecture | Details
713 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | WALL TYPES | AR | Architecture | Details
775 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | VILLAS - TYPICAL WINDOWS SCHEDULE & TYPOLOGY | AR | Architecture | Windows
418 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Villa Lounge Reflected Ceiling Plan | AR | Architecture | RCP
294 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa Lounge Floor Plan Block Works | AR | Architecture | Block Works
171 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Villa Lounge Floor Plan | AR | Architecture | General arrangement
510 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Villa Lounge Floor Finishes Plan | AR | Architecture | Finishing
632 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | VILLA LOUNGE - SECTIONS & ELEVATIONS | AR | Architecture | Details
774 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | VILLA LOUNGE - DOOR SCHEDULE, WINDOWS SCHEDULE & TYPOLOGY & ROOM FINISHES SCHEDULE | AR | Architecture | Windows
691 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | VILLA GARAGE AND BOH DETAILS | AR | Architecture | Details
15 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 9 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
14 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 8 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
13 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 7 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
12 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 6 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
11 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 5 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
10 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 4 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
9 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 3 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
26 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 20 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
625 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
558 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
290 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
557 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
326 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
417 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
509 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
291 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
593 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 20 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
8 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 2 - 5 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
25 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 19 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
624 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
556 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
288 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
555 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
325 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
416 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
508 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
289 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
592 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 19 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
553 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 -5 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
24 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 18 - 5 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
623 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
554 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
286 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
324 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
415 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
507 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
287 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
591 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 18 - 5 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
23 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 17 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
622 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
552 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
284 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
551 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
323 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
414 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
506 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
285 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
590 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 17 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
22 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 16 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
621 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
550 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
282 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
549 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
322 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
413 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
505 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
283 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
589 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 16 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
21 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 15 - 6 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
620 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
548 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
280 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
547 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
321 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
412 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
281 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
588 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 6 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
504 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 15 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
20 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 14 - 5 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
619 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
546 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
278 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
545 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
320 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
411 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
503 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
279 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
587 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 14 - 5 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
19 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 13 - 5 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
618 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
544 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
276 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
543 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
319 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
410 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
502 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
277 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
586 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 13 - 5 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
18 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 12 - 4 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
617 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
542 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
274 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
541 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
318 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
409 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
501 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
275 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
585 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 12 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
17 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 11 - 5 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
616 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
540 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
272 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
539 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
317 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
408 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
500 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
273 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
584 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 11 - 5 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
16 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 10 - 5 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
615 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
538 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
270 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
537 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
316 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
407 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
499 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
271 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
583 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 10 - 5 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
7 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXXX | 0 | Villa 1 - 6 Bedroom Villa - Setting out Plan | AR | Architecture | Site Work
614 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
536 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
268 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
535 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
315 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
406 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
498 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
269 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
582 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 09 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
613 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
534 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
266 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
533 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
314 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
405 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
497 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
267 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
581 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 08 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
612 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
532 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
264 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
531 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
313 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
404 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
496 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
265 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
580 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 07 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
611 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
530 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
262 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
529 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
312 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
403 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
495 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
263 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
579 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 06 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
610 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
528 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
260 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
527 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
311 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
402 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
494 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
261 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
578 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 05 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
609 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
526 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
258 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
525 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
310 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
401 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
493 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
259 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
577 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 04 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
608 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
524 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
256 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
523 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
309 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
400 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
492 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
257 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
576 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 03 - 4 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
521 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 -5 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
607 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
522 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
254 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
308 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
399 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
491 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
255 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
575 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 02 - 5 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
606 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Sections 1 & 2 | AR | Architecture | Finishing
520 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level RF - Wall Types Plan | AR | Architecture | Wall types
252 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level L0 & L1, Floor Plan Block Works | AR | Architecture | Block Works
519 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level L0 & L1 - Wall Types Plan | AR | Architecture | Wall types
307 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level L0 & L1 - Screed Plan | AR | Architecture | Screed
398 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level L0 & L1 - Reflected Ceiling Plan | AR | Architecture | RCP
490 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level L0 & L1 - Floor Finishes Plan | AR | Architecture | Finishing
253 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Level RF, Floor Plan Block Works | AR | Architecture | Block Works
574 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Villa 01 - 6 Bedroom Villa - Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
165 | WS-WSH-687-3235-UBJ-SDW-AR-V20-0010211 | 0 | Villa - 20 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
166 | WS-WSH-687-3235-UBJ-SDW-AR-V20-0010212 | 0 | Villa - 20 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
167 | WS-WSH-687-3235-UBJ-SDW-AR-V20-0010213 | 0 | Villa - 20 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
162 | WS-WSH-687-3235-UBJ-SDW-AR-V19-0010211 | 0 | Villa - 19 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
163 | WS-WSH-687-3235-UBJ-SDW-AR-V19-0010212 | 0 | Villa - 19 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
164 | WS-WSH-687-3235-UBJ-SDW-AR-V19-0010213 | 0 | Villa - 19 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
159 | WS-WSH-687-3235-UBJ-SDW-AR-V18-0010220 | 0 | Villa - 18 - 5 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
160 | WS-WSH-687-3235-UBJ-SDW-AR-V18-0010221 | 0 | Villa - 18 - 5 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
161 | WS-WSH-687-3235-UBJ-SDW-AR-V18-0010222 | 0 | Villa - 18 - 5 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
156 | WS-WSH-687-3235-UBJ-SDW-AR-V17-0010211 | 0 | Villa - 17 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
157 | WS-WSH-687-3235-UBJ-SDW-AR-V17-0010212 | 0 | Villa - 17 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
158 | WS-WSH-687-3235-UBJ-SDW-AR-V17-0010213 | 0 | Villa - 17 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
153 | WS-WSH-687-3235-UBJ-SDW-AR-V16-0010211 | 0 | Villa - 16 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
154 | WS-WSH-687-3235-UBJ-SDW-AR-V16-0010212 | 0 | Villa - 16 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
155 | WS-WSH-687-3235-UBJ-SDW-AR-V16-0010213 | 0 | Villa - 16 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
150 | WS-WSH-687-3235-UBJ-SDW-AR-V15-0010230 | 0 | Villa - 15 - 6 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
151 | WS-WSH-687-3235-UBJ-SDW-AR-V15-0010231 | 0 | Villa - 15 - 6 Bedroom Villa - Level L0 & L1, Floor Plan, (Typical) | AR | Architecture | General arrangement
152 | WS-WSH-687-3235-UBJ-SDW-AR-V15-0010232 | 0 | Villa - 15 - 6 Bedroom Villa - Level RF, Floor Plan, (Typical) | AR | Architecture | General arrangement
147 | WS-WSH-687-3235-UBJ-SDW-AR-V14-0010220 | 0 | Villa - 14 - 5 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
148 | WS-WSH-687-3235-UBJ-SDW-AR-V14-0010221 | 0 | Villa - 14 - 5 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
149 | WS-WSH-687-3235-UBJ-SDW-AR-V14-0010222 | 0 | Villa - 14 - 5 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
144 | WS-WSH-687-3235-UBJ-SDW-AR-V13-0010220 | 0 | Villa - 13 - 5 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
145 | WS-WSH-687-3235-UBJ-SDW-AR-V13-0010221 | 0 | Villa - 13 - 5 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
146 | WS-WSH-687-3235-UBJ-SDW-AR-V13-0010222 | 0 | Villa - 13 - 5 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
141 | WS-WSH-687-3235-UBJ-SDW-AR-V12-0010211 | 0 | Villa - 12 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
142 | WS-WSH-687-3235-UBJ-SDW-AR-V12-0010212 | 0 | Villa - 12 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
143 | WS-WSH-687-3235-UBJ-SDW-AR-V12-0010213 | 0 | Villa - 12 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
138 | WS-WSH-687-3235-UBJ-SDW-AR-V11-0010220 | 0 | Villa - 11 - 5 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
139 | WS-WSH-687-3235-UBJ-SDW-AR-V11-0010221 | 0 | Villa - 11 - 5 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
140 | WS-WSH-687-3235-UBJ-SDW-AR-V11-0010222 | 0 | Villa - 11 - 5 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
135 | WS-WSH-687-3235-UBJ-SDW-AR-V10-0010220 | 0 | Villa - 10 - 5 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
136 | WS-WSH-687-3235-UBJ-SDW-AR-V10-0010221 | 0 | Villa - 10 - 5 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
137 | WS-WSH-687-3235-UBJ-SDW-AR-V10-0010222 | 0 | Villa - 10 - 5 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
132 | WS-WSH-687-3235-UBJ-SDW-AR-V09-0010211 | 0 | Villa - 09 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
133 | WS-WSH-687-3235-UBJ-SDW-AR-V09-0010212 | 0 | Villa - 09 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
134 | WS-WSH-687-3235-UBJ-SDW-AR-V09-0010213 | 0 | Villa - 09 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
129 | WS-WSH-687-3235-UBJ-SDW-AR-V08-0010211 | 0 | Villa - 08 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
130 | WS-WSH-687-3235-UBJ-SDW-AR-V08-0010212 | 0 | Villa - 08 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
131 | WS-WSH-687-3235-UBJ-SDW-AR-V08-0010213 | 0 | Villa - 08 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
126 | WS-WSH-687-3235-UBJ-SDW-AR-V07-0010211 | 0 | Villa - 07 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
127 | WS-WSH-687-3235-UBJ-SDW-AR-V07-0010212 | 0 | Villa - 07 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
128 | WS-WSH-687-3235-UBJ-SDW-AR-V07-0010213 | 0 | Villa - 07 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
123 | WS-WSH-687-3235-UBJ-SDW-AR-V06-0010211 | 0 | Villa - 06 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
124 | WS-WSH-687-3235-UBJ-SDW-AR-V06-0010212 | 0 | Villa - 06 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
125 | WS-WSH-687-3235-UBJ-SDW-AR-V06-0010213 | 0 | Villa - 06 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
120 | WS-WSH-687-3235-UBJ-SDW-AR-V05-0010211 | 0 | Villa - 05 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
121 | WS-WSH-687-3235-UBJ-SDW-AR-V05-0010212 | 0 | Villa - 05 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
122 | WS-WSH-687-3235-UBJ-SDW-AR-V05-0010213 | 0 | Villa - 05 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
117 | WS-WSH-687-3235-UBJ-SDW-AR-V04-0010211 | 0 | Villa - 04 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
118 | WS-WSH-687-3235-UBJ-SDW-AR-V04-0010212 | 0 | Villa - 04 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
119 | WS-WSH-687-3235-UBJ-SDW-AR-V04-0010213 | 0 | Villa - 04 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
114 | WS-WSH-687-3235-UBJ-SDW-AR-V03-0010211 | 0 | Villa - 03 - 4 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
115 | WS-WSH-687-3235-UBJ-SDW-AR-V03-0010212 | 0 | Villa - 03 - 4 Bedroom Villa - Level L0 & L1, Floor Plan (Typical) | AR | Architecture | General arrangement
116 | WS-WSH-687-3235-UBJ-SDW-AR-V03-0010213 | 0 | Villa - 03 - 4 Bedroom Villa - Level RF, Floor Plan (Typical) | AR | Architecture | General arrangement
111 | WS-WSH-687-3235-UBJ-SDW-AR-V02-0010220 | 0 | Villa - 02 - 5 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
112 | WS-WSH-687-3235-UBJ-SDW-AR-V02-0010221 | 0 | Villa - 02 - 5 Bedroom Villa - Level L0 & L1, Floor Plan, (Typical) | AR | Architecture | General arrangement
113 | WS-WSH-687-3235-UBJ-SDW-AR-V02-0010222 | 0 | Villa - 02 - 5 Bedroom Villa - Level RF, Floor Plan, (Typical) | AR | Architecture | General arrangement
108 | WS-WSH-687-3235-UBJ-SDW-AR-V01-0010230 | 0 | Villa - 01 - 6 Bedroom Villa - Site Plan | AR | Architecture | General arrangement
109 | WS-WSH-687-3235-UBJ-SDW-AR-V01-0010231 | 0 | Villa - 01 - 6 Bedroom Villa - Level L0 & L1, Floor Plan, (Typical) | AR | Architecture | General arrangement
110 | WS-WSH-687-3235-UBJ-SDW-AR-V01-0010232 | 0 | Villa - 01 - 6 Bedroom Villa - Level RF, Floor Plan, (Typical) | AR | Architecture | General arrangement
739 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | UTILITY AREA GATE | AR | Architecture | Details
738 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | UTILITY AREA BOUNDRY WALL | AR | Architecture | Details
722 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL WINDOWS DETAILS | AR | Architecture | Details
717 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL WET AREA DETAILS | AR | Architecture | Details
718 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL WET AREA DETAILS | AR | Architecture | Details
719 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL STAIR DETAILS | AR | Architecture | Details
728 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL ROOF EQUIPMENT DETAILS | AR | Architecture | Details
715 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL ROOF DETAILS | AR | Architecture | Details
729 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL POOL DETAILS | AR | Architecture | Details
723 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL PARKING DETAILS | AR | Architecture | Details
741 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL PARAPET & FACADE DETAILS | AR | Architecture | Details
714 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL FLOOR DETAILS | AR | Architecture | Details
725 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL FHC DETAIL | AR | Architecture | Details
1596 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYPICAL ELEVATOR THEATRE DETAILS | ID | interior | Interior works
1595 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYPICAL ELEVATOR SPA DETAILS | ID | interior | Interior works
1594 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYPICAL ELEVATOR ROYAL SUITE DETAILS | ID | interior | Interior works
1597 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYPICAL ELEVATOR HOTEL GUESTROOMS DETAILS | ID | interior | Interior works
1593 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYPICAL ELEVATOR BRANDED RESIDENCES DETAILS | ID | interior | Interior works
721 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL DOOR DETAIL | AR | Architecture | Details
716 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL CEILING DETAILS | AR | Architecture | Details
740 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL BRIDGE DETAILS | AR | Architecture | Details
724 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL BLOCKWORK AND WALL STABILIZATION DETAILS | AR | Architecture | Details
720 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | TYPICAL ELEVATOR DETAIL | AR | Architecture | Details
916 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (9 of 15) | ID | interior | Interior works
915 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (8 of 15) | ID | interior | Interior works
914 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (7 of 15) | ID | interior | Interior works
913 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (6 of 15) | ID | interior | Interior works
912 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (5 of 15) | ID | interior | Interior works
911 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (4 of 15) | ID | interior | Interior works
910 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (3 of 15) | ID | interior | Interior works
909 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (2 of 15) | ID | interior | Interior works
922 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (15 of 15) | ID | interior | Interior works
921 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (14 of 15) | ID | interior | Interior works
920 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (13 of 15) | ID | interior | Interior works
919 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (12 of 15) | ID | interior | Interior works
918 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (11 of 15) | ID | interior | Interior works
917 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (10 of 15) | ID | interior | Interior works
908 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – WARDROBE DETAILS (1 of 15) | ID | interior | Interior works
928 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – TYPICAL WALL DETAILS | ID | interior | Interior works
930 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – TYPICAL THRESHOLD | ID | interior | Interior works
929 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – TYPICAL CEILING DETAILS | ID | interior | Interior works
927 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – RAILING DETAILS | ID | interior | Interior works
907 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – POWDER ROOM VANITY DETAILS | ID | interior | Interior works
939 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – MEDICINE CABINET DETAILS 1:5 | ID | interior | Interior works
903 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – MASTER BATHROOM VANITY DETAILS | ID | interior | Interior works
925 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – KITCHEN DETAILS (3 of 3) | ID | interior | Interior works
924 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – KITCHEN DETAILS (2 of 3) | ID | interior | Interior works
923 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – KITCHEN DETAILS (1 of 3) | ID | interior | Interior works
926 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – FIRE PLACE AND SHELVING DETAILS | ID | interior | Interior works
931 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – DOOR DETAILS | ID | interior | Interior works
932 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – DOOR DETAILS | ID | interior | Interior works
933 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – DOOR DETAILS | ID | interior | Interior works
934 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – DOOR DETAILS | ID | interior | Interior works
935 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – DOOR DETAILS | ID | interior | Interior works
936 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – DOOR DETAILS | ID | interior | Interior works
938 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – BATHROOM 5 VANITY DETAILS | ID | interior | Interior works
937 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – BATHROOM 4 VANITY DETAILS | ID | interior | Interior works
906 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – BATHROOM 3 VANITY DETAILS | ID | interior | Interior works
905 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – BATHROOM 2 VANITY DETAILS | ID | interior | Interior works
904 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | TYP. VILLA – BATHROOM 1 VANITY DETAILS | ID | interior | Interior works
672 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE KITCHEN - DETAILED PLANS & SECTIONS | AR | Architecture | Details
1103 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - WALL FINISHES PLAN - LOWER GROUND FLOOR | ID | interior | Interior works
1104 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - WALL FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
1127 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – WALL DETAILS (2 OF 2) | ID | interior | Interior works
1126 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – WALL DETAILS (1 OF 2) | ID | interior | Interior works
1124 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE - VANITY DETAILS | ID | interior | Interior works
1128 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – STAIR DETAILS | ID | interior | Interior works
1117 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – SOUND BOOTH | ID | interior | Interior works
1118 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – SOUND BOOTH | ID | interior | Interior works
1105 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - REFLECTED CEILING PLAN - LOWER GROUND FLOOR | ID | interior | Interior works
1106 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - REFLECTED CEILING PLAN - GROUND FLOOR | ID | interior | Interior works
1097 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - GENERAL ARRANGEMENT PLAN - LOWER GROUND FLOOR 1:50 | ID | interior | Interior works
1098 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - GENERAL ARRANGEMENT PLAN - GROUND FLOOR 1:50 | ID | interior | Interior works
1099 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - FURNITURE PLAN - LOWER GROUND FLOOR | ID | interior | Interior works
1100 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
1101 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - FLOOR FINISHES PLAN - LOWER GROUND FLOOR | ID | interior | Interior works
1102 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - FLOOR FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
1114 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 08 | ID | interior | Interior works
1113 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 07 | ID | interior | Interior works
1112 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 06 | ID | interior | Interior works
1111 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 05 | ID | interior | Interior works
1110 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 04 | ID | interior | Interior works
1109 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 03 | ID | interior | Interior works
1108 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 02 | ID | interior | Interior works
1107 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – ELEVATIONS 01 | ID | interior | Interior works
1132 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – DOOR DETAILS (4 of 4) | ID | interior | Interior works
1131 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – DOOR DETAILS (3 of 4) | ID | interior | Interior works
1130 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – DOOR DETAILS (2 of 4) | ID | interior | Interior works
1129 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – DOOR DETAILS (1 of 4) | ID | interior | Interior works
697 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - DETAILED SECTIONS | AR | Architecture | Details
696 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - DETAILED REFLECTED CEILING PLAN | AR | Architecture | Details
695 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - DETAILED PLAN 3 | AR | Architecture | Details
694 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - DETAILED PLAN 2 | AR | Architecture | Details
693 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | THEATRE - DETAILED PLAN 1 | AR | Architecture | Details
1119 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BAR | ID | interior | Interior works
1120 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BAR | ID | interior | Interior works
1123 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BANQUETTE GROUND FLOOR (2 OF 2) | ID | interior | Interior works
1122 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BANQUETTE GROUND FLOOR (1 OF 2) | ID | interior | Interior works
1121 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BANQUETTE BACK ROW | ID | interior | Interior works
1116 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BANQUETTE & TABLE SHELF (2 OF 2) | ID | interior | Interior works
1115 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE – BANQUETTE & TABLE SHELF (1 OF 2) | ID | interior | Interior works
1125 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | THEATRE - ADA DETAILS | ID | interior | Interior works
594 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Substation-1 Elevations | AR | Architecture | Elevations
689 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SUBSTATION TYPE 2- PLANS,SECTIONS & ELEVATIONS | AR | Architecture | Details
626 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Substation Type 1-Sections | AR | Architecture | Finishing
293 | WS-WSH-687-XXX-UBJ-SDW-AR-XX-XXXX | 0 | Substation type 1- Level RF, Floor Plan Block Works | AR | Architecture | Block Works
170 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Substation type 1- Level RF, Floor Plan | AR | Architecture | General arrangement
169 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Substation type 1- Level L0, Floor Plan | AR | Architecture | General arrangement
168 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | Substation type 1- Level B1, Floor Plan | AR | Architecture | General arrangement
668 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | STAFF WC, SHOWER & CHANGING - DETAILED PLANS & SECTIONS | AR | Architecture | Details
669 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | STAFF WC, SHOWER & CHANGING - DETAILED PLANS & SECTIONS | AR | Architecture | Details
679 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | STAFF PRAYER ROOM PLAN AND SECTION | AR | Architecture | Details
1645 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-90 FIRE POINT STATUTORY SIGN | SIGN | Interior | Wayfinding
1650 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-81 SHALLOW WATER SIGN | SIGN | Interior | Wayfinding
1644 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-80 POOL DEPTH SIGN | SIGN | Interior | Wayfinding
1643 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-70 REFUGE STATUTORY SIGN | SIGN | Interior | Wayfinding
1642 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-60 STAIRCASE STATUTORY /LEVEL ID SIGN | SIGN | Interior | Wayfinding
1641 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-50 FIRE EVACUATION MAP SIGN,A3 SIZE | SIGN | Interior | Wayfinding
1640 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-40 FIRE EVACUATION MAP SIGN,A4 SIZE | SIGN | Interior | Wayfinding
1639 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-30 RULES & REGULATION SIGN, WALL MOUNTED | SIGN | Interior | Wayfinding
1638 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-20 KEEP CLEAR STATUTORY SIGN | SIGN | Interior | Wayfinding
1649 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-130 NO SMOKING SIGN, TOTEM | SIGN | Interior | Wayfinding
1648 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-120 DESIGNATED SMOKING AREA, TOTEM, MOVEABLE | SIGN | Interior | Wayfinding
1646 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-110 FOH LIFT STATUTORY SIGN | SIGN | Interior | Wayfinding
1647 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-100 ASSEMBLY POINT SIGN | SIGN | Interior | Wayfinding
1637 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | SS-10 NO SMOKING STATUTORY SIGN | SIGN | Interior | Wayfinding
1179 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT WALL DETAILS | ID | interior | Interior works
1178 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT VANITY DETAILS | ID | interior | Interior works
1172 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT SUSHI BAR DETAILS 3 of 3 | ID | interior | Interior works
1171 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT SUSHI BAR DETAILS 2 of 3 | ID | interior | Interior works
1170 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT SUSHI BAR DETAILS 1 of 3 | ID | interior | Interior works
604 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Speciality Restaurant Sections A & B | AR | Architecture | Finishing
1177 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT MAITRE’D DETAILS 2 of 2 | ID | interior | Interior works
1176 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT MAITRE’D DETAILS 1 of 2 | ID | interior | Interior works
677 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPECIALITY RESTAURANT KITCHEN - DETAILED PLANS & SECTIONS | AR | Architecture | Details
569 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Speciality Restaurant Elevations | AR | Architecture | Elevations
570 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Speciality Restaurant Elevations | AR | Architecture | Elevations
1183 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT DOOR DETAILS (3 of 3) | ID | interior | Interior works
1182 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT DOOR DETAILS (2 of 3) | ID | interior | Interior works
1181 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT DOOR DETAILS (1 of 3) | ID | interior | Interior works
1180 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT CEILING DETAILS | ID | interior | Interior works
1175 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT BAR DETAILS 3 of 3 | ID | interior | Interior works
1174 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT BAR DETAILS 2 of 3 | ID | interior | Interior works
1173 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT BAR DETAILS 1 of 3 | ID | interior | Interior works
1169 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT BANQUETTE DETAILS 2 of 2 | ID | interior | Interior works
1168 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT BANQUETTE DETAILS 1 of 2 | ID | interior | Interior works
1157 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT - WALL FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1158 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT - REFLECTED CEILING PLAN – GROUND FLOOR | ID | interior | Interior works
1154 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT - GENERAL ARRANGEMENT PLAN – GROUND FLOOR 1:50 | ID | interior | Interior works
1155 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT - FURNITURE PLAN – GROUND FLOOR | ID | interior | Interior works
1156 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT - FLOOR FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1167 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 09 | ID | interior | Interior works
1166 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 08 | ID | interior | Interior works
1165 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 07 | ID | interior | Interior works
1164 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 06 | ID | interior | Interior works
1163 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 05 | ID | interior | Interior works
1162 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 04 | ID | interior | Interior works
1161 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 03 | ID | interior | Interior works
1160 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 02 | ID | interior | Interior works
1159 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPECIALITY RESTAURANT – ELEVATIONS 01 | ID | interior | Interior works
630 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPECIALITY RESTAURANT - DETAILED SECTIONS | AR | Architecture | Details
629 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPECIALITY RESTAURANT - DETAILED PLANS | AR | Architecture | Details
683 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA PUMP ROOM - DETAILED PLAN & SECTIONS | AR | Architecture | Details
949 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA - WALL FINISHES PLAN – BASEMENT PART 1 | ID | interior | Interior works
991 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – VIP 2 TREATMENT MAKE-UP COUNTER | ID | interior | Interior works
990 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – VIP 1 TREATMENT MAKE-UP COUNTER | ID | interior | Interior works
986 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – VANITY WC | ID | interior | Interior works
985 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – VANITY COUNTER | ID | interior | Interior works
987 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TYPICAL TREATMENT | ID | interior | Interior works
1013 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TYPICAL DETAILS (4 of 4) | ID | interior | Interior works
1012 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TYPICAL DETAILS (3 of 4) | ID | interior | Interior works
1011 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TYPICAL DETAILS (2 of 4) | ID | interior | Interior works
1010 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TYPICAL DETAILS (1 of 4) | ID | interior | Interior works
996 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TOWEL SHELF TO POOL AND WELLNESS | ID | interior | Interior works
998 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TOWEL SHELF IN TEPIDERIUM | ID | interior | Interior works
997 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TOWEL SHELF AND DRINK STATION IN RELAXATION UNIT | ID | interior | Interior works
994 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – SCRUB ROOM COUNTER | ID | interior | Interior works
977 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – RETAIL JOINERY D | ID | interior | Interior works
975 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – RETAIL JOINERY C (1 of 2) | ID | interior | Interior works
976 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – RETAIL JOINERY C (1 of 2) | ID | interior | Interior works
974 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – RETAIL JOINERY B | ID | interior | Interior works
973 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – RETAIL JOINERY A | ID | interior | Interior works
950 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA – REFLECTED CEILING PLAN – BASEMENT PART 1 | ID | interior | Interior works
972 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – RECEPTION DESK | ID | interior | Interior works
1000 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – PEDICURE TROLLEY | ID | interior | Interior works
999 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – MANICURE COUNTER | ID | interior | Interior works
951 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA – LIFT LOBBY, GENERAL LAYOUT | ID | interior | Interior works
970 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – LIFT LOBBY ELEVATIONS | ID | interior | Interior works
971 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – LIFT LOBBY ELEVATIONS | ID | interior | Interior works
1001 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – HEATED RELAXATION BENCHES | ID | interior | Interior works
993 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – HAIRDRESSER COUNTER | ID | interior | Interior works
946 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA - GENERAL ARRANGEMENT PLAN – BASEMENT PART 1 1:75 | ID | interior | Interior works
992 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – GARDEN SUITE TREATMENT | ID | interior | Interior works
995 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – GARDEN SUITE PARTITION DETAILS | ID | interior | Interior works
947 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA - FURNITURE PLAN – BASEMENT PART 1 | ID | interior | Interior works
948 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | SPA - FLOOR FINISHES PLAN – BASEMENT PART 1 | ID | interior | Interior works
969 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 18 | ID | interior | Interior works
968 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 17 | ID | interior | Interior works
967 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 16 | ID | interior | Interior works
966 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 15 | ID | interior | Interior works
965 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 14 | ID | interior | Interior works
964 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 13 | ID | interior | Interior works
963 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 12 | ID | interior | Interior works
962 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 11 | ID | interior | Interior works
961 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 10 | ID | interior | Interior works
960 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 09 | ID | interior | Interior works
959 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 08 | ID | interior | Interior works
958 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 07 | ID | interior | Interior works
957 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 06 | ID | interior | Interior works
956 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 05 | ID | interior | Interior works
955 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 04 | ID | interior | Interior works
954 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 03 | ID | interior | Interior works
953 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 02 | ID | interior | Interior works
952 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ELEVATIONS 01 | ID | interior | Interior works
1009 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (8 of 8) | ID | interior | Interior works
1008 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (7 of 8) | ID | interior | Interior works
1007 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (6 of 8) | ID | interior | Interior works
1006 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (5 of 8) | ID | interior | Interior works
1005 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (4 of 8) | ID | interior | Interior works
1004 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (3 of 8) | ID | interior | Interior works
1003 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (2 of 8) | ID | interior | Interior works
1002 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – DOOR DETAILS (1 of 8) | ID | interior | Interior works
983 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – CHANGING ROOM TOWEL SHELF M | ID | interior | Interior works
982 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – CHANGING ROOM TOWEL SHELF F | ID | interior | Interior works
981 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – CHANGING ROOM LOCKER M | ID | interior | Interior works
980 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – CHANGING ROOM LOCKER F (2 of 2) | ID | interior | Interior works
979 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – CHANGING ROOM LOCKER F (1 of 2) | ID | interior | Interior works
1014 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – CEILING DETAILS | ID | interior | Interior works
984 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – BENCH | ID | interior | Interior works
978 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – ADA LOCKER | ID | interior | Interior works
989 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – VIP TREATMENT 1 | ID | interior | Interior works
988 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | SPA – TYPICAL MAKE-UP | ID | interior | Interior works
6 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXXX | 0 | Setting out plan - SHEET 06 OF 6 | AR | Architecture | Site Work
5 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXXX | 0 | Setting out plan - SHEET 05 OF 6 | AR | Architecture | Site Work
4 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXXX | 0 | Setting out plan - SHEET 04 OF 6 | AR | Architecture | Site Work
3 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXXX | 0 | Setting out plan - SHEET 03 OF 6 | AR | Architecture | Site Work
2 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXXX | 0 | Setting out plan - SHEET 02 OF 6 | AR | Architecture | Site Work
1 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXXX | 0 | Setting out plan - SHEET 01 OF 6 | AR | Architecture | Site Work
1486 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – WARDROBE DETAILS (5 of 5) | ID | interior | Interior works
1485 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – WARDROBE DETAILS (4 of 5) | ID | interior | Interior works
1484 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – WARDROBE DETAILS (3 of 5) | ID | interior | Interior works
1483 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – WARDROBE DETAILS (2 of 5) | ID | interior | Interior works
1482 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – WARDROBE DETAILS (1 of 5) | ID | interior | Interior works
1463 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ROYAL SUITE - WALL FINISHES PLAN | ID | interior | Interior works
1493 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – TYPICAL WALL DETAILS (2 of 2) | ID | interior | Interior works
1492 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – TYPICAL WALL DETAILS (1 of 2) | ID | interior | Interior works
1495 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – TYPICAL THRESHOLD | ID | interior | Interior works
1494 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – TYPICAL CEILING DETAILS | ID | interior | Interior works
1490 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – STUDY ROOM SHELF DETAILS | ID | interior | Interior works
1480 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – SECONDARY BATHROOM VANITY DETAILS | ID | interior | Interior works
1464 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ROYAL SUITE - REFLECTED CEILING PLAN | ID | interior | Interior works
1481 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – POWDER ROOM VANITY DETAILS | ID | interior | Interior works
1491 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – OUTDOOR BAR DETAILS | ID | interior | Interior works
1479 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – MASTER BATHROOM VANITY DETAILS | ID | interior | Interior works
1488 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1487 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1489 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – GLAM ROOM DETAILS | ID | interior | Interior works
1460 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ROYAL SUITE - GENERAL ARRANGEMENT PLAN 1:50 | ID | interior | Interior works
1461 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ROYAL SUITE - FURNITURE PLAN | ID | interior | Interior works
1462 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ROYAL SUITE - FLOOR FINISHES PLAN | ID | interior | Interior works
1478 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 14 | ID | interior | Interior works
1477 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 13 | ID | interior | Interior works
1476 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 12 | ID | interior | Interior works
1475 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 11 | ID | interior | Interior works
1474 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 10 | ID | interior | Interior works
1473 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 09 | ID | interior | Interior works
1472 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 08 | ID | interior | Interior works
1471 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 07 | ID | interior | Interior works
1470 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 06 | ID | interior | Interior works
1469 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 05 | ID | interior | Interior works
1468 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 04 | ID | interior | Interior works
1467 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 03 | ID | interior | Interior works
1466 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 02 | ID | interior | Interior works
1465 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – ELEVATIONS 01 | ID | interior | Interior works
1503 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (8 of 8) | ID | interior | Interior works
1502 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (7 of 8) | ID | interior | Interior works
1501 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (6 of 8) | ID | interior | Interior works
1500 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (5 of 8) | ID | interior | Interior works
1499 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (4 of 8) | ID | interior | Interior works
1498 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (3 of 8) | ID | interior | Interior works
1497 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (2 of 8) | ID | interior | Interior works
1496 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | ROYAL SUITE – DOOR DETAILS (1 of 8) | ID | interior | Interior works
1080 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RETAIL – SHOWCASE 2 | ID | interior | Interior works
1081 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RETAIL – SHOWCASE 2 | ID | interior | Interior works
1079 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RETAIL – SHOWCASE 1 | ID | interior | Interior works
1078 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RETAIL – CENTRAL UNIT | ID | interior | Interior works
1057 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RECEPTION – WALL PANELING & CORNICE | ID | interior | Interior works
1058 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RECEPTION – SECRET DOOR DETAIL | ID | interior | Interior works
1055 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RECEPTION - PRINTER STATION | ID | interior | Interior works
1056 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | RECEPTION – DRINK STATION AND MIRROR | ID | interior | Interior works
1284 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE( K) TYPE 3 - VANITY DETAILS | ID | interior | Interior works
1286 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - WET BAR DETAILS | ID | interior | Interior works
1285 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - WARDROBE DETAILS | ID | interior | Interior works
1273 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - WALL FINISHES PLAN | ID | interior | Interior works
1274 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - REFLECTED CEILING PLAN | ID | interior | Interior works
1283 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1282 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1281 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - HEADBOARD DETAILS | ID | interior | Interior works
1270 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1271 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - FURNITURE PLAN | ID | interior | Interior works
1272 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - FLOOR FINISHES PLAN | ID | interior | Interior works
1280 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - ELEVATIONS 06 | ID | interior | Interior works
1279 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - ELEVATIONS 05 | ID | interior | Interior works
1278 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - ELEVATIONS 04 | ID | interior | Interior works
1277 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - ELEVATIONS 03 | ID | interior | Interior works
1276 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 - ELEVATIONS 02 | ID | interior | Interior works
1275 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 3 – ELEVATIONS 01 | ID | interior | Interior works
1269 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - WARDROBE DETAILS (2 of 2) | ID | interior | Interior works
1268 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - WARDROBE DETAILS (1 of 2) | ID | interior | Interior works
1256 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - WALL FINISHES PLAN | ID | interior | Interior works
1267 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - VANITY DETAILS | ID | interior | Interior works
1257 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - REFLECTED CEILING PLAN | ID | interior | Interior works
1265 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1266 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - KITCHEN DETAILS - (2 of 2) | ID | interior | Interior works
1264 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - HEADBOARD DETAILS | ID | interior | Interior works
1253 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1255 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - FLOOR FINISHES PLAN | ID | interior | Interior works
1263 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - ELEVATIONS 06 | ID | interior | Interior works
1262 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - ELEVATIONS 05 | ID | interior | Interior works
1261 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - ELEVATIONS 04 | ID | interior | Interior works
1260 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - ELEVATIONS 03 | ID | interior | Interior works
1259 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - ELEVATIONS 02 | ID | interior | Interior works
1258 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 – ELEVATIONS 01 | ID | interior | Interior works
1254 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 2 - FURNITURE PLAN | ID | interior | Interior works
1252 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - WET BAR DETAILS | ID | interior | Interior works
1244 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - WALL FINISHES PLAN | ID | interior | Interior works
1250 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - VANITY DETAILS | ID | interior | Interior works
1245 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - REFLECTED CEILING PLAN | ID | interior | Interior works
1249 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - HEADBOARD DETAILS | ID | interior | Interior works
1241 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1242 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - FURNITURE PLAN | ID | interior | Interior works
1243 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - FLOOR FINISHES PLAN | ID | interior | Interior works
1248 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 – ELEVATIONS 03 | ID | interior | Interior works
1247 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 – ELEVATIONS 02 | ID | interior | Interior works
1246 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 – ELEVATIONS 01 | ID | interior | Interior works
1251 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PREM. 1 BED SUITE (K) TYPE 1 - WARDROBE DETAILS | ID | interior | Interior works
1076 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PRAYER ROOM – SHOES RACK & ABLUTIONS | ID | interior | Interior works
1077 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | PRAYER ROOM – MIHRAB DETAILS | ID | interior | Interior works
1138 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOLBAR MALE SHOWERS – ELEVATIONS 01 | ID | interior | Interior works
1143 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOLBAR FEMALE SHOWERS – ELEVATIONS 06 | ID | interior | Interior works
1142 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOLBAR – ELEVATIONS 05 | ID | interior | Interior works
1141 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOLBAR – ELEVATIONS 04 | ID | interior | Interior works
1140 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOLBAR – ELEVATIONS 03 | ID | interior | Interior works
1139 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOLBAR – ELEVATIONS 02 | ID | interior | Interior works
676 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL RESTAURANT KITCHEN - DETAILED PLANS & SECTIONS | AR | Architecture | Details
605 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Pool Bar Sections A & B | AR | Architecture | Finishing
1136 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - WALL FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
1145 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – VANITY DETAILS | ID | interior | Interior works
1151 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – TYPICAL DETAILS | ID | interior | Interior works
1137 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - REFLECTED CEILING PLAN - GROUND FLOOR | ID | interior | Interior works
1133 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - GENERAL ARRANGEMENT PLAN - GROUND FLOOR 1:50 | ID | interior | Interior works
1134 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
1135 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - FLOOR FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
1153 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – DOOR DETAILS (2 of 2) | ID | interior | Interior works
1152 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – DOOR DETAILS (1 of 2) | ID | interior | Interior works
633 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - DETAILED SECTIONS | AR | Architecture | Details
631 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | POOL BAR - DETAILED PLANS | AR | Architecture | Details
1150 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – BAR DETAILS (5 of 5) | ID | interior | Interior works
1149 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – BAR DETAILS (4 of 5) | ID | interior | Interior works
1148 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – BAR DETAILS (3 of 5) | ID | interior | Interior works
1147 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – BAR DETAILS (2 of 5) | ID | interior | Interior works
1146 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – BAR DETAILS (1 of 5) | ID | interior | Interior works
1144 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | POOL BAR – ADA VANITY DETAILS | ID | interior | Interior works
727 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | PENETRATION DETAILS | AR | Architecture | Details
1507 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | OUTDOOR - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
699 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | OFFICE - DETAILED SECTIONS | AR | Architecture | Details
698 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | OFFICE - DETAILED PLAN | AR | Architecture | Details
736 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI TRIANGULATION DETAILS 2 | AR | Architecture | Details
735 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI TRIANGULATION DETAILS 1 | AR | Architecture | Details
733 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI TIMBER FABRIC (STRAIGHT) CANOPY | AR | Architecture | Details
734 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI TIMBER FABRIC (INCLINED) CANOPY | AR | Architecture | Details
731 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI SINGLE DOOR ELEVATION | AR | Architecture | Details
732 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI DOUBLE DOOR ELEVATION | AR | Architecture | Details
737 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | NAJDI BALUSTRADE AND EXTERNAL CEILING DETAILS | AR | Architecture | Details
730 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MEP RELATED DETAILS | AR | Architecture | Details
671 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN KITCHEN - DETAILED SECTIONS | AR | Architecture | Details
670 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN KITCHEN - DETAILED PLANS | AR | Architecture | Details
1022 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - WALL FINISHES PLAN - GROUND FLOOR PART 2 | ID | interior | Interior works
1021 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - WALL FINISHES PLAN - GROUND FLOOR PART 1 | ID | interior | Interior works
1054 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – ROYAL SUITE LOBBY | ID | interior | Interior works
1037 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – RETAIL ELEVATIONS | ID | interior | Interior works
1024 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - REFLECTED CEILING PLAN - GROUND FLOOR PART 2 | ID | interior | Interior works
1023 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - REFLECTED CEILING PLAN - GROUND FLOOR PART 1 | ID | interior | Interior works
1025 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – RECEPTION ELEVATIONS | ID | interior | Interior works
1043 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – PRIVATE DINING ELEVATIONS | ID | interior | Interior works
1051 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MALE & FEMALE TOILETS | ID | interior | Interior works
1052 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MALE & FEMALE TOILETS | ID | interior | Interior works
1053 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MALE & FEMALE TOILETS | ID | interior | Interior works
1034 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MALE & FEMALE PRAYER ROOM ELEVATIONS | ID | interior | Interior works
1035 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MALE & FEMALE PRAYER ROOM ELEVATIONS | ID | interior | Interior works
1036 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MALE & FEMALE PRAYER ROOM ELEVATIONS | ID | interior | Interior works
1044 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – MAITRE D’ ELEVATIONS | ID | interior | Interior works
1045 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOS FUEGOS ELEVATIONS | ID | interior | Interior works
1046 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOS FUEGOS ELEVATIONS | ID | interior | Interior works
1049 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ENTRANCE ELEVATIONS | ID | interior | Interior works
1050 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ENTRANCE ELEVATIONS | ID | interior | Interior works
1028 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ELEVATIONS | ID | interior | Interior works
1029 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ELEVATIONS | ID | interior | Interior works
1030 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ELEVATIONS | ID | interior | Interior works
1031 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ELEVATIONS | ID | interior | Interior works
1032 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ELEVATIONS | ID | interior | Interior works
1033 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LOBBY ELEVATIONS | ID | interior | Interior works
1047 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LIVING ROOM ELEVATIONS | ID | interior | Interior works
1048 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LIVING ROOM ELEVATIONS | ID | interior | Interior works
1026 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – LIBRARY ELEVATIONS | ID | interior | Interior works
1027 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – GUEST LOBBY ELEVATIONS | ID | interior | Interior works
1016 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - GENERAL ARRANGEMENT PLAN - GROUND FLOOR PART 2 1:50 | ID | interior | Interior works
1015 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - GENERAL ARRANGEMENT PLAN - GROUND FLOOR PART 1 1:50 | ID | interior | Interior works
1018 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - FURNITURE PLAN - GROUND FLOOR PART 2 | ID | interior | Interior works
1017 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - FURNITURE PLAN - GROUND FLOOR PART 1 | ID | interior | Interior works
1020 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - FLOOR FINISHES PLAN - GROUND FLOOR PART 2 | ID | interior | Interior works
1019 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | MAIN HOTEL - FLOOR FINISHES PLAN - GROUND FLOOR PART 1 | ID | interior | Interior works
1093 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (9 of 12) | ID | interior | Interior works
1092 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (8 of 12) | ID | interior | Interior works
1091 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (7 of 12) | ID | interior | Interior works
1090 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (6 of 12) | ID | interior | Interior works
1089 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (5 of 12) | ID | interior | Interior works
1088 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (4 of 12) | ID | interior | Interior works
1087 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (3 of 12) | ID | interior | Interior works
1086 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (2 of 12) | ID | interior | Interior works
1096 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (12 of 12) | ID | interior | Interior works
1095 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (11 of 12) | ID | interior | Interior works
1094 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (10 of 12) | ID | interior | Interior works
1085 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – DOOR DETAILS (1 of 12) | ID | interior | Interior works
1038 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – CORRIDOR ELEVATIONS | ID | interior | Interior works
1039 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – CORRIDOR ELEVATIONS | ID | interior | Interior works
1040 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – CORRIDOR ELEVATIONS | ID | interior | Interior works
1041 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – CORRIDOR ELEVATIONS | ID | interior | Interior works
1042 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | MAIN HOTEL – CORRIDOR ELEVATIONS | ID | interior | Interior works
685 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | LV & SUBSTATION ROOM (3) - DETAILED PLAN & SECTIONS | AR | Architecture | Details
684 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | LV & SUBSTATION ROOM (2) - DETAILED PLAN & SECTIONS | AR | Architecture | Details
688 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | LPG YARD PLANS AND DETAIL | AR | Architecture | Details
1073 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOS FUEGOS’, LIVING AND PRIVATE DINING ROOMS – TYPICAL DETAILS | ID | interior | Interior works
1072 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOS FUEGOS’ AND LIVING ROOM – WAITER STATIONS DETAILS | ID | interior | Interior works
1068 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOS FUEGOS’ – BAR DETAIL (3 of 3) | ID | interior | Interior works
1067 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOS FUEGOS’ – BAR DETAIL (2 of 3) | ID | interior | Interior works
1066 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOS FUEGOS’ – BAR DETAIL (1 of 3) | ID | interior | Interior works
1075 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOBBY - WALL DETAILS (2 of 2) | ID | interior | Interior works
1074 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LOBBY - WALL DETAILS (1 of 2) | ID | interior | Interior works
687 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | LOADING AREA - DETAILED PLAN & SECTION | AR | Architecture | Details
686 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | LOADING AREA - DETAILED PLAN | AR | Architecture | Details
1071 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIVING ROOM – BAR DETAIL (3 of 3) | ID | interior | Interior works
1070 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIVING ROOM – BAR DETAIL (2 of 3) | ID | interior | Interior works
1069 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIVING ROOM – BAR DETAIL (1 of 3) | ID | interior | Interior works
675 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | LIBRARY PANTRY - DETAILED PLANS & SECTIONS | AR | Architecture | Details
1064 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – WALL PANELING & CORNICE | ID | interior | Interior works
1063 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – SHELVING DISPLAY | ID | interior | Interior works
1065 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – SECRET DOOR DETAIL | ID | interior | Interior works
1059 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – CONCIERGE DESK | ID | interior | Interior works
1060 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – CAKE STATION | ID | interior | Interior works
1062 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – BANQUETTE SEATING (2 of 2) | ID | interior | Interior works
1061 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | LIBRARY – BANQUETTE SEATING (1 of 2) | ID | interior | Interior works
1229 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | KIDS CLUB - WALL FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1237 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – VANITY AND SKIRTING DETAIL | ID | interior | Interior works
1236 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – TEENS ROOM JOINERY | ID | interior | Interior works
1230 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | KIDS CLUB - REFLECTED CEILING PLAN – GROUND FLOOR | ID | interior | Interior works
1234 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – MAITRE’D STATION | ID | interior | Interior works
1235 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – INFANT ROOM JOINERY | ID | interior | Interior works
1226 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | KIDS CLUB - GENERAL ARRANGEMENT PLAN – GROUND FLOOR 1:50 | ID | interior | Interior works
1227 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | KIDS CLUB - FURNITURE PLAN – GROUND FLOOR | ID | interior | Interior works
1228 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | KIDS CLUB - FLOOR FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1233 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – ELEVATIONS 03 | ID | interior | Interior works
1232 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – ELEVATIONS 02 | ID | interior | Interior works
1231 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – ELEVATIONS 01 | ID | interior | Interior works
1240 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – DOOR DETAILS (3 of 3) | ID | interior | Interior works
1239 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – DOOR DETAILS (2 of 3) | ID | interior | Interior works
1238 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | KIDS CLUB – DOOR DETAILS (1 of 3) | ID | interior | Interior works
595 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Key Hotel Section A | AR | Architecture | Finishing
560 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Key Hotel Elevations 1, 2, 3, & 4 | AR | Architecture | Elevations
1446 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 2 - ELEVATIONS 02 | ID | interior | Interior works
1445 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 2 - ELEVATIONS 01 | ID | interior | Interior works
1449 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - WARDROBE DETAILS | ID | interior | Interior works
1440 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - WALL FINISHES PLAN | ID | interior | Interior works
1448 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - VANITY DETAILS | ID | interior | Interior works
1441 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - REFLECTED CEILING PLAN | ID | interior | Interior works
1447 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - HEADBOARD DETAILS | ID | interior | Interior works
1437 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1438 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - FURNITURE PLAN | ID | interior | Interior works
1439 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 & 2 - FLOOR FINISHES PLAN | ID | interior | Interior works
1444 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 - ELEVATIONS 03 | ID | interior | Interior works
1443 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 - ELEVATIONS 02 | ID | interior | Interior works
1442 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (Q/Q) TYPE 1 - ELEVATIONS 01 | ID | interior | Interior works
1436 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - WARDROBE DETAILS | ID | interior | Interior works
1429 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - WALL FINISHES PLAN | ID | interior | Interior works
1430 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - REFLECTED CEILING PLAN | ID | interior | Interior works
1435 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - HEADBOARD DETAILS | ID | interior | Interior works
1426 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1427 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - FURNITURE PLAN | ID | interior | Interior works
1428 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (K) TYPE 2 - FLOOR FINISHES PLAN | ID | interior | Interior works
1434 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (K) TYPE 2 – ELEVATION 04 | ID | interior | Interior works
1433 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (K) TYPE 2 – ELEVATION 03 | ID | interior | Interior works
1432 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (K) TYPE 2 – ELEVATION 02 | ID | interior | Interior works
1431 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (K) TYPE 2 – ELEVATION 01 | ID | interior | Interior works
1456 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (ADA) ELEVATIONS 02 | ID | interior | Interior works
1455 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (ADA) ELEVATIONS 01 | ID | interior | Interior works
1459 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (ADA) - WARDROBE DETAILS | ID | interior | Interior works
1453 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (ADA) - WALL FINISHES PLAN | ID | interior | Interior works
1458 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (ADA) - VANITY DETAILS | ID | interior | Interior works
1454 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (ADA) - REFLECTED CEILING PLAN | ID | interior | Interior works
1457 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | JR SUITE (ADA) - HEADBOARD DETAILS | ID | interior | Interior works
1450 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (ADA) - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1451 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (ADA) - FURNITURE PLAN | ID | interior | Interior works
1452 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | JR SUITE (ADA) - FLOOR FINISHES PLAN | ID | interior | Interior works
757 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | INTERNAL GLASS PARTITION | AR | Architecture | Glass Partition
1615 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | INTERNAL FINISHES SCHEDULE,FAENA HOTEL PUBLIC SPACES ID ROOMS | ID | interior | Interior works
1616 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | INTERNAL FINISHES SCHEDULE,FAENA HOTEL PUBLIC SPACES ID ROOMS | ID | interior | Interior works
1614 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | INTERNAL FINISHES SCHEDULE,FAENA HOTEL GUEST ROOM SPACES ID ROOMS | ID | interior | Interior works
1620 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | ID-50 HOTEL ENTRANCE ID SIGN, EXTERNAL | SIGN | Interior | Wayfinding
1619 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | ID-40 VILLA ID SIGN WALL MOUNTED | SIGN | Interior | Wayfinding
1618 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | ID-30 VILLA NUMBER ID SIGN TOTEM | SIGN | Interior | Wayfinding
1617 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | ID-10 WELCOME SIGN | SIGN | Interior | Wayfinding
678 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOUSEKEEPING LAUNDRY AREA DETAILED PLANS AND SECTIONS | AR | Architecture | Details
673 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOUSE KEEPING PANTRY - DETAILED PLANS & SECTIONS | AR | Architecture | Details
758 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL WINDOW TYPOLOGY | AR | Architecture | Windows
759 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL WINDOW TYPOLOGY | AR | Architecture | Windows
760 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL WINDOW TYPOLOGY | AR | Architecture | Windows
762 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL WINDOW TYPOLOGY | AR | Architecture | Windows
656 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (7,8,9,10) BOH Detailed Plans & Sections | AR | Architecture | Details
655 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (5,6) Detailed Plans & Sections | AR | Architecture | Details
654 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (3,4) Detailed Plans & Sections | AR | Architecture | Details
662 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (22) Detailed Plans & Sections | AR | Architecture | Details
661 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (20,21) Detailed Plans & Sections | AR | Architecture | Details
660 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (16,17,18,19) Detailed Plans & Sections | AR | Architecture | Details
659 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (15) Detailed Plans & Sections | AR | Architecture | Details
658 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (13,14) Detailed Plans & Sections | AR | Architecture | Details
657 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (11,12) Detailed Plans & Sections | AR | Architecture | Details
653 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Stair (1,2) Detailed Plans & Sections | AR | Architecture | Details
27 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Site Plan | AR | Architecture | General arrangement
599 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Sections B (Part 03 & 04) | AR | Architecture | Finishing
598 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Sections B (Part 01 & 02) | AR | Architecture | Finishing
597 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Sections A (Part 03 & 04) | AR | Architecture | Finishing
596 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Sections A (Part 01 & 02) | AR | Architecture | Finishing
603 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Section E & F | AR | Architecture | Finishing
602 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Section D (Part 3) | AR | Architecture | Finishing
601 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Section D (Part 1 & 2) | AR | Architecture | Finishing
600 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Section C (Part 1 & 2) | AR | Architecture | Finishing
306 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 8 | AR | Architecture | Screed
305 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 7 | AR | Architecture | Screed
304 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 6 | AR | Architecture | Screed
303 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 5 | AR | Architecture | Screed
302 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 4 | AR | Architecture | Screed
301 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 3 | AR | Architecture | Screed
300 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 2 | AR | Architecture | Screed
299 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Screed Plan 1 | AR | Architecture | Screed
681 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL MAIN GATE - DETAILED SECTIONS | AR | Architecture | Details
680 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL MAIN GATE - DETAILED PLANS | AR | Architecture | Details
761 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL LOUVER TYPOLOGY | AR | Architecture | Louvers
667 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Lift - Detailed Drawings - 8 | AR | Architecture | Details
666 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Lift - Detailed Drawings - 6 | AR | Architecture | Details
665 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Lift - Detailed Drawings - 3 | AR | Architecture | Details
664 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Lift - Detailed Drawings - 2 | AR | Architecture | Details
663 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Lift - Detailed Drawings - 1 | AR | Architecture | Details
674 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL FORUM KITCHEN - DETAILED PLANS & SECTIONS | AR | Architecture | Details
635 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL FORUM - DETAILED SECTION | AR | Architecture | Details
634 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL FORUM - DETAILED PLANS | AR | Architecture | Details
568 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 4 (Part 03 & 04) | AR | Architecture | Elevations
566 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 3 (Part 03 & 04) | AR | Architecture | Elevations
565 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 3 (Part 01 & 02) | AR | Architecture | Elevations
564 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 2 (Part 03 & 04) | AR | Architecture | Elevations
563 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 2 (Part 01 & 02) | AR | Architecture | Elevations
573 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 18,19,20 &21 | AR | Architecture | Elevations
572 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 16&17 | AR | Architecture | Elevations
571 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 14&15 | AR | Architecture | Elevations
562 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations (Part 03 & 04) | AR | Architecture | Elevations
561 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations (Part 01 & 02) | AR | Architecture | Elevations
567 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel Elevations 4(Part 01 & 02) | AR | Architecture | Elevations
753 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL DOOR TYPOLOGY | AR | Architecture | Doors
754 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL DOOR TYPOLOGY | AR | Architecture | Doors
755 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL DOOR TYPOLOGY | AR | Architecture | Doors
627 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL & RESIDENCES SITE ENTRANCE (2) - DETAILED PLANS & SECTIONS | AR | Architecture | Details
628 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | HOTEL & RESIDENCES SITE ENTRANCE (2) - DETAILED PLANS & SECTIONS | AR | Architecture | Details
647 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 9 | AR | Architecture | Details
646 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 8 | AR | Architecture | Details
645 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 7 | AR | Architecture | Details
644 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 6 | AR | Architecture | Details
643 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 5 | AR | Architecture | Details
642 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 4 | AR | Architecture | Details
641 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 3 | AR | Architecture | Details
640 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 2 | AR | Architecture | Details
652 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 14 | AR | Architecture | Details
651 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 13 | AR | Architecture | Details
650 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 12 | AR | Architecture | Details
649 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 11 | AR | Architecture | Details
648 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 10 | AR | Architecture | Details
639 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Wall Section - 1 | AR | Architecture | Details
251 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
107 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
250 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
106 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
249 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
105 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
248 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
104 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
247 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
103 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
246 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
102 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
245 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
101 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
244 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
100 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
243 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
99 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Roof Level, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
365 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan -Part - D, Sheet 4 of 9 | AR | Architecture | RCP
362 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan -Part - A, Sheet 1 of 9 | AR | Architecture | RCP
366 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
364 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
363 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
370 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
369 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
368 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
367 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
210 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan -Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
66 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan -Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
207 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan -Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
63 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan -Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
211 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
67 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
209 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
65 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
208 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
64 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
215 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
71 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
214 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
70 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
213 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
69 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
212 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
68 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
457 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan -Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
454 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan -Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
458 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
456 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
455 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
462 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
461 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
460 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
459 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
175 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine Floor Plan Block Works | AR | Architecture | Block Works
31 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine Floor Plan | AR | Architecture | General arrangement
514 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine - Wall Types | AR | Architecture | Wall types
330 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine - Reflected Ceiling Plan | AR | Architecture | RCP
422 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine - Floor Finishes Plan | AR | Architecture | Finishing
745 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Mezzanine - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
350 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground,Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
352 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
351 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
349 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
348 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
347 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - D, Sheet 4 of 9 | AR | Architecture | RCP
346 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
345 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
344 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Reflected Ceiling Plan - Part - A, Sheet 1 of 9 | AR | Architecture | RCP
197 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
53 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
196 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
52 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
195 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
51 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
194 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
50 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
193 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
49 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
192 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
48 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
191 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
47 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
190 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
46 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
189 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
45 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
444 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
443 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
442 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
441 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
440 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
439 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
438 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
437 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
436 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground, Floor Finishes Plan - Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
173 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground Floor Plan Block Works | AR | Architecture | Block Works
29 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground Floor Plan | AR | Architecture | General arrangement
512 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground - Wall Types | AR | Architecture | Wall types
328 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground - Reflected Ceiling Plan | AR | Architecture | RCP
420 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground - Floor Finishes Plan | AR | Architecture | Finishing
743 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Lower Ground - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
179 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level RF Floor Plan Block Works | AR | Architecture | Block Works
35 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level RF Floor Plan | AR | Architecture | General arrangement
518 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level RF - Wall Types | AR | Architecture | Wall types
426 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level RF - Floor Finishes Plan | AR | Architecture | Finishing
749 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level RF - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
334 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level RF - Reflected Ceiling Plan | AR | Architecture | RCP
397 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
396 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
395 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
394 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
393 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
392 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - D, Sheet 4 of 9 | AR | Architecture | RCP
391 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
390 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
389 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Reflected Ceiling Plan - Part - A, Sheet 1 of 9 | AR | Architecture | RCP
242 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
98 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
241 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
97 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
240 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
96 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
239 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
95 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
238 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
94 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
237 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
93 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
236 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
92 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
235 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
91 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
234 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
90 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
489 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
488 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
487 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
486 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
485 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
484 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
483 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
482 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
481 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3, Floor Finishes Plan - Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
178 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3 Floor Plan Block Works | AR | Architecture | Block Works
34 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3 Floor Plan | AR | Architecture | General arrangement
517 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3 - Wall Types | AR | Architecture | Wall types
333 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3 - Reflected Ceiling Plan | AR | Architecture | RCP
425 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3 - Floor Finishes Plan | AR | Architecture | Finishing
748 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 3 - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
388 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
387 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
386 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
385 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
384 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
383 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - D, Sheet 4 of 9 | AR | Architecture | RCP
382 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
381 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
380 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Reflected Ceiling Plan - Part - A, Sheet 1 of 9 | AR | Architecture | RCP
233 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
89 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
232 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
88 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
231 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
87 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
230 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
86 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
229 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
85 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
228 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
84 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
227 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
83 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
226 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
82 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
225 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
81 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
480 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
479 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
478 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
477 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
476 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
475 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
474 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
473 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
472 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2, Floor Finishes Plan - Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
177 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2 Floor Plan Block Works | AR | Architecture | Block Works
33 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2 Floor Plan | AR | Architecture | General arrangement
516 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2 - Wall Types | AR | Architecture | Wall types
332 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2 - Reflected Ceiling Plan | AR | Architecture | RCP
424 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2 - Floor Finishes Plan | AR | Architecture | Finishing
747 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 2 - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
379 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
378 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
377 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
376 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
375 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
374 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - D, Sheet 4 of 9 | AR | Architecture | RCP
373 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
372 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
371 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Reflected Ceiling Plan - Part - A, Sheet 1 of 9 | AR | Architecture | RCP
224 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
80 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
223 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
79 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
222 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
78 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
221 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
77 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
220 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
76 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
219 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
75 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
218 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
74 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
217 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
73 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
216 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
72 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
471 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
470 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
469 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
468 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
467 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
466 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
465 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
464 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
463 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1, Floor Finishes Plan - Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
176 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1 Floor Plan Block Works | AR | Architecture | Block Works
32 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1 Floor Plan | AR | Architecture | General arrangement
515 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1 - Wall Types | AR | Architecture | Wall types
331 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1 - Reflected Ceiling Plan | AR | Architecture | RCP
423 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1 - Floor Finishes Plan | AR | Architecture | Finishing
746 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 1 - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
361 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
360 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
359 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
358 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
357 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
356 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - D, Sheet 4 of 9 | AR | Architecture | RCP
355 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
354 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
353 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Reflected Ceiling Plan - Part - A, Sheet 1 of 9 | AR | Architecture | RCP
206 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
62 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
205 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
61 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
204 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
60 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
203 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
59 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
202 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
58 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
201 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
57 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
200 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
56 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
199 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
55 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
198 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
54 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
453 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
452 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
451 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
450 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
449 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
448 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
447 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
446 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
445 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0, Floor Finishes Plan - Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
174 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0 Floor Plan Block Works | AR | Architecture | Block Works
30 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0 Floor Plan | AR | Architecture | General arrangement
513 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0 - Wall Types | AR | Architecture | Wall types
329 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0 - Reflected Ceiling Plan | AR | Architecture | RCP
421 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0 - Floor Finishes Plan | AR | Architecture | Finishing
744 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Level 0 - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
343 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1,Reflected Ceiling Plan - Part - J, Sheet 9 of 9 | AR | Architecture | RCP
342 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - H, Sheet 8 of 9 | AR | Architecture | RCP
341 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - G, Sheet 7 of 9 | AR | Architecture | RCP
340 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - F, Sheet 6 of 9 | AR | Architecture | RCP
339 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - E, Sheet 5 of 9 | AR | Architecture | RCP
338 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - D, Sheet 4 of 9 | AR | Architecture | RCP
337 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - C, Sheet 3 of 9 | AR | Architecture | RCP
336 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - B, Sheet 2 of 9 | AR | Architecture | RCP
335 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Reflected Ceiling Plan - Part - A, Sheet 1 of 9 | AR | Architecture | RCP
188 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - J, Sheet 9 of 9 Block Works | AR | Architecture | Block Works
44 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - J, Sheet 9 of 9 | AR | Architecture | General arrangement
187 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - H, Sheet 8 of 9 Block Works | AR | Architecture | Block Works
43 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - H, Sheet 8 of 9 | AR | Architecture | General arrangement
186 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - G, Sheet 7 of 9 Block Works | AR | Architecture | Block Works
42 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - G, Sheet 7 of 9 | AR | Architecture | General arrangement
185 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - F, Sheet 6 of 9 Block Works | AR | Architecture | Block Works
41 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - F, Sheet 6 of 9 | AR | Architecture | General arrangement
184 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - E, Sheet 5 of 9 Block Works | AR | Architecture | Block Works
40 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - E, Sheet 5 of 9 | AR | Architecture | General arrangement
183 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - D, Sheet 4 of 9 Block Works | AR | Architecture | Block Works
39 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - D, Sheet 4 of 9 | AR | Architecture | General arrangement
182 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - C, Sheet 3 of 9 Block Works | AR | Architecture | Block Works
38 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - C, Sheet 3 of 9 | AR | Architecture | General arrangement
181 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - B, Sheet 2 of 9 Block Works | AR | Architecture | Block Works
37 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - B, Sheet 2 of 9 | AR | Architecture | General arrangement
180 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - A, Sheet 1 of 9 Block Works | AR | Architecture | Block Works
36 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Plan - Part - A, Sheet 1 of 9 | AR | Architecture | General arrangement
435 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - J, Sheet 9 of 9 | AR | Architecture | Finishing
434 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - H, Sheet 8 of 9 | AR | Architecture | Finishing
433 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - G, Sheet 7 of 9 | AR | Architecture | Finishing
432 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - F, Sheet 6 of 9 | AR | Architecture | Finishing
431 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - E, Sheet 5 of 9 | AR | Architecture | Finishing
430 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - D, Sheet 4 of 9 | AR | Architecture | Finishing
429 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - C, Sheet 3 of 9 | AR | Architecture | Finishing
428 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - B, Sheet 2 of 9 | AR | Architecture | Finishing
427 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1, Floor Finishes Plan - Part - A, Sheet 1 of 9 | AR | Architecture | Finishing
172 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 Floor Plan Block Works | AR | Architecture | Block Works
28 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 Floor Plan | AR | Architecture | General arrangement
511 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 - Wall Types | AR | Architecture | Wall types
559 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 - Wall Guards and Wall Corner Protection | AR | Architecture | Wall types
327 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 - Reflected Ceiling Plan | AR | Architecture | RCP
419 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 - Floor Finishes Plan | AR | Architecture | Finishing
742 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | Hotel - Basement 1 - BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
1216 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GYM - WALL FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1222 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – VANITIES | ID | interior | Interior works
1217 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GYM - REFLECTED CEILING PLAN – GROUND FLOOR | ID | interior | Interior works
1221 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – JOINERY UNIT | ID | interior | Interior works
1213 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GYM - GENERAL ARRANGEMENT PLAN – GROUND FLOOR 1:50 | ID | interior | Interior works
1214 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GYM - FURNITURE PLAN – GROUND FLOOR | ID | interior | Interior works
1215 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GYM - FLOOR FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1220 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – ELEVATIONS 03 | ID | interior | Interior works
1219 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – ELEVATIONS 02 | ID | interior | Interior works
1218 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – ELEVATIONS 01 | ID | interior | Interior works
1225 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – DOOR DETAILS (3 of 3) | ID | interior | Interior works
1224 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – DOOR DETAILS (2 of 3) | ID | interior | Interior works
1223 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GYM – DOOR DETAILS (1 of 3) | ID | interior | Interior works
1601 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS - TYPICAL WARDROBE DETAILS – TYPICAL SECTION AND BLOW UP DETAILS | ID | interior | Interior works
1606 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – TYPICAL WALL DETAILS (2 of 2) | ID | interior | Interior works
1605 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – TYPICAL WALL DETAILS (1 of 2) | ID | interior | Interior works
1608 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – TYPICAL THRESHOLD | ID | interior | Interior works
1604 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS - TYPICAL COATS DETAILS (3 of 3) | ID | interior | Interior works
1603 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS - TYPICAL COATS DETAILS (2 of 3) | ID | interior | Interior works
1602 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS - TYPICAL COATS DETAILS (1 of 3) | ID | interior | Interior works
1607 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – TYPICAL CEILING DETAILS | ID | interior | Interior works
1613 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – DOOR DETAILS (5 of 5) | ID | interior | Interior works
1612 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – DOOR DETAILS (4 of 5) | ID | interior | Interior works
1611 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – DOOR DETAILS (3 of 5) | ID | interior | Interior works
1610 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – DOOR DETAILS (2 of 5) | ID | interior | Interior works
1609 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOMS – DOOR DETAILS (1 of 5) | ID | interior | Interior works
1504 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - LOWER GROUND | ID | interior | Interior works
1512 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - LEVEL 03 EAST | ID | interior | Interior works
1510 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - LEVEL 02 WEST | ID | interior | Interior works
1511 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - LEVEL 02 EAST | ID | interior | Interior works
1508 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - LEVEL 01 WEST | ID | interior | Interior works
1509 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - LEVEL 01 EAST | ID | interior | Interior works
1505 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - GROUND FLOOR WEST | ID | interior | Interior works
1506 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM TERACES - FURNITURE PLAN - GROUND FLOOR EAST | ID | interior | Interior works
1539 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN - LEVEL 03 | ID | interior | Interior works
1531 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN - LEVEL 02 WEST | ID | interior | Interior works
1535 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN - LEVEL 02 EAST | ID | interior | Interior works
1527 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN - LEVEL 01 | ID | interior | Interior works
1519 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN - GROUND FLOOR WEST | ID | interior | Interior works
1523 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN - GROUND FLOOR EAST | ID | interior | Interior works
1515 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - WALL FINISHES PLAN | ID | interior | Interior works
1540 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN - LEVEL 03 | ID | interior | Interior works
1532 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN - LEVEL 02 WEST | ID | interior | Interior works
1536 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN - LEVEL 02 EAST | ID | interior | Interior works
1528 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN - LEVEL 01 | ID | interior | Interior works
1520 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN - GROUND FLOOR WEST | ID | interior | Interior works
1524 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN - GROUND FLOOR EAST | ID | interior | Interior works
1516 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - REFLECTED CEILING PLAN | ID | interior | Interior works
1513 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - LOWER GROUND | ID | interior | Interior works
1537 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - LEVEL 03 | ID | interior | Interior works
1529 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - LEVEL 02 WEST | ID | interior | Interior works
1533 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - LEVEL 02 EAST | ID | interior | Interior works
1525 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - LEVEL 01 | ID | interior | Interior works
1517 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - GROUND FLOOR WEST | ID | interior | Interior works
1521 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - GENERAL ARRANGEMENT PLAN - GROUND FLOOR EAST | ID | interior | Interior works
1514 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - FLOOR FINISHES PLAN - LOWER GROUND | ID | interior | Interior works
1538 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - FLOOR FINISHES PLAN - LEVEL 03 | ID | interior | Interior works
1530 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - FLOOR FINISHES PLAN - LEVEL 02 WEST | ID | interior | Interior works
1534 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - FLOOR FINISHES PLAN - LEVEL 02 EAST | ID | interior | Interior works
1526 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - FLOOR FINISHES PLAN - LEVEL 01 | ID | interior | Interior works
1518 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS - FLOOR FINISHES PLAN - GROUND FLOOR WEST | ID | interior | Interior works
1522 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUESTROOM CORRIDORS – FLOOR FINISHES PLAN - GROUND FLOOR EAST | ID | interior | Interior works
1561 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 12 - GROUND FLOOR | ID | interior | Interior works
1583 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 11 – LEVEL 02 | ID | interior | Interior works
1572 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 11 – LEVEL 01 | ID | interior | Interior works
1560 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 11 - GROUND FLOOR | ID | interior | Interior works
1582 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 10 – LEVEL 02 | ID | interior | Interior works
1571 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 10 – LEVEL 01 | ID | interior | Interior works
1559 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 10 - GROUND FLOOR | ID | interior | Interior works
1549 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 09 - LOWER GROUND | ID | interior | Interior works
1581 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 09 – LEVEL 02 | ID | interior | Interior works
1570 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 09 – LEVEL 01 | ID | interior | Interior works
1558 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 09 - GROUND FLOOR | ID | interior | Interior works
1548 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 08 - LOWER GROUND | ID | interior | Interior works
1580 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 08 – LEVEL 02 | ID | interior | Interior works
1569 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 08 – LEVEL 01 | ID | interior | Interior works
1557 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 08 - GROUND FLOOR | ID | interior | Interior works
1547 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 07 - LOWER GROUND | ID | interior | Interior works
1579 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 07 – LEVEL 02 | ID | interior | Interior works
1568 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 07 – LEVEL 01 | ID | interior | Interior works
1556 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 07 - GROUND FLOOR | ID | interior | Interior works
1546 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 06 - LOWER GROUND | ID | interior | Interior works
1589 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 06 – LEVEL 03 | ID | interior | Interior works
1578 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 06 – LEVEL 02 | ID | interior | Interior works
1567 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 06 – LEVEL 01 | ID | interior | Interior works
1555 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 06 - GROUND FLOOR | ID | interior | Interior works
1545 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 05 - LOWER GROUND | ID | interior | Interior works
1588 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 05 – LEVEL 03 | ID | interior | Interior works
1577 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 05 – LEVEL 02 | ID | interior | Interior works
1566 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 05 – LEVEL 01 | ID | interior | Interior works
1554 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 05 - GROUND FLOOR | ID | interior | Interior works
1544 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 04 - LOWER GROUND | ID | interior | Interior works
1587 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 04 – LEVEL 03 | ID | interior | Interior works
1576 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 04 – LEVEL 02 | ID | interior | Interior works
1565 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 04 – LEVEL 01 | ID | interior | Interior works
1553 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 04 - GROUND FLOOR | ID | interior | Interior works
1543 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 03 - LOWER GROUND | ID | interior | Interior works
1586 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 03 – LEVEL 03 | ID | interior | Interior works
1575 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 03 – LEVEL 02 | ID | interior | Interior works
1564 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 03 – LEVEL 01 | ID | interior | Interior works
1552 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 03 – GROUND FLOOR | ID | interior | Interior works
1542 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 02 - LOWER GROUND | ID | interior | Interior works
1585 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 02 – LEVEL 03 | ID | interior | Interior works
1574 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 02 – LEVEL 02 | ID | interior | Interior works
1563 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 02 – LEVEL 01 | ID | interior | Interior works
1551 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 02 - GROUND FLOOR | ID | interior | Interior works
1541 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 01 - LOWER GROUND | ID | interior | Interior works
1584 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 01 – LEVEL 03 | ID | interior | Interior works
1573 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 01 – LEVEL 02 | ID | interior | Interior works
1562 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 01 – LEVEL 01 | ID | interior | Interior works
1550 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUESTROOM CORRIDORS – ELEVATIONS 01 - GROUND FLOOR | ID | interior | Interior works
1598 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUEST ROOMS - TYPICAL VANITY DETAILS – SINGLE MIRROR VARIATION | ID | interior | Interior works
1600 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUEST ROOMS - TYPICAL VANITY DETAILS – POWDER ROOM VARIATION 2 | ID | interior | Interior works
1599 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GUEST ROOMS - TYPICAL VANITY DETAILS – POWDER ROOM VARIATION 1 | ID | interior | Interior works
690 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GUARDHOUSE PLANS & DETAILS | AR | Architecture | Details
292 | WS-WSH-687-XXX-UBJ-SDW-AR-XX-XXXX | 0 | Guard House- Block Works | AR | Architecture | Block Works
1082 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GROUND FLOOR TOILETS - VANITY DETAILS | ID | interior | Interior works
1083 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GROUND FLOOR TOILETS - VANITY DETAILS | ID | interior | Interior works
1084 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | GROUND FLOOR TOILETS - ADA VANITY DETAILS | ID | interior | Interior works
756 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | GLAZING TYPE SCHEDULE | AR | Architecture | Curtain Wall
692 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERATOR ROOM & FUEL TANK - DETAILED PLAN & SECTION | AR | Architecture | Details
941 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERAL ARRANGEMENT & KEY PLAN - LOWER GROUND FLOOR - PART 2 1:400 | ID | interior | Interior works
945 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERAL ARRANGEMENT & KEY PLAN - LEVEL 03 - PART 2 | ID | interior | Interior works
944 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERAL ARRANGEMENT & KEY PLAN - LEVEL 02 - PART 2 | ID | interior | Interior works
943 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERAL ARRANGEMENT & KEY PLAN - LEVEL 01 - PART 2 | ID | interior | Interior works
942 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERAL ARRANGEMENT & KEY PLAN - GROUND FLOOR - PART 2 | ID | interior | Interior works
940 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | GENERAL ARRANGEMENT & KEY PLAN - BASEMENT – PART 2 1:400 | ID | interior | Interior works
1187 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FORUM - WALL FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1205 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – WALL DETAILS (1 of 2) | ID | interior | Interior works
1206 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – WALL DETAILS (1 of 2) | ID | interior | Interior works
1208 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – THRESHOLD | ID | interior | Interior works
1188 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FORUM - REFLECTED CEILING PLAN – GROUND FLOOR | ID | interior | Interior works
1203 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – MALE VANITY DETAILS | ID | interior | Interior works
1184 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | FORUM - GENERAL ARRANGEMENT PLAN – GROUND FLOOR 1:50 | ID | interior | Interior works
1185 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | FORUM - FURNITURE PLAN – GROUND FLOOR | ID | interior | Interior works
1186 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FORUM - FLOOR FINISHES PLAN – GROUND FLOOR | ID | interior | Interior works
1204 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – FEMALE VANITY DETAILS | ID | interior | Interior works
1198 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 10 | ID | interior | Interior works
1197 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 09 | ID | interior | Interior works
1196 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 08 | ID | interior | Interior works
1195 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 07 | ID | interior | Interior works
1194 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 06 | ID | interior | Interior works
1193 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 05 | ID | interior | Interior works
1192 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 04 | ID | interior | Interior works
1191 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 03 | ID | interior | Interior works
1190 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 02 | ID | interior | Interior works
1189 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ELEVATIONS 01 | ID | interior | Interior works
1212 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – DOOR DETAILS (4 of 4) | ID | interior | Interior works
1211 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – DOOR DETAILS (3 of 4) | ID | interior | Interior works
1210 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – DOOR DETAILS (2 of 4) | ID | interior | Interior works
1209 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – DOOR DETAILS (1 of 4) | ID | interior | Interior works
1201 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – COATS ROOM DETAILS (3 of 3) | ID | interior | Interior works
1200 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – COATS ROOM DETAILS (2 of 3) | ID | interior | Interior works
1199 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – COATS ROOM DETAILS (1 of 3) | ID | interior | Interior works
1207 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – CEILING DETAILS | ID | interior | Interior works
1202 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FORUM – ADA VANITY DETAILS | ID | interior | Interior works
1629 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-90 FOH ROOM NUMBER ID SIGN | SIGN | Interior | Wayfinding
1628 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-70 FOH LEVEL ID | SIGN | Interior | Wayfinding
1627 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-60 FOH FACILITY DIRECTIONAL SIGN | SIGN | Interior | Wayfinding
1626 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-50 FOH FACILITY ID SIGN, TEXT ONLY | SIGN | Interior | Wayfinding
1625 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-40 FOH STAIRCASE ID SIGN | SIGN | Interior | Wayfinding
1624 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-30 FOH FACILITY ID SIGN, PICTO | SIGN | Interior | Wayfinding
1623 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-20 FOH FACILITY DOOR ID SIGN, PICTO ONLY | SIGN | Interior | Wayfinding
1631 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-120 FOH ROOM NUMBER DIRECTIONAL SIGN | SIGN | Interior | Wayfinding
1630 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | FH-110 FOH QIBLA ARROW SIGN | SIGN | Interior | Wayfinding
1354 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - WET BAR DETAILS (2 of 2) | ID | interior | Interior works
1353 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - WET BAR DETAILS (1 of 2) | ID | interior | Interior works
1352 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - WARDROBE DETAILS (4 of 4) | ID | interior | Interior works
1351 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - WARDROBE DETAILS (3 of 4) | ID | interior | Interior works
1350 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - WARDROBE DETAILS (2 of 4) | ID | interior | Interior works
1349 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - WARDROBE DETAILS (1 of 4) | ID | interior | Interior works
1334 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 2 – WALL FINISHES PLAN | ID | interior | Interior works
1335 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 2 – REFLECTED CEILING PLAN | ID | interior | Interior works
1348 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - KITCHEN DETAILS | ID | interior | Interior works
1347 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - HEADBOARD DETAILS DOUBLE QUEEN | ID | interior | Interior works
1346 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 - HEADBOARD DETAILS | ID | interior | Interior works
1331 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 2 – GENERAL ARRANGEMENT PLAN 1:50 | ID | interior | Interior works
1332 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 2 – FURNITURE PLAN | ID | interior | Interior works
1333 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 2 – FLOOR FINISHES PLAN | ID | interior | Interior works
1345 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 10 | ID | interior | Interior works
1344 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 09 | ID | interior | Interior works
1343 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 08 | ID | interior | Interior works
1342 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 07 | ID | interior | Interior works
1341 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 06 | ID | interior | Interior works
1340 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 05 | ID | interior | Interior works
1339 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 04 | ID | interior | Interior works
1338 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 03 | ID | interior | Interior works
1337 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 02 | ID | interior | Interior works
1336 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 2 – ELEVATIONS 01 | ID | interior | Interior works
1330 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - WET BAR DETAILS (2 of 2) | ID | interior | Interior works
1329 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - WET BAR DETAILS (1 of 2) | ID | interior | Interior works
1328 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - WARDROBE DETAILS (3 of 3) | ID | interior | Interior works
1327 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - WARDROBE DETAILS (2 of 3) | ID | interior | Interior works
1326 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - WARDROBE DETAILS (1 of 3) | ID | interior | Interior works
1309 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 1 - WALL FINISHES PLAN | ID | interior | Interior works
1325 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - VANITY DETAILS | ID | interior | Interior works
1310 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 1 - REFLECTED CEILING PLAN | ID | interior | Interior works
1324 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1323 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1322 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - HEADBOARD DETAILS DOUBLE QUEEN | ID | interior | Interior works
1321 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 - HEADBOARD DETAILS | ID | interior | Interior works
1306 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 1 - GENERAL ARRANGEMENT PLAN 1:30 | ID | interior | Interior works
1307 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 1 - FURNITURE PLAN | ID | interior | Interior works
1308 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | FAENA SUITE TYPE 1 - FLOOR FINISHES PLAN | ID | interior | Interior works
1320 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 10 | ID | interior | Interior works
1319 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 09 | ID | interior | Interior works
1318 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 08 | ID | interior | Interior works
1317 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 07 | ID | interior | Interior works
1316 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 06 | ID | interior | Interior works
1315 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 05 | ID | interior | Interior works
1314 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 04 | ID | interior | Interior works
1313 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 03 | ID | interior | Interior works
1312 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 02 | ID | interior | Interior works
1311 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | FAENA SUITE TYPE 1 – ELEVATIONS 01 | ID | interior | Interior works
1652 | WS-WSH-687-0000-UBJ-SDW-AR-100-0001004_PDF | 0 | FAENA HOTEL,GRIDS AND COORDINATES SET OUT | AR | ARchitecture | Details
1590 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EXTERNAL JOINERY STATION – WATER/FRUIT DISPLAY AND DIRTY TOWEL STATION | ID | interior | Interior works
1592 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EXTERNAL JOINERY STATION – WAITER STATIONS AND WELLCOME PLINTH | ID | interior | Interior works
1591 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EXTERNAL JOINERY STATION – CLEAN TOWEL AND ARRIVAL AREA VALET PLINTH | ID | interior | Interior works
1408 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 - WARDROBE DETAILS (3 of 3) | ID | interior | Interior works
1407 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 - WARDROBE DETAILS (2 of 3) | ID | interior | Interior works
1406 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 - WARDROBE DETAILS (1 of 3) | ID | interior | Interior works
1405 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 - VANITY DETAILS | ID | interior | Interior works
1401 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 – ELEVATIONS 06 | ID | interior | Interior works
1400 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 – ELEVATIONS 05 | ID | interior | Interior works
1399 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 – ELEVATIONS 04 | ID | interior | Interior works
1398 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 – ELEVATIONS 03 | ID | interior | Interior works
1397 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 – ELEVATIONS 02 | ID | interior | Interior works
1396 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 3 – ELEVATIONS 01 | ID | interior | Interior works
1389 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 - WARDROBE DETAILS (2 of 3) | ID | interior | Interior works
1390 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 - WARDROBE DETAILS (2 of 3) | ID | interior | Interior works
1388 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 - WARDROBE DETAILS (1 of 3) | ID | interior | Interior works
1387 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 - VANITY DETAILS | ID | interior | Interior works
1383 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 – ELEVATIONS 06 | ID | interior | Interior works
1382 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 – ELEVATIONS 05 | ID | interior | Interior works
1381 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 – ELEVATIONS 04 | ID | interior | Interior works
1380 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 – ELEVATIONS 03 | ID | interior | Interior works
1379 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 – ELEVATIONS 02 | ID | interior | Interior works
1378 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 2 – ELEVATIONS 01 | ID | interior | Interior works
1371 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 - WARDROBE DETAILS (2 of 3) | ID | interior | Interior works
1372 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 - WARDROBE DETAILS (2 of 3) | ID | interior | Interior works
1370 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 - WARDROBE DETAILS (1 of 3) | ID | interior | Interior works
1369 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 - VANITY DETAILS | ID | interior | Interior works
1365 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 – ELEVATIONS 06 | ID | interior | Interior works
1364 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 – ELEVATIONS 05 | ID | interior | Interior works
1363 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 – ELEVATIONS 04 | ID | interior | Interior works
1362 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 – ELEVATIONS 03 | ID | interior | Interior works
1361 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 – ELEVATIONS 02 | ID | interior | Interior works
1360 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX.SUITE (K) TYPE 1 – ELEVATIONS 01 | ID | interior | Interior works
1394 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - WALL FINISHES PLAN | ID | interior | Interior works
1395 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - REFLECTED CEILING PLAN | ID | interior | Interior works
1404 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1403 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1402 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - HEADBOARD DETAILS | ID | interior | Interior works
1391 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1393 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - FLOOR FINISHES PLAN | ID | interior | Interior works
1392 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 3 - FURNITURE PLAN | ID | interior | Interior works
1376 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - WALL FINISHES PLAN | ID | interior | Interior works
1377 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - REFLECTED CEILING PLAN | ID | interior | Interior works
1386 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1385 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1384 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - HEADBOARD DETAILS | ID | interior | Interior works
1373 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1374 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - FURNITURE PLAN | ID | interior | Interior works
1375 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 2 - FLOOR FINISHES PLAN | ID | interior | Interior works
1358 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - WALL FINISHES PLAN | ID | interior | Interior works
1359 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - REFLECTED CEILING PLAN | ID | interior | Interior works
1368 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1367 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1366 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - HEADBOARD DETAILS | ID | interior | Interior works
1355 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1357 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - FLOOR FINISHES PLAN | ID | interior | Interior works
1356 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | EX SUITE (K) TYPE 1 - FURNITURE PLAN | ID | interior | Interior works
770 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-STP ROOM | AR | Architecture | Doors
764 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-SOUTH WING | AR | Architecture | Doors
765 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-SOUTH WING | AR | Architecture | Doors
763 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-NORTH WING | AR | Architecture | Doors
766 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-MAIN HOTEL | AR | Architecture | Doors
767 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-MAIN HOTEL | AR | Architecture | Doors
768 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-MAIN HOTEL | AR | Architecture | Doors
769 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DOOR MASTER SCHEDULE-FORUM,SP,PB & SPA | AR | Architecture | Doors
1421 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 2 - ELEVATIONS 04 | ID | interior | Interior works
1420 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 2 - ELEVATIONS 03 | ID | interior | Interior works
1419 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 2 - ELEVATIONS 02 | ID | interior | Interior works
1418 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 2 - ELEVATIONS 01 | ID | interior | Interior works
1425 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - WARDROBE DETAILS (2 of 2) | ID | interior | Interior works
1424 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - WARDROBE DETAILS (1 of 2) | ID | interior | Interior works
1412 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 – WALL FINISHES PLAN | ID | interior | Interior works
1413 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 – REFLECTED CEILING PLAN | ID | interior | Interior works
1423 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - KITCHEN DETAILS | ID | interior | Interior works
1409 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 – GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1411 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 – FLOOR FINISHES PLAN | ID | interior | Interior works
1410 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 – FURNITURE PLAN | ID | interior | Interior works
1417 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 - ELEVATIONS 04 | ID | interior | Interior works
1416 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 - ELEVATIONS 03 | ID | interior | Interior works
1415 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 - ELEVATIONS 02 | ID | interior | Interior works
1414 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX. 1BED SUITE (K) TYPE 1 - ELEVATIONS 01 | ID | interior | Interior works
1422 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | DLX 1BED SUITE (K) TYPE 1 & 2 - HEADBOARD DETAILS | ID | interior | Interior works
726 | WS-WSH-687-0000-UBJ-SDW-AR-XX-XXXX | 0 | DETAILS EXPANSION JOINT & WALL PROTECTION DETAIL | AR | Architecture | Details
1622 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | CP-40 LOADING ID SIGN | SIGN | Interior | Wayfinding
1621 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | CP-30 COLUMN ID SIGN | SIGN | Interior | Wayfinding
1651 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | BH-60 BOH STAIRCASE ID SIGN | SIGN | Interior | Wayfinding
1636 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | BH-50 BOH LEVEL ID / LIFT STATUTORY SIGN | SIGN | Interior | Wayfinding
1635 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | BH-30 BOH FACILITY ID SIGN, TEXT | SIGN | Interior | Wayfinding
1634 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | BH-20 BOH ROOM ID SIGN, DOOR MOUNTED | SIGN | Interior | Wayfinding
1632 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | BH-11 BOH ROOM ID SIGN,GLASS MOUNTED | SIGN | Interior | Wayfinding
1633 | WS-WSH-687-0000-UBJ-SDW-SF-XX-XXXXX | 0 | BH-10 BOH ROOM ID SIGN, WALL MOUNTED | SIGN | Interior | Wayfinding
638 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ARCADES (3) - DETAILED PLANS & SECTIONS | AR | Architecture | Details
637 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ARCADES (2) - DETAILED PLANS & SECTIONS | AR | Architecture | Details
636 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | ARCADES (1) - DETAILED PLANS & SECTIONS | AR | Architecture | Details
779 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES - WALL FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
789 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – VANITY DETAILS | ID | interior | Interior works
790 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – TYPICAL DETAILS | ID | interior | Interior works
780 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES - REFLECTED CEILING PLAN - GROUND FLOOR | ID | interior | Interior works
788 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – RECEPTION DESK | ID | interior | Interior works
776 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES - GENERAL ARRANGEMENT PLAN - GROUND FLOOR 1:50 | ID | interior | Interior works
777 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
778 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES - FLOOR FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
787 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 07 | ID | interior | Interior works
786 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 06 | ID | interior | Interior works
785 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 05 | ID | interior | Interior works
784 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 04 | ID | interior | Interior works
783 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 03 | ID | interior | Interior works
782 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 02 | ID | interior | Interior works
781 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – ELEVATION 01 | ID | interior | Interior works
797 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (7 of 7) | ID | interior | Interior works
796 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (6 of 7) | ID | interior | Interior works
795 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (5 of 7) | ID | interior | Interior works
794 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (4 of 7) | ID | interior | Interior works
793 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (3 of 7) | ID | interior | Interior works
792 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (2 of 7) | ID | interior | Interior works
791 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | AMENITIES – DOOR DETAILS (1 of 7) | ID | interior | Interior works
773 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 6-BEDROOM VILLA - DOORS SCHEDULE & TYPOLOGY | AR | Architecture | Doors
712 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 6 BEDROOM VILLA - TYPICAL WALL SECTION-2 | AR | Architecture | Details
711 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 6 BEDROOM VILLA - TYPICAL WALL SECTION-1 | AR | Architecture | Details
709 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 6 BEDROOM VILLA - TYPICAL TOILET DETAILED PLANS & ELEVATION | AR | Architecture | Details
710 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 6 BEDROOM VILLA - TYPICAL STAIR DETAILED PLAN & SECTIONS | AR | Architecture | Details
752 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 6 Bedroom Villa - Level L0 & L1 - Typical BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
871 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – WALL FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
872 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – WALL FINISHES PLAN - FIRST FLOOR | ID | interior | Interior works
873 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – REFLECTED CEILING PLAN - GROUND FLOOR | ID | interior | Interior works
874 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – REFLECTED CEILING PLAN - FIRST FLOOR | ID | interior | Interior works
882 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - POWDER ROOM ELEVATIONS | ID | interior | Interior works
880 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - OPEN KITCHEN ELEVATIONS | ID | interior | Interior works
888 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - MASTER DRESSING ELEVATIONS | ID | interior | Interior works
887 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - MASTER BEDROOM ELEVATIONS | ID | interior | Interior works
889 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - MASTER BATHROOM ELEVATIONS | ID | interior | Interior works
877 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – MAJILS ELEVATIONS | ID | interior | Interior works
879 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - LIVING ELEVATIONS | ID | interior | Interior works
886 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - LIVING ELEVATIONS | ID | interior | Interior works
881 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – LIFT LOBBY ELEVATIONS | ID | interior | Interior works
902 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - HALLWAY SECOND FLOOR | ID | interior | Interior works
876 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - HALLWAY ELEVATIONS | ID | interior | Interior works
865 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - GENERAL ARRANGEMENT PLAN - GROUND FLOOR 1:50 | ID | interior | Interior works
866 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - GENERAL ARRANGEMENT PLAN - FIRST FLOOR 1:50 | ID | interior | Interior works
867 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
868 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - FURNITURE PLAN - FIRST FLOOR | ID | interior | Interior works
875 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - FOYER ELEVATIONS | ID | interior | Interior works
869 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - FLOOR FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
870 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – FLOOR FINISHES PLAN - FIRST FLOOR | ID | interior | Interior works
891 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - DRESSING ELEVATIONS | ID | interior | Interior works
894 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - DRESSING ELEVATIONS | ID | interior | Interior works
900 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - DRESSING 5 ELEVATIONS | ID | interior | Interior works
897 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - DRESSING 4 ELEVATIONS | ID | interior | Interior works
885 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA – DRESSING ELEVATIONS | ID | interior | Interior works
878 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - DINING ELEVATIONS | ID | interior | Interior works
899 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BEDROOM 5 ELEVATIONS | ID | interior | Interior works
896 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BEDROOM 4 ELEVATIONS | ID | interior | Interior works
893 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BEDROOM 3 ELEVATIONS | ID | interior | Interior works
890 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BEDROOM 2 ELEVATIONS | ID | interior | Interior works
883 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BEDROOM 1 ELEVATIONS | ID | interior | Interior works
901 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BATHROOM 5 ELEVATIONS | ID | interior | Interior works
898 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BATHROOM 4 ELEVATIONS | ID | interior | Interior works
895 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BATHROOM 3 ELEVATIONS | ID | interior | Interior works
892 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BATHROOM 2 ELEVATIONS | ID | interior | Interior works
884 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 6 BED VILLA - BATHROOM 1 ELEVATIONS | ID | interior | Interior works
707 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 5 BEDROOM VILLA - TYPICAL WALL SECTIONS-2 | AR | Architecture | Details
706 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 5 BEDROOM VILLA - TYPICAL WALL SECTIONS-1 | AR | Architecture | Details
708 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 5 BEDROOM VILLA - TYPICAL TOILET DETAILED PLANS & ELEVATION | AR | Architecture | Details
705 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 5 BEDROOM VILLA - TYPICAL STAIR DETAILED PLAN & SECTIONS | AR | Architecture | Details
751 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 5 Bedroom Villa - Level L0 & L1 - Typical BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
772 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 5 BEDROOM VILLA - DOORS SCHEDULE & TYPOLOGY | AR | Architecture | Doors
836 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - WALL FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
837 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - WALL FINISHES PLAN - FIRST FLOOR | ID | interior | Interior works
838 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - REFLECTED CEILING PLAN - GROUND FLOOR | ID | interior | Interior works
839 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - REFLECTED CEILING PLAN - FIRST FLOOR | ID | interior | Interior works
847 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - POWDER ROOM ELEVATIONS | ID | interior | Interior works
845 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - OPEN KITCHEN ELEVATIONS | ID | interior | Interior works
852 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - MASTER DRESSING ELEVATIONS | ID | interior | Interior works
851 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - MASTER BEDROOM ELEVATIONS | ID | interior | Interior works
853 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - MASTER BATHROOM ELEVATIONS | ID | interior | Interior works
842 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA – MAJILS ELEVATIONS | ID | interior | Interior works
863 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA – LIVING SECOND FLOOR | ID | interior | Interior works
844 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - LIVING ELEVATIONS | ID | interior | Interior works
846 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA – LIFT LOBBY ELEVATIONS | ID | interior | Interior works
864 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA – HALLWAY SECOND FLOOR | ID | interior | Interior works
841 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - HALLWAY ELEVATIONS | ID | interior | Interior works
830 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - GENERAL ARRANGEMENT PLAN - GROUND FLOOR 1:50 | ID | interior | Interior works
831 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - GENERAL ARRANGEMENT PLAN - FIRST FLOOR 1:50 | ID | interior | Interior works
832 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
833 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - FURNITURE PLAN - FIRST FLOOR | ID | interior | Interior works
840 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - FOYER ELEVATIONS | ID | interior | Interior works
834 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - FLOOR FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
835 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - FLOOR FINISHES PLAN - FIRST FLOOR | ID | interior | Interior works
855 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - DRESSING ELEVATIONS | ID | interior | Interior works
858 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - DRESSING ELEVATIONS | ID | interior | Interior works
861 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - DRESSING 4LEVATIONS | ID | interior | Interior works
850 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA – DRESSING 1 ELEVATIONS | ID | interior | Interior works
843 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - DINING ELEVATIONS | ID | interior | Interior works
860 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BEDROOM 4 ELEVATIONS | ID | interior | Interior works
857 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BEDROOM 3 ELEVATIONS | ID | interior | Interior works
854 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BEDROOM 2 ELEVATIONS | ID | interior | Interior works
848 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BEDROOM 1 ELEVATIONS | ID | interior | Interior works
862 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BATHROOM 4 ELEVATIONS | ID | interior | Interior works
859 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BATHROOM 3 ELEVATIONS | ID | interior | Interior works
856 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BATHROOM 2 ELEVATIONS | ID | interior | Interior works
849 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 5 BED VILLA - BATHROOM 1 ELEVATIONS | ID | interior | Interior works
771 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4-BEDROOM VILLA - DOOR SCHEDULE & TYPOLOGY | AR | Architecture | Doors
702 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4 BEDROOM VILLA - TYPICAL WALL SECTIONS-2 | AR | Architecture | Details
701 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4 BEDROOM VILLA - TYPICAL WALL SECTIONS-1 | AR | Architecture | Details
703 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4 BEDROOM VILLA - TYPICAL TOILET DETAILED PLANS & ELEVATION | AR | Architecture | Details
704 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4 BEDROOM VILLA - TYPICAL TOILET DETAILED PLANS & ELEVATION | AR | Architecture | Details
700 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4 BEDROOM VILLA - TYPICAL STAIR DETAILED PLAN & SECTIONS | AR | Architecture | Details
750 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | 4 Bedroom Villa - Level L0 & L1 - Typical BOH Room Finishes Schedule | AR | Architecture | Finishes Schedules
804 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - WALL FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
805 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - WALL FINISHES PLAN - FIRST FLOOR | ID | interior | Interior works
806 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - REFLECTED CEILING PLAN - GROUND FLOOR | ID | interior | Interior works
807 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - REFLECTED CEILING PLAN - FIRST FLOOR | ID | interior | Interior works
815 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - POWDER ROOM ELEVATIONS | ID | interior | Interior works
813 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - OPEN KITCHEN ELEVATIONS | ID | interior | Interior works
821 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - MASTER DRESSING ELEVATIONS | ID | interior | Interior works
820 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - MASTER BEDROOM ELEVATIONS | ID | interior | Interior works
822 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - MASTER BATHROOM ELEVATIONS | ID | interior | Interior works
810 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – MAJILS ELEVATIONS | ID | interior | Interior works
819 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – LIVING SECOND FLOOR ELEVATIONS | ID | interior | Interior works
829 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – LIVING SECOND FLOOR | ID | interior | Interior works
812 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - LIVING ELEVATIONS | ID | interior | Interior works
814 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – LIFT LOBBY ELEVATIONS | ID | interior | Interior works
809 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - HALLWAY ELEVATIONS | ID | interior | Interior works
798 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - GENERAL ARRANGEMENT PLAN - GROUND FLOOR 1:50 | ID | interior | Interior works
799 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - GENERAL ARRANGEMENT PLAN - FIRST FLOOR 1:50 | ID | interior | Interior works
800 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - FURNITURE PLAN - GROUND FLOOR | ID | interior | Interior works
801 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - FURNITURE PLAN - FIRST FLOOR | ID | interior | Interior works
808 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - FOYER ELEVATIONS | ID | interior | Interior works
802 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - FLOOR FINISHES PLAN - GROUND FLOOR | ID | interior | Interior works
803 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - FLOOR FINISHES PLAN - FIRST FLOOR | ID | interior | Interior works
827 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – DRESSING 3 ELEVATIONS | ID | interior | Interior works
824 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – DRESSING 2 ELEVATIONS | ID | interior | Interior works
818 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA – DRESSING 1 ELEVATIONS | ID | interior | Interior works
811 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - DINING ELEVATIONS | ID | interior | Interior works
826 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - BEDROOM 3 ELEVATIONS | ID | interior | Interior works
823 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - BEDROOM 2 ELEVATIONS | ID | interior | Interior works
816 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - BEDROOM 1 ELEVATIONS | ID | interior | Interior works
828 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - BATHROOM 3 ELEVATIONS | ID | interior | Interior works
825 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - BATHROOM 2 ELEVATIONS | ID | interior | Interior works
817 | WS-WSH-687-3235-UBJ-SDW-ID-XX-XXXX | 0 | 4 BED VILLA - BATHROOM 1 ELEVATIONS | ID | interior | Interior works
1305 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - WARDROBE DETAILS (2 of 2) | ID | interior | Interior works
1304 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - WARDROBE DETAILS (1 of 2) | ID | interior | Interior works
1290 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | 2 BED SUITE (K&K) - WALL FINISHES PLAN | ID | interior | Interior works
1303 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - VANITY DETAILS | ID | interior | Interior works
1291 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | 2 BED SUITE (K&K) - REFLECTED CEILING PLAN | ID | interior | Interior works
1302 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works
1301 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works
1300 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - HEADBOARD DETAILS | ID | interior | Interior works
1287 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | 2 BED SUITE (K&K) - GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works
1289 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | 2 BED SUITE (K&K) - FLOOR FINISHES PLAN | ID | interior | Interior works
1299 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 08 | ID | interior | Interior works
1298 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 07 | ID | interior | Interior works
1297 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 06 | ID | interior | Interior works
1296 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 05 | ID | interior | Interior works
1295 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 04 | ID | interior | Interior works
1294 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 03 | ID | interior | Interior works
1293 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 02 | ID | interior | Interior works
1292 | WS-WSH-687-3230-UBJ-SDW-ID-XX-XXXX | 0 | 2 BED SUITE (K&K) - ELEVATIONS 01 | ID | interior | Interior works
1288 | WS-WSH-687-3230-UBJ-SDW-AR-XX-XXXX | 0 | 2 BED SUITE (K&K) - FURNITURE PLAN | ID | interior | Interior works
295 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Block Work Details | AR | Architecture | Block Works
296 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Block Work Details | AR | Architecture | Block Works
297 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Block Work Details | AR | Architecture | Block Works
298 | WS-WSH-687-3235-UBJ-SDW-AR-XX-XXXX | 0 | Block Work Details | AR | Architecture | Block Works

## Sheet5
Sr/No | Drawing Number | Rev. No. | Description |  | Discipline | Trade | Activity / Package | Submission Date
JR SUITE (K) TYPE 2
1426 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306301 | 0 | JR SUITE (K) TYPE 2 - | GENERAL ARRANGEMENT PLAN | ID | interior | Interior works | 2025-07-31
1427 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306302 | 0 | JR SUITE (K) TYPE 2 - | FURNITURE PLAN | ID | interior | Interior works | 2025-07-31
1428 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306303 | 0 | JR SUITE (K) TYPE 2 - | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-07-31
1429 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306304 | 0 | JR SUITE (K) TYPE 2 - | WALL FINISHES PLAN | ID | interior | Interior works | 2025-07-31
1430 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306305 | 0 | JR SUITE (K) TYPE 2 - | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-07-31
1432 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306306 | 0 | JR SUITE (K) TYPE 2 - | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-07-31
1433 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306307 | 0 | JR SUITE (K) TYPE 2 - | BEDROOM ELEVATIONS | ID | interior | Interior works | 2025-07-31
1434 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306308 | 0 | JR SUITE (K) TYPE 2 - | BATHROOM ELEVATIONS | ID | interior | Interior works | 2025-07-31
1435 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306309 | 0 | JR SUITE (K) TYPE 2 - | TOILET ELEVATIONS & SHOWER ELEVATIONS | ID | interior | Interior works | 2025-07-31
1436 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306310 | 0 | JR SUITE (K) TYPE 2 - | DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-07-31
1437 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306311 | 0 | JR SUITE (K) TYPE 2 - | HEADBOARD DETAILS | ID | interior | Interior works | 2025-07-31
1438 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306312 | 0 | JR SUITE (K) TYPE 2 - | TYPE 1 & 2 - VANITY DETAILS | ID | interior | Interior works | 2025-07-31
1439 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306313 | 0 | JR SUITE (K) TYPE 2 - | TYPE 1 & 2 - WARDROBE DETAILS | ID | interior | Interior works | 2025-07-31
1440 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306314 | 0 | JR SUITE (K) TYPE 2 - | TYPE 1 & 2 - FLOORS DETAILS 1 | ID | interior | Interior works | submit separately
1441 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306315 | 0 | JR SUITE (K) TYPE 2 - | TYPE 1 & 2 - FLOORS DETAILS 2 | ID | interior | Interior works | submit separately
1442 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306316 | 0 | JR SUITE (K) TYPE 2 - | TYPE 1 & 2 - CEILING DETAILS 1 | ID | interior | Interior works | submit separately
1443 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306317 | 0 | JR SUITE (K) TYPE 2 - | TYPE 1 & 2 - CEILING DETAILS 2 | ID | interior | Interior works | submit separately
JR SUITE (Q/Q) TYPE 1
1444 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306001 | 0 | JR SUITE (Q/Q) TYPE 1- | GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works | 2025-08-31
1445 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306002 | 0 | JR SUITE (Q/Q) TYPE 1- | FURNITURE PLAN | ID | interior | Interior works | 2025-08-31
1446 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306003 | 0 | JR SUITE (Q/Q) TYPE 1- | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-08-31
1447 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306004 | 0 | JR SUITE (Q/Q) TYPE 1- | WALL FINISHES PLAN | ID | interior | Interior works | 2025-08-31
1448 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306005 | 0 | JR SUITE (Q/Q) TYPE 1- | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-08-31
1450 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306006 | 0 | JR SUITE (Q/Q) TYPE 1- | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1451 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306007 | 0 | JR SUITE (Q/Q) TYPE 1- | BEDROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1452 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306008 | 0 | JR SUITE (Q/Q) TYPE 1- | BATHROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1453 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306009 | 0 | JR SUITE (Q/Q) TYPE 1- | TOILET ELEVATIONS & SHOWER ELEVATIONS | ID | interior | Interior works | 2025-08-31
1454 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306010 | 0 | JR SUITE (Q/Q) TYPE 1- | DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-07-31
1455 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306011 | 0 | JR SUITE (Q/Q) TYPE 1- | HEADBOARD DETAILS | ID | interior | Interior works | 2025-08-31
1456 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306012 | 0 | JR SUITE (Q/Q) TYPE 1- | TYPE 1 & 2 - VANITY DETAILS | ID | interior | Interior works | 2025-08-31
1457 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306013 | 0 | JR SUITE (Q/Q) TYPE 1- | TYPE 1 & 2 - WARDROBE DETAILS | ID | interior | Interior works | 2025-08-31
1458 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306014 | 0 | JR SUITE (Q/Q) TYPE 1- | TYPE 1 & 2 - FLOORS DETAILS 1 | ID | interior | Interior works | 2025-08-31
1459 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306015 | 0 | JR SUITE (Q/Q) TYPE 1- | TYPE 1 & 2 - FLOORS DETAILS 2 | ID | interior | Interior works | 2025-07-31
1460 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306016 | 0 | JR SUITE (Q/Q) TYPE 1- | TYPE 1 & 2 - CEILING DETAILS 1 | ID | interior | Interior works | 2025-08-31
1461 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306017 | 0 | JR SUITE (Q/Q) TYPE 1- | TYPE 1 & 2 - CEILING DETAILS 2 | ID | interior | Interior works | 2025-08-31
EX SUITE (K) TYPE 1
1462 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306201 | 0 | EX SUITE (K) TYPE 1 - | GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works | 2025-08-31
1463 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306202 | 0 | EX SUITE (K) TYPE 1 - | FURNITURE PLAN | ID | interior | Interior works | 2025-08-31
1464 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306203 | 0 | EX SUITE (K) TYPE 1 - | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-08-31
1465 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306204 | 0 | EX SUITE (K) TYPE 1 - | WALL FINISHES PLAN | ID | interior | Interior works | 2025-08-31
1466 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306205 | 0 | EX SUITE (K) TYPE 1 - | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-08-31
1468 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306206 | 0 | EX SUITE (K) TYPE 1 - | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1469 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306207 | 0 | EX SUITE (K) TYPE 1 - | DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1470 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306208 | 0 | EX SUITE (K) TYPE 1 - | MASTER DRESSING ROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-08-31
1471 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306209 | 0 | EX SUITE (K) TYPE 1 - | MASTER DRESSING ROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-08-31
1472 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306210 | 0 | EX SUITE (K) TYPE 1 - | BEDROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1473 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306211 | 0 | EX SUITE (K) TYPE 1 - | POWDER ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1474 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306212 | 0 | EX SUITE (K) TYPE 1 - | KITCHEN ELEVATIONS | ID | interior | Interior works | 2025-08-31
1475 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306213 | 0 | EX SUITE (K) TYPE 1 - | BATHROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1476 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306214 | 0 | EX SUITE (K) TYPE 1 - | TOILET ELEVATIONS & SHOWER ELEVATIONS | ID | interior | Interior works | 2025-08-31
1477 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306215 | 0 | EX SUITE (K) TYPE 1 - | HEADBOARD DETAILS | ID | interior | Interior works | 2025-08-31
1478 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306216 | 0 | EX SUITE (K) TYPE 1 - | KITCHEN DETAILS (1 of 2) | ID | interior | Interior works | 2025-08-31
1479 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306217 | 0 | EX SUITE (K) TYPE 1 - | KITCHEN DETAILS (2 of 2) | ID | interior | Interior works | 2025-08-31
1480 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306218 | 0 | EX SUITE (K) TYPE 1 - | VANITY DETAILS | ID | interior | Interior works | 2025-08-31
1481 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306219 | 0 | EX SUITE (K) TYPE 1 - | WARDROBE DETAILS (1 of 3) | ID | interior | Interior works | 2025-08-31
1482 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306220 | 0 | EX SUITE (K) TYPE 1 - | WARDROBE DETAILS (2 of 3) | ID | interior | Interior works | 2025-08-31
1483 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306221 | 0 | EX SUITE (K) TYPE 1 - | WARDROBE DETAILS (3 of 3) | ID | interior | Interior works | 2025-08-31
1484 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306222 | 0 | EX SUITE (K) TYPE 1 - | FLOORS DETAILS 1 | ID | interior | Interior works | 2025-08-31
1485 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306223 | 0 | EX SUITE (K) TYPE 1 - | FLOORS DETAILS 2 | ID | interior | Interior works | 2025-08-31
1486 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306224 | 0 | EX SUITE (K) TYPE 1 - | CEILING DETAILS 1 | ID | interior | Interior works | 2025-08-31
1487 | WS-WSH-687-3230-UBJ-SDW-ID-500-1306225 | 0 | EX SUITE (K) TYPE 1 - | CEILING DETAILS 2 | ID | interior | Interior works | 2025-08-31
DLX. 1BED SUITE (K) TYPE 2
1488 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305801 | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - | GENERAL ARRANGEMENT PLAN | ID | interior | Interior works | 2025-08-31
1489 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305802 | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - | FURNITURE PLAN | ID | interior | Interior works | 2025-08-31
1490 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305803 | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-08-31
1491 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305804 | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - | WALL FINISHES PLAN | ID | interior | Interior works | 2025-08-31
1492 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305805 | 0 | DLX. 1BED SUITE (K) TYPE 1 & 2 - | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-08-31
1494 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305806 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | LIVING ROOM & DINING ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1495 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305807 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1496 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305808 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | POWDER ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1497 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305809 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | BEDROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1498 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305810 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | MASTER DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1499 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305811 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | BATHROOM ELEVATIONS | ID | interior | Interior works | 2025-08-31
1500 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305812 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | TOILET ELEVATIONS & SHOWER ELEVATIONS | ID | interior | Interior works | 2025-08-31
1501 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305813 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | HEADBOARD DETAILS | ID | interior | Interior works | 2025-08-31
1502 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305814 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | VANITY DETAILS | ID | interior | Interior works | 2025-08-31
1503 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305815 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | WARDROBE DETAILS (1 of 2) | ID | interior | Interior works | 2025-08-31
1504 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305816 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | WARDROBE DETAILS (2 of 2) | ID | interior | Interior works | 2025-08-31
1505 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305817 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | FLOORS DETAILS 1 | ID | interior | Interior works | 2025-08-31
1506 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305818 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | FLOORS DETAILS 2 | ID | interior | Interior works | 2025-08-31
1507 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305819 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | CEILING DETAILS 1 | ID | interior | Interior works | 2025-08-31
1508 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305820 | 0 | DLX. 1BED SUITE (K) TYPE 2 - | CEILING DETAILS 2 | ID | interior | Interior works | 2025-08-31
PREM. 1 BED SUITE (K) TYPE 3
1509 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305201 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works | 2025-09-30
1510 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305202 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | FURNITURE PLAN | ID | interior | Interior works | 2025-09-30
1511 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305203 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-09-30
1512 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305204 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | WALL FINISHES PLAN | ID | interior | Interior works | 2025-09-30
1513 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305205 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-09-30
1515 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305206 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1516 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305207 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1517 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305208 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | POWDER ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1518 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305209 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | BEDROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1519 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305210 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | MASTER DRESSING ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1520 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305211 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | BATHROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1521 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305212 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | TOILET ELEVATIONS & SHOWER ELEVATIONS | ID | interior | Interior works | 2025-09-30
1522 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305213 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | KITCHEN ELEVATIONS | ID | interior | Interior works | 2025-09-30
1523 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305214 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | HEADBOARD DETAILS | ID | interior | Interior works | 2025-09-30
1524 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305215 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | VANITY DETAILS | ID | interior | Interior works | 2025-09-30
1525 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305216 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | WARDROBE DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30
1526 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305217 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | WARDROBE DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30
1527 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305218 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | FLOORS DETAILS 1 | ID | interior | Interior works | 2025-09-30 | FAENA SUITE TYPE 2 – CEILING DETAILS 2
1528 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305219 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | FLOORS DETAILS 2 | ID | interior | Interior works | 2025-09-30
1529 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305220 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | CEILING DETAILS 1 | ID | interior | Interior works | 2025-09-30
1530 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305221 | 0 | PREM. 1 BED SUITE (K) TYPE 3 - | CEILING DETAILS 2 | ID | interior | Interior works | 2025-09-30
2 BED SUITE (K&K)
1531 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305301 | 0 | 2 BED SUITE (K&K) - | GENERAL ARRANGEMENT PLAN 1:25 | ID | interior | Interior works | 2025-09-30
1532 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305302 | 0 | 2 BED SUITE (K&K) - | FURNITURE PLAN | ID | interior | Interior works | 2025-09-30
1533 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305303 | 0 | 2 BED SUITE (K&K) - | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-09-30
1534 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305304 | 0 | 2 BED SUITE (K&K) - | WALL FINISHES PLAN | ID | interior | Interior works | 2025-09-30
1535 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305305 | 0 | 2 BED SUITE (K&K) - | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-09-30
1537 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305306 | 0 | 2 BED SUITE (K&K) - | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1538 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305307 | 0 | 2 BED SUITE (K&K) - | DINING ROOM ELEVATION | ID | interior | Interior works | 2025-09-30
1539 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305308 | 0 | 2 BED SUITE (K&K) - | POWDER ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1540 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305309 | 0 | 2 BED SUITE (K&K) - | DRESSING ROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1541 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305310 | 0 | 2 BED SUITE (K&K) - | BEDROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1542 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305311 | 0 | 2 BED SUITE (K&K) - | DRESSING ROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1543 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305312 | 0 | 2 BED SUITE (K&K) - | BATHROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1544 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305313 | 0 | 2 BED SUITE (K&K) - | TOILET 1 ELEVATIONS & SHOWER 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1545 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305314 | 0 | 2 BED SUITE (K&K) - | BEDROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1546 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305315 | 0 | 2 BED SUITE (K&K) - | DRESSING ROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1547 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305316 | 0 | 2 BED SUITE (K&K) - | BATHROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1548 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305317 | 0 | 2 BED SUITE (K&K) - | TOILET 2 ELEVATIONS & SHOWER 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1549 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305318 | 0 | 2 BED SUITE (K&K) - | KITCHEN ELEVATIONS | ID | interior | Interior works | 2025-09-30
1550 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305319 | 0 | 2 BED SUITE (K&K) - | HEADBOARD DETAILS | ID | interior | Interior works | 2025-09-30
1551 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305320 | 0 | 2 BED SUITE (K&K) - | KITCHEN DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30
1552 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305321 | 0 | 2 BED SUITE (K&K) - | KITCHEN DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30
1553 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305322 | 0 | 2 BED SUITE (K&K) - | VANITY DETAILS | ID | interior | Interior works | 2025-09-30
1554 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305323 | 0 | 2 BED SUITE (K&K) - | WARDROBE DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30
1555 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305324 | 0 | 2 BED SUITE (K&K) - | WARDROBE DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30
1556 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305325 | 0 | 2 BED SUITE (K&K) - | FLOORS DETAILS 1 | ID | interior | Interior works | 2025-09-30
1557 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305326 | 0 | 2 BED SUITE (K&K) - | FLOORS DETAILS 2 | ID | interior | Interior works | 2025-09-30
1558 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305327 | 0 | 2 BED SUITE (K&K) - | CEILING DETAILS 1 | ID | interior | Interior works | 2025-09-30
1559 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305328 | 0 | 2 BED SUITE (K&K) - | CEILING DETAILS 2 | ID | interior | Interior works | 2025-09-30
FAENA SUITE TYPE 1
1560 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305401 | 0 | FAENA SUITE TYPE 1 - | GENERAL ARRANGEMENT PLAN 1:30 | ID | interior | Interior works | 2025-09-30
1561 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305402 | 0 | FAENA SUITE TYPE 1 - | FURNITURE PLAN | ID | interior | Interior works | 2025-09-30
1562 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305403 | 0 | FAENA SUITE TYPE 1 - | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-09-30 | LIVING ROOM ELEVATIONS
1563 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305404 | 0 | FAENA SUITE TYPE 1 - | WALL FINISHES PLAN | ID | interior | Interior works | 2025-09-30 | DINING ROOM ELEVATION
1564 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305405 | 0 | FAENA SUITE TYPE 1 - | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-09-30 | LOBBY ELEVATIONS
1566 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305406 | 0 | FAENA SUITE TYPE 1 - | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30 | POWDER ROOM ELEVATIONS
1567 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305407 | 0 | FAENA SUITE TYPE 1 - | DINING ROOM ELEVATION | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM ELEVATIONS
1568 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305408 | 0 | FAENA SUITE TYPE 1 - | POWDER ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30 | KITCHEN ROOM ELEVATIONS
1569 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305409 | 0 | FAENA SUITE TYPE 1 - | DRESSING ROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | BEDROOM 1 ROOM ELEVATIONS
1570 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305410 | 0 | FAENA SUITE TYPE 1 - | BEDROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | BATHROOM 1 ELEVATIONS
1571 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305411 | 0 | FAENA SUITE TYPE 1 - | DRESSING ROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | TOILET 1 ELEVATIONS
1572 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305412 | 0 | FAENA SUITE TYPE 1 - | BATHROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | SHOWER 1 ELEVATIONS
1573 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305413 | 0 | FAENA SUITE TYPE 1 - | TOILET 1 ELEVATIONS & SHOWER 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM 1-1 ELEVATIONS
1574 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305414 | 0 | FAENA SUITE TYPE 1 - | BEDROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM 1-2 ELEVATIONS
1575 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305415 | 0 | FAENA SUITE TYPE 1 - | DRESSING ROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | BEDROOM 2 ROOM ELEVATIONS
1576 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305416 | 0 | FAENA SUITE TYPE 1 - | BATHROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | BATHROOM 2 ELEVATIONS
1577 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305417 | 0 | FAENA SUITE TYPE 1 - | TOILET 2 ELEVATIONS & SHOWER 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | TOILET 2 ELEVATIONS
1578 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305418 | 0 | FAENA SUITE TYPE 1 - | BEDROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | SHOWER 2 ELEVATIONS
1579 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305419 | 0 | FAENA SUITE TYPE 1 - | DRESSING ROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM 2-1 ELEVATIONS
1580 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305420 | 0 | FAENA SUITE TYPE 1 - | BATHROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM 2-2 ELEVATIONS
1581 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305421 | 0 | FAENA SUITE TYPE 1 - | TOILET 3 ELEVATIONS & SHOWER 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30 | BEDROOM 3 ROOM ELEVATIONS
1582 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305422 | 0 | FAENA SUITE TYPE 1 - | HEADBOARD DETAILS | ID | interior | Interior works | 2025-09-30 | BATHROOM 3 ELEVATIONS
1583 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305423 | 0 | FAENA SUITE TYPE 1 - | HEADBOARD DETAILS DOUBLE QUEEN | ID | interior | Interior works | 2025-09-30 | TOILET 3 ELEVATIONS
1584 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305424 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30 | SHOWER 3 ELEVATIONS
1585 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305425 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM 3-1 ELEVATIONS
1586 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305426 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - VANITY DETAILS | ID | interior | Interior works | 2025-09-30 | DRESSING ROOM 3-2 ELEVATIONS
1587 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305427 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - WARDROBE DETAILS (1 of 4) | ID | interior | Interior works | 2025-09-30
1588 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305428 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - WARDROBE DETAILS (2 of 4) | ID | interior | Interior works | 2025-09-30
1589 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305429 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - WARDROBE DETAILS (3 of 4) | ID | interior | Interior works | 2025-09-30
1590 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305430 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - WARDROBE DETAILS (4 of 4) | ID | interior | Interior works | 2025-09-30
1591 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305431 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - WET BAR DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30
1592 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305432 | 0 | FAENA SUITE TYPE 1 - | FAENA SUITE TYPE 1 - WET BAR DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30
1593 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305433 | 0 | FAENA SUITE TYPE 1 - | FLOORS DETAILS 1 | ID | interior | Interior works | 2025-09-30
1594 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305434 | 0 | FAENA SUITE TYPE 1 - | FLOORS DETAILS 2 | ID | interior | Interior works | 2025-09-30
1595 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305435 | 0 | FAENA SUITE TYPE 1 - | FLOORS DETAILS 3 | ID | interior | Interior works | 2025-09-30
1596 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305436 | 0 | FAENA SUITE TYPE 1 - | CEILING DETAILS 1 | ID | interior | Interior works | 2025-09-30
1597 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305437 | 0 | FAENA SUITE TYPE 1 - | CEILING DETAILS 2 | ID | interior | Interior works | 2025-09-30
1598 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305438 | 0 | FAENA SUITE TYPE 1 - | CEILING DETAILS 3 | ID | interior | Interior works | 2025-09-30
FAENA SUITE TYPE 2
1599 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305501 | 0 | FAENA SUITE TYPE 2 – | GENERAL ARRANGEMENT PLAN 1:30 | ID | interior | Interior works | 2025-09-30
1600 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305502 | 0 | FAENA SUITE TYPE 2 – | FURNITURE PLAN | ID | interior | Interior works | 2025-09-30
1601 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305503 | 0 | FAENA SUITE TYPE 2 – | FLOOR FINISHES PLAN | ID | interior | Interior works | 2025-09-30
1602 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305504 | 0 | FAENA SUITE TYPE 2 – | WALL FINISHES PLAN | ID | interior | Interior works | 2025-09-30
1603 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305505 | 0 | FAENA SUITE TYPE 2 – | REFLECTED CEILING PLAN | ID | interior | Interior works | 2025-09-30
1605 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305506 | 0 | FAENA SUITE TYPE 2 – | LIVING ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1606 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305507 | 0 | FAENA SUITE TYPE 2 – | DINING ROOM ELEVATION | ID | interior | Interior works | 2025-09-30
1607 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305508 | 0 | FAENA SUITE TYPE 2 – | POWDER ROOM ELEVATIONS | ID | interior | Interior works | 2025-09-30
1608 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305509 | 0 | FAENA SUITE TYPE 2 – | DRESSING ROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1609 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305510 | 0 | FAENA SUITE TYPE 2 – | BEDROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1610 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305511 | 0 | FAENA SUITE TYPE 2 – | DRESSING ROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1611 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305512 | 0 | FAENA SUITE TYPE 2 – | BATHROOM 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1612 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305513 | 0 | FAENA SUITE TYPE 2 – | TOILET 1 ELEVATIONS & SHOWER 1 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1613 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305514 | 0 | FAENA SUITE TYPE 2 – | BEDROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1614 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305515 | 0 | FAENA SUITE TYPE 2 – | DRESSING ROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1615 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305516 | 0 | FAENA SUITE TYPE 2 – | BATHROOM 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1616 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305517 | 0 | FAENA SUITE TYPE 2 – | TOILET 2 ELEVATIONS & SHOWER 2 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1617 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305518 | 0 | FAENA SUITE TYPE 2 – | BEDROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1618 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305519 | 0 | FAENA SUITE TYPE 2 – | DRESSING ROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1619 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305520 | 0 | FAENA SUITE TYPE 2 – | BATHROOM 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1620 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305521 | 0 | FAENA SUITE TYPE 2 – | TOILET 3 ELEVATIONS & SHOWER 3 ELEVATIONS | ID | interior | Interior works | 2025-09-30
1621 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305522 | 0 | FAENA SUITE TYPE 2 – | HEADBOARD DETAILS | ID | interior | Interior works | 2025-09-30
1622 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305523 | 0 | FAENA SUITE TYPE 2 – | HEADBOARD DETAILS DOUBLE QUEEN | ID | interior | Interior works | 2025-09-30
1623 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305524 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - KITCHEN DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30
1624 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305525 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - KITCHEN DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30
1625 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305526 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - VANITY DETAILS | ID | interior | Interior works | 2025-09-30
1626 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305527 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - WARDROBE DETAILS (1 of 4) | ID | interior | Interior works | 2025-09-30
1627 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305528 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - WARDROBE DETAILS (2 of 4) | ID | interior | Interior works | 2025-09-30
1628 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305529 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - WARDROBE DETAILS (3 of 4) | ID | interior | Interior works | 2025-09-30
1629 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305530 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - WARDROBE DETAILS (4 of 4) | ID | interior | Interior works | 2025-09-30
1630 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305531 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - WET BAR DETAILS (1 of 2) | ID | interior | Interior works | 2025-09-30
1631 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305532 | 0 | FAENA SUITE TYPE 2 – | FAENA SUITE TYPE 1 - WET BAR DETAILS (2 of 2) | ID | interior | Interior works | 2025-09-30
1632 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305533 | 0 | FAENA SUITE TYPE 2 – | FLOORS DETAILS 1 | ID | interior | Interior works | 2025-09-30
1633 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305534 | 0 | FAENA SUITE TYPE 2 – | FLOORS DETAILS 2 | ID | interior | Interior works | 2025-09-30
1634 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305535 | 0 | FAENA SUITE TYPE 2 – | FLOORS DETAILS 3 | ID | interior | Interior works | 2025-09-30
1635 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305536 | 0 | FAENA SUITE TYPE 2 – | CEILING DETAILS 1 | ID | interior | Interior works | 2025-09-30
1636 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305537 | 0 | FAENA SUITE TYPE 2 – | CEILING DETAILS 2 | ID | interior | Interior works | 2025-09-30
1637 | WS-WSH-687-3230-UBJ-SDW-ID-500-1305538 | 0 | FAENA SUITE TYPE 2 – | CEILING DETAILS 3 | ID | interior | Interior works | 2025-09-30

## Internal (hidden)
Activity ID | Activity Name | Original Duration | Start | Finish | Total Float | Nonlabor Units % Complete
F.M.ENG.TC.1 | Prepare and Submit Calculation Sheet for Tower Cranes | 0.5 | 2024-08-01 | 2024-08-15 | 19.58 | 0%
F.M.ENG.TC.2 | Review and Approve Calculation Sheet for Tower Cranes | 0.7 | 2024-08-18 | 2024-09-04 | 21.2 | 0%
F.E.Z4.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2024-11-25 | 2024-12-10 | 0 | 0%
F.E.Z5.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2024-11-30 | 2024-12-15 | 0.12 | 0%
F.E.Z3.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2024-12-03 | 2024-12-18 | 0.38 | 0%
F.E.Z4.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2024-12-11 | 2024-12-31 | 0 | 0%
F.E.Z6.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2024-12-14 | 2024-12-29 | 1.38 | 0%
F.E.Z4.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.46 | 2024-12-15 | 2024-12-28 | 0 | 0%
F.E.Z4.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.46 | 2024-12-15 | 2024-12-28 | 0 | 0%
F.E.Z5.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2024-12-16 | 2024-12-31 | 0.12 | 0%
F.E.Z5.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2024-12-16 | 2024-12-31 | 0.12 | 0%
F.E.Z5.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2024-12-16 | 2025-01-05 | 0.15 | 0%
F.E.Z3.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2024-12-19 | 2025-01-08 | 0.4 | 0%
F.E.Z7.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2024-12-19 | 2025-01-04 | 2.62 | 0%
F.E.Z1.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2024-12-23 | 2025-01-07 | 2.42 | 0%
F.E.Z3.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2024-12-28 | 2025-01-12 | 0.42 | 0%
F.E.Z3.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2024-12-28 | 2025-01-12 | 0.42 | 0%
F.E.Z4.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2024-12-29 | 2025-01-16 | 0 | 0%
F.E.Z4.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2024-12-29 | 2025-01-16 | 0 | 0%
F.E.Z6.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2024-12-30 | 2025-01-19 | 1.5 | 0%
F.E.Z5.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-01-01 | 2025-01-21 | 0.1 | 0%
F.E.Z5.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-01-01 | 2025-01-21 | 0.1 | 0%
F.E.Z8.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-01-02 | 2025-01-18 | 3.04 | 0%
F.E.Z7.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-01-05 | 2025-01-23 | 2.9 | 0%
F.E.Z1.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-01-08 | 2025-01-28 | 2.65 | 0%
F.E.Z2.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-01-09 | 2025-01-25 | 3.73 | 0%
F.E.Z9.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-01-12 | 2025-01-27 | 4.62 | 0%
F.E.Z3.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-01-13 | 2025-02-02 | 0.45 | 0%
F.E.Z3.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-01-13 | 2025-02-02 | 0.45 | 0%
F.E.Z5.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.38 | 2025-01-16 | 2025-01-27 | 0.15 | 0%
F.E.Z8.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-01-19 | 2025-02-06 | 3.3 | 0%
F.E.Z4.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-01-20 | 2025-01-27 | 0 | 0%
F.E.Z3.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-01-23 | 2025-02-08 | 0.31 | 0%
F.E.Z4.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-01-23 | 2025-02-08 | 0 | 0%
F.E.Z4.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-01-23 | 2025-02-08 | 0 | 0%
F.E.Z4.ST.LG.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-01-23 | 2025-02-08 | 0 | 0%
F.E.Z4.ST.LG.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-01-23 | 2025-02-08 | 0 | 0%
F.E.Z2.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-01-26 | 2025-02-13 | 4.05 | 0%
F.E.Z5.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-01-26 | 2025-02-10 | 0.12 | 0%
F.E.Z5.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-01-26 | 2025-02-10 | 0.12 | 0%
F.E.Z5.ST.LG.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-01-26 | 2025-02-10 | 0.12 | 0%
F.E.Z5.ST.LG.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-01-26 | 2025-02-10 | 0.12 | 0%
F.E.Z4.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-01-28 | 2025-02-17 | 0 | 0%
F.E.Z5.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-01-28 | 2025-02-17 | 0.15 | 0%
F.E.Z9.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-01-28 | 2025-02-17 | 5.05 | 0%
F.E.Z7.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-02-03 | 2025-02-19 | 1.77 | 0%
F.E.Z7.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-02-03 | 2025-02-19 | 1.77 | 0%
F.E.Z3.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-02-09 | 2025-02-27 | 0.4 | 0%
F.E.Z4.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-02-09 | 2025-02-27 | 0 | 0%
F.E.Z4.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-02-09 | 2025-02-27 | 0 | 0%
F.E.Z4.ST.LG.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-02-09 | 2025-02-27 | 0 | 0%
F.E.Z4.ST.LG.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-02-09 | 2025-02-27 | 0 | 0%
F.E.Z5.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-02-11 | 2025-03-03 | 0.15 | 0%
F.E.Z5.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-02-11 | 2025-03-03 | 0.15 | 0%
F.E.Z5.ST.LG.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-02-11 | 2025-03-03 | 0.15 | 0%
F.E.Z5.ST.LG.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-02-11 | 2025-03-03 | 0.15 | 0%
F.E.Z4.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-02-17 | 2025-03-04 | 1.46 | 0%
F.E.Z4.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-02-17 | 2025-03-04 | 1.46 | 0%
F.E.Z6.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-02-17 | 2025-03-04 | 0 | 0%
F.E.Z6.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-02-17 | 2025-03-04 | 0 | 0%
F.E.Z7.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-02-20 | 2025-03-12 | 1.85 | 0%
F.E.Z7.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-02-20 | 2025-03-12 | 1.85 | 0%
F.E.Z3.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-02-22 | 2025-03-09 | 0.35 | 0%
F.E.Z3.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-02-22 | 2025-03-09 | 0.35 | 0%
F.E.Z3.ST.BF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-02-22 | 2025-03-09 | 0.35 | 0%
F.E.Z3.ST.BF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-02-22 | 2025-03-09 | 0.35 | 0%
F.E.Z5.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-02-22 | 2025-03-09 | 0.08 | 0%
F.E.Z5.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-02-22 | 2025-03-09 | 0.08 | 0%
F.E.Z4.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-03-05 | 2025-03-25 | 1.55 | 0%
F.E.Z4.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-03-05 | 2025-03-25 | 1.55 | 0%
F.E.Z6.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-03-05 | 2025-03-25 | 0 | 0%
F.E.Z6.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-03-05 | 2025-03-25 | 0 | 0%
F.E.Z7.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-03-08 | 2025-03-23 | 1.81 | 0%
F.E.Z3.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-03-10 | 2025-04-03 | 0.4 | 0%
F.E.Z3.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-03-10 | 2025-04-03 | 0.4 | 0%
F.E.Z3.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-03-10 | 2025-04-03 | 0.4 | 0%
F.E.Z3.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-03-10 | 2025-04-03 | 0.4 | 0%
F.E.Z5.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-03-10 | 2025-04-03 | 0.1 | 0%
F.E.Z5.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-03-10 | 2025-04-03 | 0.1 | 0%
F.E.Z4.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-03-13 | 2025-03-29 | 1.58 | 0%
F.E.Z4.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-03-13 | 2025-03-29 | 1.58 | 0%
F.E.Z4.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-03-13 | 2025-03-29 | 1.5 | 0%
F.E.Z4.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-03-13 | 2025-03-29 | 1.5 | 0%
F.E.Z4.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-03-13 | 2025-03-29 | 1.5 | 0%
F.E.Z1.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-03-17 | 2025-04-06 | 0.42 | 0%
F.E.Z1.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-03-17 | 2025-04-06 | 0.42 | 0%
F.E.Z6.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-03-17 | 2025-04-06 | 0 | 0%
F.E.Z5.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-03-20 | 2025-04-09 | 0.12 | 0%
F.E.Z5.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-03-20 | 2025-04-09 | 0.12 | 0%
F.E.Z5.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-03-20 | 2025-04-09 | 0.19 | 0%
F.E.Z5.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-03-20 | 2025-04-09 | 0.19 | 0%
F.E.Z5.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-03-20 | 2025-04-09 | 0.19 | 0%
F.E.Z3.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-03-23 | 2025-04-12 | 0.77 | 0%
F.E.Z3.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-03-23 | 2025-04-12 | 0.77 | 0%
F.E.Z7.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-03-24 | 2025-04-17 | 1.95 | 0%
F.E.Z2.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-04-03 | 2025-04-19 | 1.73 | 0%
F.E.Z2.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-04-03 | 2025-04-19 | 1.73 | 0%
F.E.Z4.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-04-03 | 2025-04-23 | 1.7 | 0%
F.E.Z4.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-04-03 | 2025-04-23 | 1.7 | 0%
F.E.Z4.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-04-03 | 2025-04-23 | 1.6 | 0%
F.E.Z4.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-04-03 | 2025-04-23 | 1.6 | 0%
F.E.Z4.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-04-03 | 2025-04-23 | 1.6 | 0%
F.E.Z1.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-04-07 | 2025-04-27 | 0.45 | 0%
F.E.Z1.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-04-07 | 2025-04-27 | 0.45 | 0%
F.E.Z6.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-04-07 | 2025-04-27 | 0 | 0%
F.E.Z4.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-04-08 | 2025-04-23 | 3.23 | 0%
F.E.Z4.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-04-08 | 2025-04-23 | 3.19 | 0%
F.E.Z5.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-04-08 | 2025-04-23 | 2.96 | 0%
F.E.Z5.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-04-08 | 2025-04-23 | 2.88 | 0%
F.E.Z5.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-04-10 | 2025-04-30 | 0.1 | 0%
F.E.Z5.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-04-10 | 2025-04-30 | 0.1 | 0%
F.E.Z5.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-04-10 | 2025-04-30 | 0.2 | 0%
F.E.Z5.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-04-10 | 2025-04-30 | 0.2 | 0%
F.E.Z5.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-04-10 | 2025-04-30 | 0.2 | 0%
F.E.Z4.ST.2F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-04-12 | 2025-04-27 | 1.69 | 0%
F.E.Z4.ST.2F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-04-12 | 2025-04-27 | 1.69 | 0%
F.E.Z3.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-04-13 | 2025-05-01 | 0.85 | 0%
F.E.Z3.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-04-13 | 2025-05-01 | 0.85 | 0%
F.E.Z6.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-04-14 | 2025-04-29 | 0 | 0%
F.E.Z6.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-04-14 | 2025-04-29 | 0 | 0%
F.E.Z6.ST.BF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-04-14 | 2025-04-29 | 0 | 0%
F.E.Z6.ST.BF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-04-14 | 2025-04-29 | 0 | 0%
F.E.Z4.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-04-15 | 2025-04-30 | 1.46 | 0%
F.E.Z4.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-04-15 | 2025-04-30 | 1.46 | 0%
F.E.Z4.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-04-15 | 2025-04-30 | 1.46 | 0%
F.E.Z5.ST.2F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-04-19 | 2025-05-04 | 0.12 | 0%
F.E.Z5.ST.2F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-04-19 | 2025-05-04 | 0.12 | 0%
F.E.Z1.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-04-20 | 2025-05-05 | 0.42 | 0%
F.E.Z2.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-04-20 | 2025-05-08 | 1.9 | 0%
F.E.Z2.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-04-20 | 2025-05-08 | 1.9 | 0%
F.E.Z4.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-04-20 | 2025-05-05 | 2.85 | 0%
F.E.Z5.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-04-20 | 2025-05-05 | 2.58 | 0%
F.E.Z8.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-04-20 | 2025-05-05 | 0.27 | 0%
F.E.Z8.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-04-20 | 2025-05-05 | 0.27 | 0%
F.E.Z5.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-04-22 | 2025-05-07 | 0.19 | 0%
F.E.Z5.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-04-22 | 2025-05-07 | 0.19 | 0%
F.E.Z5.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-04-22 | 2025-05-07 | 0.19 | 0%
F.E.Z4.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-04-24 | 2025-05-14 | 3.5 | 0%
F.E.Z4.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-04-24 | 2025-05-14 | 3.45 | 0%
F.E.Z5.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-04-24 | 2025-05-14 | 3.2 | 0%
F.E.Z5.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-04-24 | 2025-05-14 | 3.15 | 0%
F.E.Z3.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-04-26 | 2025-05-11 | 0.77 | 0%
F.E.Z3.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-04-26 | 2025-05-11 | 0.77 | 0%
F.E.Z3.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-04-26 | 2025-05-11 | 1.69 | 0%
F.E.Z3.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-04-26 | 2025-05-11 | 1.69 | 0%
F.E.Z3.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-04-26 | 2025-05-11 | 1.69 | 0%
F.E.Z4.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-04-28 | 2025-05-13 | 2.35 | 0%
F.E.Z4.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-04-28 | 2025-05-13 | 2.38 | 0%
F.E.Z4.HV.1F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-04-28 | 2025-05-13 | 2.23 | 0%
F.E.Z4.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-04-28 | 2025-05-18 | 1.85 | 0%
F.E.Z4.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-04-28 | 2025-05-18 | 1.85 | 0%
F.E.Z5.AR.LG.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-04-29 | 2025-05-14 | 2.35 | 0%
F.E.Z5.AR.LG.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-04-29 | 2025-05-14 | 2.35 | 0%
F.E.Z5.AR.LG.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-04-29 | 2025-05-14 | 2.35 | 0%
F.E.Z6.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-04-30 | 2025-05-20 | 0 | 0%
F.E.Z6.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-04-30 | 2025-05-20 | 0 | 0%
F.E.Z6.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-04-30 | 2025-05-20 | 0 | 0%
F.E.Z6.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-04-30 | 2025-05-20 | 0 | 0%
F.E.Z4.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-05-01 | 2025-05-21 | 1.6 | 0%
F.E.Z4.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-05-01 | 2025-05-21 | 1.6 | 0%
F.E.Z4.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-05-01 | 2025-05-21 | 1.6 | 0%
F.E.Z2.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-05-04 | 2025-05-19 | 1.73 | 0%
F.E.Z5.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-05-05 | 2025-05-25 | 0.15 | 0%
F.E.Z5.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-05-05 | 2025-05-25 | 0.15 | 0%
F.E.Z1.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-05-06 | 2025-05-26 | 0.45 | 0%
F.E.Z4.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-05-06 | 2025-05-21 | 1.69 | 0%
F.E.Z4.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-05-06 | 2025-05-21 | 1.69 | 0%
F.E.Z4.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-05-06 | 2025-05-26 | 3.1 | 0%
F.E.Z5.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-05-06 | 2025-05-21 | 2.31 | 0%
F.E.Z5.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-05-06 | 2025-05-21 | 2.35 | 0%
F.E.Z5.HV.1F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-05-06 | 2025-05-21 | 2.19 | 0%
F.E.Z5.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-05-06 | 2025-05-26 | 2.8 | 0%
F.E.Z8.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-05-06 | 2025-05-26 | 0.3 | 0%
F.E.Z8.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-05-06 | 2025-05-26 | 0.3 | 0%
F.E.Z5.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-05-08 | 2025-05-28 | 0.2 | 0%
F.E.Z5.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-05-08 | 2025-05-28 | 0.2 | 0%
F.E.Z5.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-05-08 | 2025-05-28 | 0.2 | 0%
F.E.Z3.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-05-12 | 2025-05-27 | 2.58 | 0%
F.E.Z3.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-05-12 | 2025-05-27 | 2.58 | 0%
F.E.Z3.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-05-12 | 2025-05-27 | 2.65 | 0%
F.E.Z3.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-05-12 | 2025-05-27 | 2.46 | 0%
F.E.Z3.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-05-12 | 2025-06-01 | 0.85 | 0%
F.E.Z3.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-05-12 | 2025-06-01 | 0.85 | 0%
F.E.Z3.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-05-12 | 2025-06-01 | 1.85 | 0%
F.E.Z3.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-05-12 | 2025-06-01 | 1.85 | 0%
F.E.Z3.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-05-12 | 2025-06-01 | 1.85 | 0%
F.E.Z4.AR.2F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-05-12 | 2025-05-27 | 1.46 | 0%
F.E.Z4.AR.2F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-05-12 | 2025-05-27 | 1.46 | 0%
F.E.Z4.AR.2F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-05-12 | 2025-05-27 | 1.46 | 0%
F.E.Z4.F2.1F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-05-12 | 2025-05-27 | 4.42 | 0%
F.E.Z1.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-05-13 | 2025-05-28 | 0.42 | 0%
F.E.Z1.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-05-13 | 2025-05-28 | 0.42 | 0%
F.E.Z1.ST.BF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-05-13 | 2025-05-28 | 0.42 | 0%
F.E.Z1.ST.BF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-05-13 | 2025-05-28 | 0.42 | 0%
F.E.Z5.ST.3F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-05-13 | 2025-05-28 | 0.15 | 0%
F.E.Z5.ST.3F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-05-13 | 2025-05-28 | 0.15 | 0%
F.E.Z5.PL.LG.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-05-13 | 2025-05-28 | 2.5 | 0%
F.E.Z5.DR.LG.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-05-13 | 2025-05-28 | 2.5 | 0%
F.E.Z5.HV.LG.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-05-13 | 2025-05-28 | 2.35 | 0%
F.E.Z4.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-05-14 | 2025-06-03 | 2.55 | 0%
F.E.Z4.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-05-14 | 2025-06-03 | 2.6 | 0%
F.E.Z4.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-05-14 | 2025-06-03 | 2.45 | 0%
F.E.Z2.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-05-15 | 2025-05-31 | 1.73 | 0%
F.E.Z2.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-05-15 | 2025-05-31 | 1.73 | 0%
F.E.Z2.ST.BF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-05-15 | 2025-05-31 | 1.73 | 0%
F.E.Z2.ST.BF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-05-15 | 2025-05-31 | 1.73 | 0%
F.E.Z5.AR.LG.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-05-15 | 2025-06-04 | 2.55 | 0%
F.E.Z5.AR.LG.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-05-15 | 2025-06-04 | 2.55 | 0%
F.E.Z5.AR.LG.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-05-15 | 2025-06-04 | 2.55 | 0%
F.E.Z4.AR.LG.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-05-18 | 2025-06-02 | 1.96 | 0%
F.E.Z4.AR.LG.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-05-18 | 2025-06-02 | 1.96 | 0%
F.E.Z4.AR.LG.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-05-18 | 2025-06-02 | 1.96 | 0%
F.E.Z8.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-05-19 | 2025-06-03 | 0.27 | 0%
F.E.Z9.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-05-19 | 2025-06-03 | 1.85 | 0%
F.E.Z9.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-05-19 | 2025-06-03 | 1.85 | 0%
F.E.Z2.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-05-20 | 2025-06-11 | 1.9 | 0%
F.E.Z5.F2.1F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-05-20 | 2025-06-04 | 4.08 | 0%
F.E.Z5.AR.2F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-05-20 | 2025-06-04 | 0.19 | 0%
F.E.Z5.AR.2F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-05-20 | 2025-06-04 | 0.19 | 0%
F.E.Z5.AR.2F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-05-20 | 2025-06-04 | 0.19 | 0%
F.E.Z6.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-05-20 | 2025-06-04 | 0 | 0%
F.E.Z6.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-05-20 | 2025-06-04 | 0 | 0%
F.E.Z4.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-05-22 | 2025-06-15 | 1.85 | 0%
F.E.Z4.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-05-22 | 2025-06-15 | 1.85 | 0%
F.E.Z5.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-05-22 | 2025-06-15 | 2.5 | 0%
F.E.Z5.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-05-22 | 2025-06-15 | 2.55 | 0%
F.E.Z5.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-05-22 | 2025-06-15 | 2.4 | 0%
F.E.Z3.ST.2F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-05-26 | 2025-06-14 | 0.73 | 0%
F.E.Z3.ST.2F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-05-26 | 2025-06-14 | 0.73 | 0%
F.E.Z3.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-05-26 | 2025-06-14 | 1.46 | 0%
F.E.Z3.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-05-26 | 2025-06-14 | 1.46 | 0%
F.E.Z3.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-05-26 | 2025-06-14 | 1.46 | 0%
F.E.Z4.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-05-26 | 2025-06-14 | 3.54 | 0%
F.E.Z4.PL.2F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-05-26 | 2025-06-14 | 1.73 | 0%
F.E.Z4.DR.2F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-05-26 | 2025-06-14 | 1.73 | 0%
F.E.Z4.HV.2F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-05-26 | 2025-06-14 | 1.73 | 0%
F.E.Z4.F2.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-05-26 | 2025-06-14 | 2.19 | 0%
R.E.4B.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-05-28 | 2025-06-16 | 1.54 | 0%
F.E.Z3.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-05-28 | 2025-06-19 | 2.8 | 0%
F.E.Z3.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-05-28 | 2025-06-19 | 2.8 | 0%
F.E.Z3.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-05-28 | 2025-06-19 | 2.9 | 0%
F.E.Z3.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-05-28 | 2025-06-19 | 2.7 | 0%
F.E.Z4.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-05-28 | 2025-06-19 | 1.6 | 0%
F.E.Z4.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-05-28 | 2025-06-19 | 1.6 | 0%
F.E.Z4.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-05-28 | 2025-06-19 | 1.6 | 0%
F.E.Z4.F2.1F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-05-28 | 2025-06-19 | 4.8 | 0%
R.E.6B.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-05-28 | 2025-06-16 | 2.23 | 0%
R.E.SS.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-05-28 | 2025-06-16 | 7.5 | 0%
R.E.GE.EX.CU.IR.002 | Prepare and Submit Shop Drawings For Leveling Works | 0.13 | 2025-05-28 | 2025-05-31 | 0.83 | 0%
F.E.Z1.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-05-29 | 2025-06-22 | 0.45 | 0%
F.E.Z1.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-05-29 | 2025-06-22 | 0.45 | 0%
F.E.Z1.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-05-29 | 2025-06-22 | 0.45 | 0%
F.E.Z1.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-05-29 | 2025-06-22 | 0.45 | 0%
F.E.Z5.ST.3F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-05-29 | 2025-06-22 | 0.15 | 0%
F.E.Z5.ST.3F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-05-29 | 2025-06-22 | 0.15 | 0%
F.E.Z5.PL.LG.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-05-29 | 2025-06-22 | 2.7 | 0%
F.E.Z5.DR.LG.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-05-29 | 2025-06-22 | 2.7 | 0%
F.E.Z5.HV.LG.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-05-29 | 2025-06-22 | 2.55 | 0%
F.E.Z4.PL.LG.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-05-31 | 2025-06-18 | 2.15 | 0%
F.E.Z4.DR.LG.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-05-31 | 2025-06-18 | 2.15 | 0%
F.E.Z4.HV.LG.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-05-31 | 2025-06-18 | 2 | 0%
R.E.5B.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.19 | 2025-05-31 | 2025-06-04 | 2.42 | 0%
F.E.Z2.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-06-01 | 2025-06-23 | 1.9 | 0%
F.E.Z2.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-06-01 | 2025-06-23 | 1.9 | 0%
F.E.Z2.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-06-01 | 2025-06-23 | 1.9 | 0%
F.E.Z2.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-06-01 | 2025-06-23 | 1.9 | 0%
R.E.GE.EX.GE.CU.004 | Review and Approve Shop Drawings For Leveling Works | 0.13 | 2025-06-01 | 2025-06-04 | 0.83 | 0%
F.E.Z5.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-06-02 | 2025-06-21 | 3.23 | 0%
F.E.Z4.F2.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-06-02 | 2025-06-21 | 3.31 | 0%
F.E.Z4.AR.LG.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-06-03 | 2025-06-25 | 2.15 | 0%
F.E.Z4.AR.LG.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-06-03 | 2025-06-25 | 2.15 | 0%
F.E.Z4.AR.LG.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-06-03 | 2025-06-25 | 2.15 | 0%
F.E.Z5.PL.2F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-06-03 | 2025-06-22 | 1.46 | 0%
F.E.Z5.DR.2F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-06-03 | 2025-06-22 | 1.46 | 0%
F.E.Z5.HV.2F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-06-03 | 2025-06-22 | 1.46 | 0%
F.E.Z8.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-06-04 | 2025-06-26 | 0.3 | 0%
F.E.Z9.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-06-04 | 2025-06-26 | 2 | 0%
F.E.Z9.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-06-04 | 2025-06-26 | 2 | 0%
F.E.Z5.F2.1F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-06-09 | 2025-06-29 | 4.4 | 0%
F.E.Z5.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-06-09 | 2025-06-29 | 0.2 | 0%
F.E.Z5.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-06-09 | 2025-06-29 | 0.2 | 0%
F.E.Z5.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-06-09 | 2025-06-29 | 0.2 | 0%
F.E.Z6.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-06-09 | 2025-06-29 | 0 | 0%
F.E.Z6.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-06-09 | 2025-06-29 | 0 | 0%
R.E.5B.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-06-09 | 2025-06-29 | 2.65 | 0%
F.E.Z4.EL.LG.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 1.77 | 0%
F.E.Z4.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 1.23 | 0%
F.E.Z4.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 1.23 | 0%
F.E.Z4.EL.2F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 3.15 | 0%
F.E.Z4.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-06-10 | 2025-06-25 | 1.46 | 0%
F.E.Z4.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-06-10 | 2025-06-25 | 1.46 | 0%
F.E.Z4.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-06-10 | 2025-06-25 | 1.46 | 0%
F.E.Z5.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-10 | 2025-06-25 | 0.65 | 0%
F.E.Z5.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-10 | 2025-06-25 | 0.65 | 0%
F.E.Z5.EL.LG.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 1.54 | 0%
F.E.Z5.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 0.92 | 0%
F.E.Z5.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 0.92 | 0%
F.E.Z5.EL.2F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-10 | 2025-06-25 | 3.15 | 0%
F.E.Z7.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-06-10 | 2025-06-25 | 0.12 | 0%
F.E.Z7.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-06-10 | 2025-06-25 | 0.12 | 0%
F.E.Z7.ST.BF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-10 | 2025-06-25 | 0.12 | 0%
F.E.Z7.ST.BF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-10 | 2025-06-25 | 0.12 | 0%
F.E.Z2.ST.LG.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-12 | 2025-06-28 | 2 | 0%
F.E.Z2.ST.LG.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-12 | 2025-06-28 | 2 | 0%
F.E.Z4.F2.2F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-06-12 | 2025-06-28 | 3.54 | 0%
F.E.Z3.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-06-14 | 2025-06-29 | 1.62 | 0%
F.E.Z3.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-06-14 | 2025-06-29 | 1.62 | 0%
F.E.Z3.HV.1F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-06-14 | 2025-06-29 | 1.69 | 0%
F.E.Z3.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-14 | 2025-06-29 | 1.5 | 0%
F.E.Z5.F2.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-06-14 | 2025-06-29 | 2.96 | 0%
F.E.Z3.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-06-15 | 2025-07-03 | 0.8 | 0%
F.E.Z3.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-06-15 | 2025-07-03 | 0.8 | 0%
F.E.Z3.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-06-15 | 2025-07-03 | 1.6 | 0%
F.E.Z3.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-06-15 | 2025-07-03 | 1.6 | 0%
F.E.Z3.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-06-15 | 2025-07-03 | 1.6 | 0%
F.E.Z4.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-06-15 | 2025-07-03 | 3.85 | 0%
F.E.Z4.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-06-15 | 2025-07-03 | 1.9 | 0%
F.E.Z4.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-06-15 | 2025-07-03 | 1.9 | 0%
F.E.Z4.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-06-15 | 2025-07-03 | 1.9 | 0%
F.E.Z4.F2.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-06-15 | 2025-07-03 | 2.4 | 0%
R.E.4B.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-06-17 | 2025-07-07 | 1.65 | 0%
F.E.Z6.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-17 | 2025-07-02 | 0.12 | 0%
F.E.Z6.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-17 | 2025-07-02 | 0.12 | 0%
F.E.Z6.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-06-17 | 2025-07-02 | 0 | 0%
F.E.Z6.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-06-17 | 2025-07-02 | 0 | 0%
F.E.Z6.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-06-17 | 2025-07-02 | 0 | 0%
R.E.6B.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-06-17 | 2025-07-07 | 2.4 | 0%
R.E.SS.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-06-17 | 2025-07-07 | 8.1 | 0%
R.E.4B.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-06-19 | 2025-07-05 | 1.62 | 0%
R.E.4B.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-06-19 | 2025-07-05 | 1.62 | 0%
F.E.Z4.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-06-19 | 2025-07-05 | 2.81 | 0%
F.E.Z4.PL.LG.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-06-19 | 2025-07-09 | 2.3 | 0%
F.E.Z4.DR.LG.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-06-19 | 2025-07-09 | 2.3 | 0%
F.E.Z4.HV.LG.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-06-19 | 2025-07-09 | 2.15 | 0%
F.E.Z5.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-06-19 | 2025-07-05 | 2.73 | 0%
R.E.SS.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-06-19 | 2025-07-05 | 7.35 | 0%
R.E.SS.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-06-19 | 2025-07-05 | 7.35 | 0%
F.E.Z5.AR.3F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-06-21 | 2025-07-06 | 0.19 | 0%
F.E.Z5.AR.3F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-06-21 | 2025-07-06 | 0.19 | 0%
F.E.Z5.AR.3F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-06-21 | 2025-07-06 | 0.19 | 0%
F.E.Z5.F2.2F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-06-21 | 2025-07-06 | 3.27 | 0%
F.E.Z4.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-06-22 | 2025-07-07 | 5.69 | 0%
F.E.Z4.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-06-22 | 2025-07-07 | 7.38 | 0%
F.E.Z5.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-06-22 | 2025-07-10 | 3.5 | 0%
F.E.Z8.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-06-22 | 2025-07-07 | 0.27 | 0%
F.E.Z8.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-06-22 | 2025-07-07 | 0.27 | 0%
F.E.Z8.ST.BF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-22 | 2025-07-07 | 0.27 | 0%
F.E.Z8.ST.BF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-22 | 2025-07-07 | 0.27 | 0%
F.E.Z4.F2.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-06-22 | 2025-07-10 | 3.6 | 0%
F.E.Z4.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-06-23 | 2025-07-08 | 1.5 | 0%
F.E.Z4.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-06-23 | 2025-07-08 | 1.5 | 0%
F.E.Z4.HV.RF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-06-23 | 2025-07-08 | 1.5 | 0%
F.E.Z4.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-06-23 | 2025-07-08 | 2.85 | 0%
F.E.Z5.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-06-23 | 2025-07-13 | 1.6 | 0%
F.E.Z5.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-06-23 | 2025-07-13 | 1.6 | 0%
F.E.Z5.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-06-23 | 2025-07-13 | 1.6 | 0%
R.E.6B.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-06-23 | 2025-07-08 | 2.65 | 0%
R.E.6B.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-06-23 | 2025-07-08 | 2.65 | 0%
F.E.Z1.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-24 | 2025-07-09 | 0.65 | 0%
F.E.Z1.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-24 | 2025-07-09 | 0.65 | 0%
F.E.Z3.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-06-24 | 2025-07-09 | 2.19 | 0%
F.E.Z3.AR.1F.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-06-24 | 2025-07-09 | 2.19 | 0%
F.E.Z5.F2.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-06-24 | 2025-07-09 | 2.38 | 0%
F.E.Z4.F2.LG.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-06-24 | 2025-07-09 | 2.88 | 0%
F.E.Z4.F2.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-06-24 | 2025-07-09 | 2.46 | 0%
F.E.Z5.F2.LG.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-06-24 | 2025-07-09 | 2.88 | 0%
F.E.Z3.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-06-26 | 2025-07-12 | 1.42 | 0%
F.E.Z3.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-06-26 | 2025-07-12 | 1.42 | 0%
F.E.Z3.AR.2F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-06-26 | 2025-07-12 | 1.5 | 0%
F.E.Z3.AR.2F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-06-26 | 2025-07-12 | 1.5 | 0%
F.E.Z3.AR.2F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-06-26 | 2025-07-12 | 1.5 | 0%
F.E.Z4.HV.2F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-06-26 | 2025-07-12 | 2.62 | 0%
F.E.Z4.FF.2F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-06-26 | 2025-07-12 | 2.62 | 0%
F.E.Z4.EL.LG.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 1.9 | 0%
F.E.Z4.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 1.3 | 0%
F.E.Z4.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 1.3 | 0%
F.E.Z4.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 3.4 | 0%
F.E.Z4.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-06-26 | 2025-07-16 | 1.55 | 0%
F.E.Z4.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-06-26 | 2025-07-16 | 1.55 | 0%
F.E.Z4.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-06-26 | 2025-07-16 | 1.55 | 0%
F.E.Z5.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-06-26 | 2025-07-16 | 0.7 | 0%
F.E.Z5.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-06-26 | 2025-07-16 | 0.7 | 0%
F.E.Z5.EL.LG.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 1.65 | 0%
F.E.Z5.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 1 | 0%
F.E.Z5.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 1 | 0%
F.E.Z5.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-26 | 2025-07-16 | 3.4 | 0%
F.E.Z7.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-06-26 | 2025-07-16 | 0.1 | 0%
F.E.Z7.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-06-26 | 2025-07-16 | 0.1 | 0%
F.E.Z7.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-06-26 | 2025-07-16 | 0.1 | 0%
F.E.Z7.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-06-26 | 2025-07-16 | 0.1 | 0%
F.E.Z4.F2.2F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-06-26 | 2025-07-12 | 1.73 | 0%
R.E.5B.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.27 | 2025-06-28 | 2025-07-05 | 2.38 | 0%
R.E.5B.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-06-28 | 2025-07-05 | 2.38 | 0%
F.E.Z2.ST.LG.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-06-29 | 2025-07-17 | 2.2 | 0%
F.E.Z2.ST.LG.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-06-29 | 2025-07-17 | 2.2 | 0%
F.E.Z4.F2.2F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-06-29 | 2025-07-17 | 3.85 | 0%
F.E.Z3.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-06-30 | 2025-07-20 | 1.75 | 0%
F.E.Z3.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-06-30 | 2025-07-20 | 1.75 | 0%
F.E.Z3.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-06-30 | 2025-07-20 | 1.85 | 0%
F.E.Z3.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-06-30 | 2025-07-20 | 1.65 | 0%
F.E.Z5.F2.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-06-30 | 2025-07-20 | 3.2 | 0%
F.E.Z3.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-07-01 | 2025-07-16 | 1.58 | 0%
F.E.Z3.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-01 | 2025-07-16 | 1.58 | 0%
F.E.Z3.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-01 | 2025-07-16 | 1.73 | 0%
F.E.Z3.AR.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-07-01 | 2025-07-16 | 1.58 | 0%
F.E.Z3.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-01 | 2025-07-16 | 1.58 | 0%
F.E.Z3.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-01 | 2025-07-16 | 1.73 | 0%
F.E.Z6.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-01 | 2025-07-16 | 0.19 | 0%
F.E.Z6.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-01 | 2025-07-16 | 0.23 | 0%
F.E.Z6.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-01 | 2025-07-16 | 0.19 | 0%
F.E.Z6.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-03 | 2025-07-23 | 0.1 | 0%
F.E.Z6.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-07-03 | 2025-07-23 | 0.1 | 0%
F.E.Z6.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-07-03 | 2025-07-23 | 0 | 0%
F.E.Z6.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-07-03 | 2025-07-23 | 0 | 0%
F.E.Z6.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-07-03 | 2025-07-23 | 0 | 0%
F.E.Z9.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-07-03 | 2025-07-19 | 1.77 | 0%
F.E.Z4.F2.2F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-07-03 | 2025-07-19 | 2.58 | 0%
F.E.Z4.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-07-05 | 2025-07-20 | 5.69 | 0%
F.E.Z4.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-07-05 | 2025-07-20 | 5.69 | 0%
F.E.Z4.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-07-05 | 2025-07-20 | 7.35 | 0%
F.E.Z5.HV.2F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-05 | 2025-07-20 | 2.35 | 0%
F.E.Z5.FF.2F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-05 | 2025-07-20 | 2.35 | 0%
F.E.Z5.PL.3F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-05 | 2025-07-20 | 1.12 | 0%
F.E.Z5.DR.3F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-05 | 2025-07-20 | 1.12 | 0%
F.E.Z5.HV.3F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-05 | 2025-07-20 | 1.12 | 0%
F.E.Z5.EL.3F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-05 | 2025-07-20 | 2.35 | 0%
F.E.Z5.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-07-05 | 2025-07-20 | 4.54 | 0%
F.E.Z5.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-07-05 | 2025-07-20 | 6.96 | 0%
F.E.Z6.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-05 | 2025-07-20 | 0.08 | 0%
R.E.4B.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-07-06 | 2025-07-24 | 1.75 | 0%
R.E.4B.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-07-06 | 2025-07-24 | 1.75 | 0%
F.E.Z2.AR.LG.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-06 | 2025-07-21 | 2.04 | 0%
F.E.Z2.AR.LG.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-06 | 2025-07-21 | 2.04 | 0%
F.E.Z2.AR.LG.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-06 | 2025-07-21 | 2.04 | 0%
F.E.Z2.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-07-06 | 2025-07-21 | 5.23 | 0%
F.E.Z2.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-07-06 | 2025-07-21 | 6.92 | 0%
F.E.Z3.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-07-06 | 2025-07-21 | 1.58 | 0%
F.E.Z3.AR.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-07-06 | 2025-07-21 | 1.58 | 0%
F.E.Z4.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-07-06 | 2025-07-21 | 3.88 | 0%
F.E.Z4.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-06 | 2025-07-24 | 3.05 | 0%
F.E.Z5.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-06 | 2025-07-24 | 2.95 | 0%
R.E.5B.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-07-06 | 2025-07-24 | 2.6 | 0%
R.E.5B.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-07-06 | 2025-07-24 | 2.6 | 0%
R.E.SS.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-07-06 | 2025-07-24 | 8 | 0%
R.E.SS.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-07-06 | 2025-07-24 | 8 | 0%
F.E.Z4.HV.LG.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-07 | 2025-07-22 | 2 | 0%
F.E.Z4.FF.LG.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-07 | 2025-07-22 | 2.04 | 0%
F.E.Z4.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-07 | 2025-07-22 | 1.42 | 0%
F.E.Z4.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-07 | 2025-07-22 | 1.5 | 0%
F.E.Z4.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-07-07 | 2025-07-22 | 5.69 | 0%
F.E.Z5.HV.LG.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-07 | 2025-07-22 | 2 | 0%
F.E.Z5.FF.LG.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-07 | 2025-07-22 | 2.04 | 0%
F.E.Z5.F2.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-07-07 | 2025-07-22 | 0.92 | 0%
F.E.Z5.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-07 | 2025-07-22 | 1.5 | 0%
F.E.Z5.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-07 | 2025-07-22 | 1.54 | 0%
F.E.Z5.AR.3F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-07-07 | 2025-07-27 | 0.2 | 0%
F.E.Z5.AR.3F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-07-07 | 2025-07-27 | 0.2 | 0%
F.E.Z5.AR.3F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-07-07 | 2025-07-27 | 0.2 | 0%
F.E.Z4.F2.LG.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-07-07 | 2025-07-22 | 2 | 0%
F.E.Z4.F2.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-07-07 | 2025-07-22 | 1.5 | 0%
F.E.Z5.F2.LG.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-07-07 | 2025-07-22 | 1.54 | 0%
F.E.Z5.F2.2F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-07-07 | 2025-07-27 | 3.55 | 0%
F.E.Z4.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-07-08 | 2025-07-28 | 6.15 | 0%
F.E.Z4.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-07-08 | 2025-07-28 | 8.05 | 0%
F.E.Z8.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-07-08 | 2025-07-28 | 0.3 | 0%
F.E.Z8.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-07-08 | 2025-07-28 | 0.3 | 0%
F.E.Z8.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-08 | 2025-07-28 | 0.3 | 0%
F.E.Z8.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-07-08 | 2025-07-28 | 0.3 | 0%
F.E.Z4.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-07-09 | 2025-07-29 | 1.6 | 0%
F.E.Z4.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-07-09 | 2025-07-29 | 1.6 | 0%
F.E.Z4.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-07-09 | 2025-07-29 | 1.6 | 0%
F.E.Z4.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-07-09 | 2025-07-29 | 3.05 | 0%
R.E.6B.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-07-09 | 2025-07-29 | 2.85 | 0%
R.E.6B.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-07-09 | 2025-07-29 | 2.85 | 0%
F.E.Z1.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-10 | 2025-07-30 | 0.7 | 0%
F.E.Z1.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-07-10 | 2025-07-30 | 0.7 | 0%
F.E.Z2.AR.BF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-10 | 2025-07-26 | 1.77 | 0%
F.E.Z2.AR.BF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-10 | 2025-07-26 | 1.77 | 0%
F.E.Z2.AR.BF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-10 | 2025-07-26 | 1.77 | 0%
F.E.Z3.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-07-10 | 2025-07-30 | 2.35 | 0%
F.E.Z3.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-07-10 | 2025-07-30 | 2.35 | 0%
F.E.Z4.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-07-10 | 2025-07-26 | 6.35 | 0%
F.E.Z5.F2.GF.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-07-10 | 2025-07-30 | 2.55 | 0%
F.E.Z9.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-07-10 | 2025-07-26 | 1.85 | 0%
F.E.Z4.F2.LG.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-07-10 | 2025-07-30 | 3.1 | 0%
F.E.Z4.F2.GF.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-07-10 | 2025-07-30 | 2.65 | 0%
F.E.Z5.F2.LG.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-07-10 | 2025-07-30 | 3.1 | 0%
F.E.Z4.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-07-12 | 2025-07-27 | 6.38 | 0%
F.E.Z6.ST.2F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-07-12 | 2025-07-27 | 0.96 | 0%
F.E.Z6.ST.2F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-07-12 | 2025-07-27 | 0.96 | 0%
F.E.Z2.PL.LG.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-13 | 2025-07-28 | 2.5 | 0%
F.E.Z2.DR.LG.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-13 | 2025-07-28 | 2.5 | 0%
F.E.Z2.HV.LG.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-13 | 2025-07-28 | 2.54 | 0%
F.E.Z3.PL.2F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-13 | 2025-07-28 | 2.19 | 0%
F.E.Z3.DR.2F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-13 | 2025-07-28 | 2.19 | 0%
F.E.Z3.HV.2F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-13 | 2025-07-28 | 2.27 | 0%
F.E.Z3.EL.2F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-13 | 2025-07-28 | 2.73 | 0%
F.E.Z3.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-13 | 2025-07-31 | 1.55 | 0%
F.E.Z3.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-07-13 | 2025-07-31 | 1.55 | 0%
F.E.Z3.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-07-13 | 2025-07-31 | 1.65 | 0%
F.E.Z3.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-07-13 | 2025-07-31 | 1.65 | 0%
F.E.Z3.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-07-13 | 2025-07-31 | 1.65 | 0%
F.E.Z4.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-13 | 2025-07-31 | 2.85 | 0%
F.E.Z4.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-13 | 2025-07-31 | 2.85 | 0%
F.E.Z4.F2.2F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-07-13 | 2025-07-31 | 1.9 | 0%
F.E.Z5.F2.2F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-07-13 | 2025-07-28 | 2.27 | 0%
R.E.4B.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-07-14 | 2025-07-29 | 1.65 | 0%
F.E.Z2.EL.LG.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-14 | 2025-07-29 | 2.42 | 0%
F.E.Z5.F2.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-07-14 | 2025-07-29 | 1.31 | 0%
F.E.Z5.F2.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-07-14 | 2025-07-29 | 0.92 | 0%
F.E.Z7.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-07-14 | 2025-07-29 | 0.12 | 0%
F.E.Z7.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-07-14 | 2025-07-29 | 0.12 | 0%
F.E.Z4.F2.LG.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-07-14 | 2025-07-29 | 1.81 | 0%
F.E.Z4.F2.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-07-14 | 2025-07-29 | 1.27 | 0%
F.E.Z5.F2.LG.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-07-14 | 2025-07-29 | 1.81 | 0%
F.E.Z6.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-07-15 | 2025-07-30 | 1.92 | 0%
F.E.Z6.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-15 | 2025-07-30 | 0 | 0%
F.E.Z6.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-15 | 2025-07-30 | 0 | 0%
F.E.Z6.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-15 | 2025-07-30 | 0 | 0%
F.E.Z2.PL.BF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-17 | 2025-08-02 | 1.88 | 0%
F.E.Z2.DR.BF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-17 | 2025-08-02 | 1.88 | 0%
F.E.Z2.HV.BF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-17 | 2025-08-02 | 1.96 | 0%
F.E.Z2.EL.BF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-17 | 2025-08-02 | 1.81 | 0%
F.E.Z2.EX.GE.PO.002 | Prepare and Submit Shop Drawings For Pools and Water Features | 0.54 | 2025-07-17 | 2025-08-02 | 6.04 | 0%
F.E.Z3.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-07-17 | 2025-08-06 | 1.7 | 0%
F.E.Z3.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-17 | 2025-08-06 | 1.7 | 0%
F.E.Z3.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-17 | 2025-08-06 | 1.85 | 0%
F.E.Z3.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-07-17 | 2025-08-06 | 1.7 | 0%
F.E.Z3.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-17 | 2025-08-06 | 1.7 | 0%
F.E.Z3.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-17 | 2025-08-06 | 1.85 | 0%
F.E.Z5.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-07-17 | 2025-08-02 | 4.5 | 0%
F.E.Z5.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-07-17 | 2025-08-02 | 4.5 | 0%
F.E.Z5.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-07-17 | 2025-08-02 | 6.92 | 0%
F.E.Z6.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-07-17 | 2025-08-06 | 0.2 | 0%
F.E.Z6.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-07-17 | 2025-08-06 | 0.25 | 0%
F.E.Z6.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-07-17 | 2025-08-06 | 0.2 | 0%
R.E.VL.ST.FO.EX.002 | Prepare and Submit Shop Drawings For Excavation and Setting out | 0.54 | 2025-07-17 | 2025-08-02 | 0 | 0%
F.E.Z2.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-07-19 | 2025-08-03 | 5.23 | 0%
F.E.Z2.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-07-19 | 2025-08-03 | 5.23 | 0%
F.E.Z2.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-07-19 | 2025-08-03 | 6.88 | 0%
F.E.Z5.F2.3F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-07-19 | 2025-08-03 | 2.35 | 0%
F.E.Z5.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-19 | 2025-08-03 | 0.19 | 0%
F.E.Z5.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-19 | 2025-08-03 | 0.19 | 0%
F.E.Z5.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-19 | 2025-08-03 | 0.19 | 0%
F.E.Z2.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-07-20 | 2025-08-04 | 3.42 | 0%
F.E.Z2.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-20 | 2025-08-04 | 2.04 | 0%
F.E.Z2.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-20 | 2025-08-04 | 2.04 | 0%
F.E.Z2.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-20 | 2025-08-04 | 2.04 | 0%
F.E.Z5.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-07-20 | 2025-08-04 | 4.5 | 0%
F.E.Z4.F2.2F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-07-20 | 2025-08-07 | 2.8 | 0%
R.E.6B.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-07-20 | 2025-08-04 | 2.54 | 0%
F.E.Z9.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-07-20 | 2025-08-07 | 1.95 | 0%
F.E.Z2.F1.LG.RP.002 | Prepare and Submit Shop Drawings For RCP For Public Spaces | 0.54 | 2025-07-21 | 2025-08-05 | 3.35 | 0%
F.E.Z2.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-07-21 | 2025-08-05 | 5.23 | 0%
F.E.Z4.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2025-07-21 | 2025-08-05 | 5.19 | 0%
F.E.Z4.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-21 | 2025-08-05 | 1.77 | 0%
F.E.Z4.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-21 | 2025-08-05 | 1.81 | 0%
F.E.Z4.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-07-21 | 2025-08-10 | 6.15 | 0%
F.E.Z4.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-07-21 | 2025-08-10 | 6.15 | 0%
F.E.Z4.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-07-21 | 2025-08-10 | 7.95 | 0%
F.E.Z5.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-21 | 2025-08-10 | 2.55 | 0%
F.E.Z5.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-21 | 2025-08-10 | 2.55 | 0%
F.E.Z5.PL.3F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-07-21 | 2025-08-10 | 1.2 | 0%
F.E.Z5.DR.3F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-07-21 | 2025-08-10 | 1.2 | 0%
F.E.Z5.HV.3F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-07-21 | 2025-08-10 | 1.2 | 0%
F.E.Z5.EL.3F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-07-21 | 2025-08-10 | 2.55 | 0%
F.E.Z5.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-07-21 | 2025-08-10 | 4.9 | 0%
F.E.Z5.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-07-21 | 2025-08-10 | 7.6 | 0%
F.E.Z6.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-07-21 | 2025-08-10 | 0.1 | 0%
F.E.Z5.F2.2F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-07-21 | 2025-08-05 | 0.92 | 0%
R.E.5B.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-07-21 | 2025-07-28 | 2.46 | 0%
F.E.Z1.AR.BF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-22 | 2025-08-06 | 0.38 | 0%
F.E.Z1.AR.BF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-22 | 2025-08-06 | 0.38 | 0%
F.E.Z1.AR.BF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-22 | 2025-08-06 | 0.38 | 0%
F.E.Z1.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-22 | 2025-08-06 | 0.65 | 0%
F.E.Z1.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-22 | 2025-08-06 | 0.65 | 0%
F.E.Z1.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-22 | 2025-08-06 | 0.65 | 0%
F.E.Z1.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-07-22 | 2025-08-06 | 4.69 | 0%
F.E.Z1.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-07-22 | 2025-08-06 | 6.38 | 0%
F.E.Z2.AR.LG.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-07-22 | 2025-08-11 | 2.2 | 0%
F.E.Z2.AR.LG.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-07-22 | 2025-08-11 | 2.2 | 0%
F.E.Z2.AR.LG.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-07-22 | 2025-08-11 | 2.2 | 0%
F.E.Z2.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-07-22 | 2025-08-11 | 5.65 | 0%
F.E.Z2.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-07-22 | 2025-08-11 | 7.55 | 0%
F.E.Z3.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-07-22 | 2025-08-11 | 1.7 | 0%
F.E.Z3.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-07-22 | 2025-08-11 | 1.7 | 0%
F.E.Z4.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-07-22 | 2025-08-11 | 4.2 | 0%
F.E.Z5.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-07-22 | 2025-08-06 | 5.96 | 0%
F.E.Z4.HV.LG.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-23 | 2025-08-12 | 2.15 | 0%
F.E.Z4.FF.LG.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-23 | 2025-08-12 | 2.2 | 0%
F.E.Z4.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-23 | 2025-08-12 | 1.55 | 0%
F.E.Z4.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-23 | 2025-08-12 | 1.6 | 0%
F.E.Z4.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-07-23 | 2025-08-12 | 6.15 | 0%
F.E.Z5.HV.LG.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-23 | 2025-08-12 | 2.15 | 0%
F.E.Z5.FF.LG.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-23 | 2025-08-12 | 2.2 | 0%
F.E.Z5.F2.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-07-23 | 2025-08-12 | 1 | 0%
F.E.Z5.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-07-23 | 2025-08-12 | 1.6 | 0%
F.E.Z5.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-07-23 | 2025-08-12 | 1.65 | 0%
F.E.Z4.F2.LG.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-07-23 | 2025-08-12 | 2.15 | 0%
F.E.Z4.F2.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-07-23 | 2025-08-12 | 1.6 | 0%
F.E.Z5.F2.LG.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-07-23 | 2025-08-12 | 1.65 | 0%
F.E.Z2.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-07-24 | 2025-08-09 | 5.88 | 0%
F.E.Z3.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-24 | 2025-08-09 | 1.38 | 0%
F.E.Z3.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-24 | 2025-08-09 | 1.38 | 0%
F.E.Z3.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-24 | 2025-08-09 | 1.38 | 0%
F.E.Z3.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-07-24 | 2025-08-09 | 4.62 | 0%
F.E.Z3.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-07-24 | 2025-08-09 | 6.31 | 0%
F.E.Z5.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-07-24 | 2025-08-09 | 5.96 | 0%
F.E.Z4.F2.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-07-24 | 2025-08-09 | 3.12 | 0%
F.E.Z4.F2.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-07-24 | 2025-08-09 | 3.08 | 0%
R.E.5B.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-07-24 | 2025-08-09 | 2.54 | 0%
R.E.5B.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-07-24 | 2025-08-09 | 2.54 | 0%
R.E.4B.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-07-26 | 2025-08-10 | 1.77 | 0%
R.E.4B.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-07-26 | 2025-08-10 | 1.77 | 0%
R.E.4B.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-07-26 | 2025-08-10 | 1.77 | 0%
R.E.4B.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-07-26 | 2025-08-10 | 1.77 | 0%
F.E.Z2.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-07-26 | 2025-08-10 | 5.92 | 0%
F.E.Z8.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-07-26 | 2025-08-10 | 0.35 | 0%
F.E.Z8.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-07-26 | 2025-08-10 | 0.35 | 0%
F.E.Z2.F1.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For Public Spaces | 0.54 | 2025-07-27 | 2025-08-11 | 2.42 | 0%
F.E.Z2.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-07-27 | 2025-08-14 | 1.95 | 0%
F.E.Z2.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-07-27 | 2025-08-14 | 1.95 | 0%
F.E.Z2.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-07-27 | 2025-08-14 | 1.95 | 0%
F.E.Z4.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-07-27 | 2025-08-14 | 6.9 | 0%
F.E.Z9.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-27 | 2025-08-14 | 2 | 0%
F.E.Z2.F1.LG.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Public Spaces | 0.54 | 2025-07-28 | 2025-08-12 | 2.77 | 0%
F.E.Z2.HV.LG.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-28 | 2025-08-12 | 2.42 | 0%
F.E.Z2.FF.LG.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-28 | 2025-08-12 | 2.88 | 0%
F.E.Z4.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-07-28 | 2025-08-17 | 6.9 | 0%
F.E.Z6.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-07-28 | 2025-08-12 | 0.65 | 0%
F.E.Z6.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-28 | 2025-08-12 | 0.46 | 0%
F.E.Z6.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-28 | 2025-08-12 | 0.62 | 0%
F.E.Z6.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-28 | 2025-08-17 | 1.05 | 0%
F.E.Z6.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-07-28 | 2025-08-17 | 1.05 | 0%
F.E.Z2.PL.LG.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-07-29 | 2025-08-18 | 2.7 | 0%
F.E.Z2.DR.LG.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-07-29 | 2025-08-18 | 2.7 | 0%
F.E.Z2.HV.LG.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-07-29 | 2025-08-18 | 2.75 | 0%
F.E.Z3.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-07-29 | 2025-08-18 | 2.35 | 0%
F.E.Z3.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-07-29 | 2025-08-18 | 2.35 | 0%
F.E.Z3.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-07-29 | 2025-08-18 | 2.45 | 0%
F.E.Z3.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-07-29 | 2025-08-18 | 2.95 | 0%
F.E.Z6.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-29 | 2025-08-13 | 0.12 | 0%
F.E.Z6.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-29 | 2025-08-13 | 0.15 | 0%
F.E.Z6.HV.1F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-29 | 2025-08-13 | 0.12 | 0%
F.E.Z5.F2.2F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-07-29 | 2025-08-18 | 2.45 | 0%
R.E.5B.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.38 | 2025-07-29 | 2025-08-09 | 2.54 | 0%
R.E.5B.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.38 | 2025-07-29 | 2025-08-09 | 2.54 | 0%
R.E.5B.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-07-29 | 2025-08-18 | 2.65 | 0%
R.E.4B.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-07-30 | 2025-08-19 | 1.8 | 0%
F.E.Z2.EL.LG.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-07-30 | 2025-08-19 | 2.6 | 0%
F.E.Z5.F2.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-07-30 | 2025-08-19 | 1.4 | 0%
F.E.Z5.F2.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-07-30 | 2025-08-19 | 1 | 0%
F.E.Z7.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-07-30 | 2025-08-19 | 0.1 | 0%
F.E.Z7.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-07-30 | 2025-08-19 | 0.1 | 0%
F.E.Z4.F2.LG.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-07-30 | 2025-08-19 | 1.95 | 0%
F.E.Z4.F2.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-07-30 | 2025-08-19 | 1.35 | 0%
F.E.Z5.F2.LG.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-07-30 | 2025-08-19 | 1.95 | 0%
F.E.Z1.PL.BF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-31 | 2025-08-16 | 0.46 | 0%
F.E.Z1.DR.BF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-31 | 2025-08-16 | 0.46 | 0%
F.E.Z1.HV.BF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-31 | 2025-08-16 | 0.35 | 0%
F.E.Z1.EL.BF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-31 | 2025-08-16 | 0.35 | 0%
F.E.Z1.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-07-31 | 2025-08-16 | 0.77 | 0%
F.E.Z1.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-31 | 2025-08-16 | 0.77 | 0%
F.E.Z1.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-31 | 2025-08-16 | 0.62 | 0%
F.E.Z1.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-31 | 2025-08-16 | 0.62 | 0%
F.E.Z2.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-07-31 | 2025-08-16 | 2.38 | 0%
F.E.Z2.HV.RF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-07-31 | 2025-08-16 | 2.38 | 0%
F.E.Z2.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-07-31 | 2025-08-16 | 2.04 | 0%
F.E.Z3.AR.BF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-07-31 | 2025-08-16 | 0.77 | 0%
F.E.Z3.AR.BF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-07-31 | 2025-08-16 | 0.77 | 0%
F.E.Z3.AR.BF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-07-31 | 2025-08-16 | 0.77 | 0%
F.E.Z3.HV.2F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-07-31 | 2025-08-16 | 2.12 | 0%
F.E.Z3.FF.2F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-07-31 | 2025-08-16 | 2.27 | 0%
F.E.Z6.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-07-31 | 2025-08-20 | 2.05 | 0%
F.E.Z6.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-07-31 | 2025-08-20 | 0 | 0%
F.E.Z6.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-07-31 | 2025-08-20 | 0 | 0%
F.E.Z6.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-07-31 | 2025-08-20 | 0 | 0%
R.E.SS.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-07-31 | 2025-08-16 | 7.42 | 0%
F.E.Z2.F1.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Public Spaces | 0.54 | 2025-08-02 | 2025-08-17 | 1.88 | 0%
F.E.Z2.HV.BF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-02 | 2025-08-17 | 2 | 0%
F.E.Z2.FF.BF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-02 | 2025-08-17 | 2 | 0%
F.E.Z2.F1.LG.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Public Spaces | 0.54 | 2025-08-02 | 2025-08-17 | 2.77 | 0%
F.E.Z5.HV.3F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-02 | 2025-08-17 | 1.42 | 0%
F.E.Z5.FF.3F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-02 | 2025-08-17 | 1.42 | 0%
F.E.Z5.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-02 | 2025-08-17 | 0.19 | 0%
F.E.Z5.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-02 | 2025-08-17 | 0.19 | 0%
F.E.Z5.HV.RF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-02 | 2025-08-17 | 0.19 | 0%
F.E.Z5.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-02 | 2025-08-17 | 1.54 | 0%
F.E.Z6.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-02 | 2025-08-17 | 0 | 0%
F.E.Z2.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-08-03 | 2025-08-21 | 2.05 | 0%
F.E.Z2.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-03 | 2025-08-21 | 2.05 | 0%
F.E.Z2.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-03 | 2025-08-21 | 2.15 | 0%
F.E.Z2.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-03 | 2025-08-21 | 1.95 | 0%
F.E.Z2.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.75 | 2025-08-03 | 2025-08-21 | 6.55 | 0%
F.E.Z5.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-08-03 | 2025-08-21 | 4.9 | 0%
F.E.Z5.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-08-03 | 2025-08-21 | 4.9 | 0%
F.E.Z5.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-08-03 | 2025-08-21 | 7.5 | 0%
F.E.Z9.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-03 | 2025-08-18 | 1.85 | 0%
F.E.Z9.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-03 | 2025-08-18 | 1.85 | 0%
F.E.Z9.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-03 | 2025-08-18 | 1.85 | 0%
F.E.Z9.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-08-03 | 2025-08-18 | 2.08 | 0%
F.E.Z9.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-08-03 | 2025-08-18 | 2.31 | 0%
F.E.Z4.F2.2F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-03 | 2025-08-18 | 3.69 | 0%
R.E.VL.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.75 | 2025-08-03 | 2025-08-21 | 0 | 0%
F.E.Z1.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-08-04 | 2025-08-19 | 4.69 | 0%
F.E.Z1.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-08-04 | 2025-08-19 | 4.69 | 0%
F.E.Z1.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-08-04 | 2025-08-19 | 6.35 | 0%
F.E.Z2.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-08-04 | 2025-08-24 | 5.65 | 0%
F.E.Z2.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-08-04 | 2025-08-24 | 5.65 | 0%
F.E.Z2.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-08-04 | 2025-08-24 | 7.45 | 0%
F.E.Z3.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-08-04 | 2025-08-19 | 2.31 | 0%
F.E.Z3.AR.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-08-04 | 2025-08-19 | 2.31 | 0%
F.E.Z5.F2.3F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-08-04 | 2025-08-24 | 2.55 | 0%
F.E.Z5.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-04 | 2025-08-24 | 0.2 | 0%
F.E.Z5.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-04 | 2025-08-24 | 0.2 | 0%
F.E.Z5.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-04 | 2025-08-24 | 0.2 | 0%
F.E.Z2.F1.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Public Spaces | 0.54 | 2025-08-05 | 2025-08-20 | 1.88 | 0%
F.E.Z2.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-08-05 | 2025-08-25 | 3.7 | 0%
F.E.Z2.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-05 | 2025-08-25 | 2.2 | 0%
F.E.Z2.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-05 | 2025-08-25 | 2.2 | 0%
F.E.Z2.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-05 | 2025-08-25 | 2.2 | 0%
F.E.Z3.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-08-05 | 2025-08-20 | 4.65 | 0%
F.E.Z3.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-08-05 | 2025-08-20 | 4.65 | 0%
F.E.Z3.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-08-05 | 2025-08-20 | 6.31 | 0%
F.E.Z5.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-08-05 | 2025-08-25 | 4.85 | 0%
F.E.Z6.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-08-05 | 2025-08-20 | 0.35 | 0%
F.E.Z6.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-08-05 | 2025-08-20 | 4.23 | 0%
F.E.Z6.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-08-05 | 2025-08-20 | 5.92 | 0%
R.E.6B.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-08-05 | 2025-08-25 | 2.75 | 0%
F.E.Z2.F1.LG.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.75 | 2025-08-06 | 2025-08-26 | 3.6 | 0%
F.E.Z2.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-08-06 | 2025-08-26 | 5.65 | 0%
F.E.Z4.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2025-08-06 | 2025-08-26 | 5.6 | 0%
F.E.Z4.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-08-06 | 2025-08-26 | 1.9 | 0%
F.E.Z4.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-08-06 | 2025-08-26 | 1.95 | 0%
F.E.Z5.F2.2F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-08-06 | 2025-08-26 | 1 | 0%
F.E.Z1.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-08-07 | 2025-08-23 | 4.65 | 0%
F.E.Z1.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-07 | 2025-08-27 | 0.4 | 0%
F.E.Z1.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-07 | 2025-08-27 | 0.4 | 0%
F.E.Z1.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-07 | 2025-08-27 | 0.4 | 0%
F.E.Z1.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-07 | 2025-08-27 | 0.7 | 0%
F.E.Z1.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-07 | 2025-08-27 | 0.7 | 0%
F.E.Z1.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-07 | 2025-08-27 | 0.7 | 0%
F.E.Z1.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-08-07 | 2025-08-27 | 5.05 | 0%
F.E.Z1.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-08-07 | 2025-08-27 | 6.95 | 0%
F.E.Z3.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-08-07 | 2025-08-23 | 4.65 | 0%
F.E.Z4.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-08-07 | 2025-08-23 | 6.38 | 0%
F.E.Z5.F2.3F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-08-07 | 2025-08-23 | 0.85 | 0%
F.E.Z5.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-08-07 | 2025-08-27 | 6.45 | 0%
F.E.Z7.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-07 | 2025-08-23 | 0.12 | 0%
F.E.Z7.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-07 | 2025-08-23 | 0.12 | 0%
F.E.Z7.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-07 | 2025-08-23 | 0.12 | 0%
F.E.Z7.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-08-07 | 2025-08-23 | 4.15 | 0%
F.E.Z7.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-08-07 | 2025-08-23 | 5.85 | 0%
R.E.VL.ST.FO.GA.002 | Prepare and Submit Shop Drawings For Foundation General arrangement | 0.54 | 2025-08-07 | 2025-08-23 | 0 | 0%
R.E.VL.ST.FO.SR.002 | Prepare and Submit Shop Drawings For Foundation Steel Reinforcement | 0.54 | 2025-08-07 | 2025-08-23 | 0 | 0%
F.E.Z1.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-09 | 2025-08-24 | 1.46 | 0%
F.E.Z1.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-09 | 2025-08-24 | 1.46 | 0%
F.E.Z1.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-09 | 2025-08-24 | 1.46 | 0%
F.E.Z1.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-08-09 | 2025-08-24 | 5.38 | 0%
F.E.Z3.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-09 | 2025-08-24 | 1.58 | 0%
F.E.Z3.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-09 | 2025-08-24 | 1.58 | 0%
F.E.Z3.HV.RF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-09 | 2025-08-24 | 1.65 | 0%
F.E.Z3.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-09 | 2025-08-24 | 1.88 | 0%
F.E.Z1.AR.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-08-10 | 2025-08-25 | 2.35 | 0%
F.E.Z2.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-08-10 | 2025-08-28 | 6.4 | 0%
F.E.Z3.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-08-10 | 2025-08-25 | 5.35 | 0%
F.E.Z3.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-10 | 2025-08-28 | 1.5 | 0%
F.E.Z3.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-10 | 2025-08-28 | 1.5 | 0%
F.E.Z3.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-10 | 2025-08-28 | 1.5 | 0%
F.E.Z3.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-08-10 | 2025-08-28 | 5 | 0%
F.E.Z3.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-08-10 | 2025-08-28 | 6.9 | 0%
F.E.Z5.F2.3F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-08-10 | 2025-08-25 | 1.35 | 0%
F.E.Z5.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-08-10 | 2025-08-28 | 6.45 | 0%
F.E.Z1.F1.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For Public Spaces | 0.54 | 2025-08-10 | 2025-08-25 | 2.42 | 0%
F.E.Z4.F2.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-08-10 | 2025-08-28 | 3.4 | 0%
F.E.Z4.F2.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-08-10 | 2025-08-28 | 3.35 | 0%
R.E.5B.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-08-10 | 2025-08-28 | 2.75 | 0%
R.E.5B.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-08-10 | 2025-08-28 | 2.75 | 0%
R.E.5B.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-08-10 | 2025-08-28 | 2.75 | 0%
R.E.5B.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-08-10 | 2025-08-28 | 2.75 | 0%
F.E.Z1.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-08-11 | 2025-08-26 | 1.46 | 0%
F.E.Z1.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-08-11 | 2025-08-26 | 5.38 | 0%
R.E.4B.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-08-11 | 2025-08-31 | 1.9 | 0%
R.E.4B.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-08-11 | 2025-08-31 | 1.9 | 0%
R.E.4B.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-08-11 | 2025-08-31 | 1.9 | 0%
R.E.4B.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-08-11 | 2025-08-31 | 1.9 | 0%
F.E.Z2.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-08-11 | 2025-08-31 | 6.4 | 0%
F.E.Z3.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-08-11 | 2025-08-26 | 1.5 | 0%
F.E.Z8.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-08-11 | 2025-08-31 | 0.4 | 0%
F.E.Z8.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-08-11 | 2025-08-31 | 0.4 | 0%
F.E.Z2.F1.BF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.75 | 2025-08-12 | 2025-09-01 | 2.6 | 0%
F.E.Z3.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-08-12 | 2025-08-27 | 5.35 | 0%
F.E.Z6.F2.1F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-08-12 | 2025-08-27 | 1.27 | 0%
F.E.Z6.AR.2F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-12 | 2025-08-27 | 0.69 | 0%
F.E.Z6.AR.2F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-12 | 2025-08-27 | 0.69 | 0%
F.E.Z6.AR.2F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-12 | 2025-08-27 | 0.69 | 0%
F.E.Z7.AR.BF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-12 | 2025-08-27 | 0.65 | 0%
F.E.Z7.AR.BF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-12 | 2025-08-27 | 0.65 | 0%
F.E.Z7.AR.BF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-12 | 2025-08-27 | 0.65 | 0%
F.E.Z4.F2.LG.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-12 | 2025-08-27 | 2.15 | 0%
F.E.Z5.F2.LG.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-12 | 2025-08-27 | 2.15 | 0%
F.E.Z2.F1.LG.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.75 | 2025-08-13 | 2025-09-02 | 3 | 0%
F.E.Z2.HV.LG.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-08-13 | 2025-09-02 | 2.6 | 0%
F.E.Z2.FF.LG.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-08-13 | 2025-09-02 | 3.1 | 0%
F.E.Z6.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-08-13 | 2025-09-02 | 0.7 | 0%
F.E.Z6.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-08-13 | 2025-09-02 | 0.5 | 0%
F.E.Z6.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-08-13 | 2025-09-02 | 0.65 | 0%
F.E.Z4.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-08-14 | 2025-08-30 | 5.81 | 0%
F.E.Z5.F2.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-14 | 2025-08-30 | 2.35 | 0%
F.E.Z6.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-08-14 | 2025-09-03 | 0.1 | 0%
F.E.Z6.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-14 | 2025-09-03 | 0.15 | 0%
F.E.Z6.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-14 | 2025-09-03 | 0.1 | 0%
F.E.Z9.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-14 | 2025-08-30 | 2.31 | 0%
F.E.Z9.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-14 | 2025-08-30 | 2.27 | 0%
F.E.Z9.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-08-14 | 2025-08-30 | 2.08 | 0%
F.E.Z9.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-08-14 | 2025-08-30 | 2.08 | 0%
F.E.Z9.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-08-14 | 2025-08-30 | 5.54 | 0%
F.E.Z4.F2.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-14 | 2025-08-30 | 2.42 | 0%
F.E.Z5.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-08-16 | 2025-08-31 | 2.54 | 0%
F.E.Z5.AR.RF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-08-16 | 2025-08-31 | 1.42 | 0%
F.E.Z6.AR.BF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-16 | 2025-08-31 | 0.12 | 0%
F.E.Z6.AR.BF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-16 | 2025-08-31 | 0.12 | 0%
F.E.Z6.AR.BF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-16 | 2025-08-31 | 0.12 | 0%
F.E.Z9.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-08-16 | 2025-08-31 | 2.08 | 0%
R.E.6B.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-08-16 | 2025-08-31 | 2.12 | 0%
R.E.6B.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-08-16 | 2025-08-31 | 2.12 | 0%
R.E.6B.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-08-16 | 2025-08-31 | 2.12 | 0%
R.E.6B.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-08-16 | 2025-08-31 | 2.12 | 0%
F.E.Z1.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-08-17 | 2025-09-01 | 1.5 | 0%
F.E.Z1.AR.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-08-17 | 2025-09-01 | 0.38 | 0%
F.E.Z1.HV.BF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-17 | 2025-09-01 | 1.77 | 0%
F.E.Z1.FF.BF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-17 | 2025-09-01 | 1.88 | 0%
F.E.Z1.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-17 | 2025-09-01 | 2.5 | 0%
F.E.Z1.HV.RF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-17 | 2025-09-01 | 2.58 | 0%
F.E.Z1.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-17 | 2025-09-01 | 1.65 | 0%
F.E.Z1.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-08-17 | 2025-09-04 | 0.5 | 0%
F.E.Z1.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-17 | 2025-09-04 | 0.5 | 0%
F.E.Z1.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-17 | 2025-09-04 | 0.4 | 0%
F.E.Z1.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-17 | 2025-09-04 | 0.4 | 0%
F.E.Z1.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-08-17 | 2025-09-04 | 0.85 | 0%
F.E.Z1.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-17 | 2025-09-04 | 0.85 | 0%
F.E.Z1.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-17 | 2025-09-04 | 0.7 | 0%
F.E.Z1.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-17 | 2025-09-04 | 0.7 | 0%
F.E.Z2.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-17 | 2025-09-04 | 2.6 | 0%
F.E.Z2.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-17 | 2025-09-04 | 2.6 | 0%
F.E.Z2.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-17 | 2025-09-04 | 2.2 | 0%
F.E.Z3.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-08-17 | 2025-09-01 | 1.42 | 0%
F.E.Z3.PL.BF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-17 | 2025-09-01 | 0.88 | 0%
F.E.Z3.DR.BF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-17 | 2025-09-01 | 0.88 | 0%
F.E.Z3.HV.BF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-17 | 2025-09-01 | 0.96 | 0%
F.E.Z3.EL.BF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-17 | 2025-09-01 | 0.81 | 0%
F.E.Z3.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-17 | 2025-09-04 | 0.85 | 0%
F.E.Z3.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-17 | 2025-09-04 | 0.85 | 0%
F.E.Z3.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-17 | 2025-09-04 | 0.85 | 0%
F.E.Z3.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-08-17 | 2025-09-04 | 2.3 | 0%
F.E.Z3.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-08-17 | 2025-09-04 | 2.45 | 0%
F.E.Z9.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-08-17 | 2025-09-01 | 2.08 | 0%
R.E.SS.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-08-17 | 2025-09-04 | 8.05 | 0%
F.E.Z1.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-18 | 2025-09-02 | 0.85 | 0%
F.E.Z1.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-18 | 2025-09-02 | 1 | 0%
F.E.Z2.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-08-18 | 2025-09-02 | 5.92 | 0%
F.E.Z2.F1.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.75 | 2025-08-18 | 2025-09-07 | 2.05 | 0%
F.E.Z2.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-08-18 | 2025-09-07 | 2.15 | 0%
F.E.Z2.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-08-18 | 2025-09-07 | 2.15 | 0%
F.E.Z2.F1.LG.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.75 | 2025-08-18 | 2025-09-07 | 3 | 0%
F.E.Z5.HV.3F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-08-18 | 2025-09-07 | 1.55 | 0%
F.E.Z5.FF.3F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-08-18 | 2025-09-07 | 1.55 | 0%
F.E.Z5.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-08-18 | 2025-09-07 | 0.2 | 0%
F.E.Z5.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-18 | 2025-09-07 | 0.2 | 0%
F.E.Z5.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-18 | 2025-09-07 | 0.2 | 0%
F.E.Z5.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-18 | 2025-09-07 | 1.65 | 0%
F.E.Z6.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-08-18 | 2025-09-02 | 4.23 | 0%
F.E.Z6.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-08-18 | 2025-09-02 | 4.23 | 0%
F.E.Z6.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-08-18 | 2025-09-02 | 6.19 | 0%
F.E.Z6.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-18 | 2025-09-07 | 0 | 0%
F.E.Z9.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-18 | 2025-09-02 | 2 | 0%
F.E.Z9.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-08-18 | 2025-09-02 | 2.96 | 0%
R.E.5B.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-08-18 | 2025-09-02 | 2.62 | 0%
R.E.5B.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-08-18 | 2025-09-02 | 2.62 | 0%
R.E.4B.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-08-19 | 2025-09-03 | 1.73 | 0%
R.E.4B.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-08-19 | 2025-09-03 | 1.73 | 0%
F.E.Z2.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-08-19 | 2025-09-03 | 6 | 0%
F.E.Z3.AR.RF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-08-19 | 2025-09-03 | 2.15 | 0%
F.E.Z5.F2.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-08-19 | 2025-09-03 | 2.19 | 0%
F.E.Z5.F2.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-19 | 2025-09-03 | 2.15 | 0%
F.E.Z5.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-08-19 | 2025-09-03 | 6 | 0%
F.E.Z6.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-08-19 | 2025-09-03 | 4.27 | 0%
F.E.Z7.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-08-19 | 2025-09-03 | 4.19 | 0%
F.E.Z7.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-08-19 | 2025-09-03 | 4.19 | 0%
F.E.Z7.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-08-19 | 2025-09-03 | 5.85 | 0%
F.E.Z8.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-08-19 | 2025-09-03 | 0.35 | 0%
F.E.Z8.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-08-19 | 2025-09-03 | 0.35 | 0%
F.E.Z8.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-19 | 2025-09-03 | 0.46 | 0%
F.E.Z8.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-19 | 2025-09-03 | 0.46 | 0%
F.E.Z8.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-19 | 2025-09-03 | 0.46 | 0%
F.E.Z9.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-19 | 2025-09-08 | 2 | 0%
F.E.Z9.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-19 | 2025-09-08 | 2 | 0%
F.E.Z9.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-19 | 2025-09-08 | 2 | 0%
F.E.Z9.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-08-19 | 2025-09-08 | 2.25 | 0%
F.E.Z9.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-08-19 | 2025-09-08 | 2.5 | 0%
F.E.Z4.F2.2F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-08-19 | 2025-09-08 | 4 | 0%
F.E.Z1.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-08-20 | 2025-09-09 | 5.05 | 0%
F.E.Z1.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-08-20 | 2025-09-09 | 5.05 | 0%
F.E.Z1.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-08-20 | 2025-09-09 | 6.85 | 0%
F.E.Z3.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-08-20 | 2025-09-09 | 2.5 | 0%
F.E.Z3.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-08-20 | 2025-09-09 | 2.5 | 0%
F.E.Z1.AR.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-08-21 | 2025-09-06 | 1.73 | 0%
R.E.GE.EX.GE.PO.002 | Prepare and Submit Shop Drawings For Pools and Water Features | 0.54 | 2025-08-21 | 2025-09-06 | 0.58 | 0%
F.E.Z2.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-21 | 2025-09-06 | 5.19 | 0%
F.E.Z2.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-21 | 2025-09-06 | 5.23 | 0%
F.E.Z2.F1.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.75 | 2025-08-21 | 2025-09-10 | 2 | 0%
F.E.Z3.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-08-21 | 2025-09-10 | 5 | 0%
F.E.Z3.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-08-21 | 2025-09-10 | 5 | 0%
F.E.Z3.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-08-21 | 2025-09-10 | 6.8 | 0%
F.E.Z6.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-08-21 | 2025-09-10 | 0.35 | 0%
F.E.Z6.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-08-21 | 2025-09-10 | 4.55 | 0%
F.E.Z6.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-08-21 | 2025-09-10 | 6.45 | 0%
F.E.Z8.AR.BF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-08-21 | 2025-09-06 | 0.27 | 0%
F.E.Z8.AR.BF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-08-21 | 2025-09-06 | 0.27 | 0%
F.E.Z8.AR.BF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-08-21 | 2025-09-06 | 0.27 | 0%
F.E.Z1.F1.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Public Spaces | 0.54 | 2025-08-21 | 2025-09-06 | 0.38 | 0%
F.E.Z4.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-08-23 | 2025-09-07 | 6.85 | 0%
F.E.Z6.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-08-23 | 2025-09-07 | 4.92 | 0%
F.E.Z7.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-08-23 | 2025-09-07 | 4.15 | 0%
F.E.Z7.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-08-23 | 2025-09-07 | 6.85 | 0%
F.E.Z1.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-08-24 | 2025-09-11 | 5.05 | 0%
F.E.Z3.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-08-24 | 2025-09-11 | 5.05 | 0%
F.E.Z4.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-08-24 | 2025-09-11 | 6.9 | 0%
F.E.Z5.F2.3F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-08-24 | 2025-09-11 | 0.95 | 0%
F.E.Z7.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-24 | 2025-09-08 | 0.23 | 0%
F.E.Z7.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-24 | 2025-09-08 | 0.23 | 0%
F.E.Z7.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-24 | 2025-09-08 | 0.31 | 0%
F.E.Z7.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-24 | 2025-09-11 | 0.15 | 0%
F.E.Z7.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-24 | 2025-09-11 | 0.15 | 0%
F.E.Z7.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-24 | 2025-09-11 | 0.15 | 0%
F.E.Z7.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-08-24 | 2025-09-11 | 4.5 | 0%
F.E.Z7.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-08-24 | 2025-09-11 | 6.4 | 0%
R.E.VL.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.75 | 2025-08-24 | 2025-09-11 | 0 | 0%
R.E.VL.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.75 | 2025-08-24 | 2025-09-11 | 0 | 0%
F.E.Z1.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-25 | 2025-09-14 | 1.6 | 0%
F.E.Z1.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-25 | 2025-09-14 | 1.6 | 0%
F.E.Z1.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-25 | 2025-09-14 | 1.6 | 0%
F.E.Z1.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-08-25 | 2025-09-14 | 5.85 | 0%
F.E.Z3.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-08-25 | 2025-09-14 | 1.7 | 0%
F.E.Z3.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-25 | 2025-09-14 | 1.7 | 0%
F.E.Z3.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-25 | 2025-09-14 | 1.8 | 0%
F.E.Z3.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-08-25 | 2025-09-14 | 2.05 | 0%
F.E.Z4.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-08-25 | 2025-09-09 | 7.31 | 0%
F.E.Z6.F2.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-08-25 | 2025-09-09 | 0 | 0%
F.E.Z6.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-25 | 2025-09-09 | 0.38 | 0%
F.E.Z6.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-25 | 2025-09-09 | 0.54 | 0%
F.E.Z6.PL.2F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-25 | 2025-09-09 | 0.85 | 0%
F.E.Z6.DR.2F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-25 | 2025-09-09 | 0.85 | 0%
F.E.Z6.HV.2F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-25 | 2025-09-09 | 0.92 | 0%
F.E.Z6.EL.2F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-25 | 2025-09-09 | 1.46 | 0%
F.E.Z6.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-08-25 | 2025-09-09 | 4.92 | 0%
F.E.Z7.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-08-25 | 2025-09-09 | 5.08 | 0%
F.E.Z1.F1.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Public Spaces | 0.54 | 2025-08-25 | 2025-09-09 | 1.69 | 0%
F.E.Z1.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-08-26 | 2025-09-10 | 0.38 | 0%
F.E.Z1.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-08-26 | 2025-09-10 | 0.73 | 0%
F.E.Z1.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-08-26 | 2025-09-15 | 2.55 | 0%
F.E.Z3.AR.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-08-26 | 2025-09-10 | 1.5 | 0%
F.E.Z3.AR.RF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-08-26 | 2025-09-10 | 1.54 | 0%
F.E.Z3.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-26 | 2025-09-10 | 1.54 | 0%
F.E.Z3.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-26 | 2025-09-10 | 1.69 | 0%
F.E.Z3.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-08-26 | 2025-09-15 | 5.8 | 0%
F.E.Z5.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-08-26 | 2025-09-10 | 5.42 | 0%
F.E.Z5.F2.3F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-08-26 | 2025-09-15 | 1.45 | 0%
F.E.Z7.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-26 | 2025-09-10 | 0.15 | 0%
F.E.Z7.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-08-26 | 2025-09-10 | 5.35 | 0%
F.E.Z1.F1.BF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.75 | 2025-08-26 | 2025-09-15 | 2.6 | 0%
F.E.Z3.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2025-08-26 | 2025-09-10 | 1.96 | 0%
F.E.Z1.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-08-27 | 2025-09-16 | 1.55 | 0%
F.E.Z1.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-08-27 | 2025-09-16 | 5.8 | 0%
F.E.Z3.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-08-27 | 2025-09-16 | 1.6 | 0%
F.E.Z2.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-08-28 | 2025-09-13 | 5.35 | 0%
F.E.Z3.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-08-28 | 2025-09-17 | 5.75 | 0%
F.E.Z6.F2.1F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-08-28 | 2025-09-17 | 1.35 | 0%
F.E.Z6.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-28 | 2025-09-17 | 0.75 | 0%
F.E.Z6.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-28 | 2025-09-17 | 0.75 | 0%
F.E.Z6.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-28 | 2025-09-17 | 0.75 | 0%
F.E.Z7.PL.BF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-28 | 2025-09-13 | 0.77 | 0%
F.E.Z7.DR.BF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-28 | 2025-09-13 | 0.77 | 0%
F.E.Z7.HV.BF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-28 | 2025-09-13 | 0.88 | 0%
F.E.Z7.EL.BF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-08-28 | 2025-09-13 | 0.65 | 0%
F.E.Z7.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-08-28 | 2025-09-17 | 0.7 | 0%
F.E.Z7.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-08-28 | 2025-09-17 | 0.7 | 0%
F.E.Z7.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-08-28 | 2025-09-17 | 0.7 | 0%
F.E.Z8.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-28 | 2025-09-13 | 0.65 | 0%
F.E.Z8.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-28 | 2025-09-13 | 0.65 | 0%
F.E.Z8.HV.GF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-28 | 2025-09-13 | 0.65 | 0%
F.E.Z4.F2.LG.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-08-28 | 2025-09-17 | 2.3 | 0%
F.E.Z5.F2.LG.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-08-28 | 2025-09-17 | 2.3 | 0%
F.E.Z5.F2.2F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-08-28 | 2025-09-13 | 2.85 | 0%
F.E.Z2.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-08-30 | 2025-09-14 | 2.04 | 0%
F.E.Z5.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2025-08-30 | 2025-09-14 | 3.65 | 0%
F.E.Z5.AR.RF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-08-30 | 2025-09-14 | 0.42 | 0%
F.E.Z5.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-08-30 | 2025-09-14 | 0.46 | 0%
F.E.Z5.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-08-30 | 2025-09-14 | 0.5 | 0%
F.E.Z6.PL.BF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-08-30 | 2025-09-14 | 0.38 | 0%
F.E.Z6.DR.BF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-08-30 | 2025-09-14 | 0.42 | 0%
F.E.Z6.HV.BF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-08-30 | 2025-09-14 | 0.46 | 0%
F.E.Z2.F1.LG.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Public Spaces | 0.54 | 2025-08-31 | 2025-09-15 | 2.88 | 0%
F.E.Z3.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-08-31 | 2025-09-15 | 1.5 | 0%
F.E.Z3.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-08-31 | 2025-09-15 | 1.54 | 0%
F.E.Z4.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-08-31 | 2025-09-18 | 6.3 | 0%
F.E.Z5.F2.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-08-31 | 2025-09-18 | 2.55 | 0%
F.E.Z9.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-08-31 | 2025-09-15 | 1.85 | 0%
F.E.Z9.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-08-31 | 2025-09-18 | 2.5 | 0%
F.E.Z9.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-08-31 | 2025-09-18 | 2.45 | 0%
F.E.Z9.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-08-31 | 2025-09-18 | 2.25 | 0%
F.E.Z9.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-08-31 | 2025-09-18 | 2.25 | 0%
F.E.Z9.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-08-31 | 2025-09-18 | 6.05 | 0%
F.E.Z4.F2.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-08-31 | 2025-09-18 | 2.65 | 0%
F.E.Z5.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-09-01 | 2025-09-21 | 2.75 | 0%
F.E.Z5.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-09-01 | 2025-09-21 | 1.55 | 0%
F.E.Z6.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-09-01 | 2025-09-21 | 0.15 | 0%
F.E.Z6.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-09-01 | 2025-09-21 | 0.15 | 0%
F.E.Z6.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-09-01 | 2025-09-21 | 0.15 | 0%
F.E.Z7.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-01 | 2025-09-16 | 0.77 | 0%
F.E.Z7.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-01 | 2025-09-16 | 0.77 | 0%
F.E.Z7.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-01 | 2025-09-16 | 0.77 | 0%
F.E.Z8.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-09-01 | 2025-09-16 | 0.54 | 0%
F.E.Z9.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-09-01 | 2025-09-21 | 2.25 | 0%
R.E.6B.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-09-01 | 2025-09-21 | 2.3 | 0%
R.E.6B.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-09-01 | 2025-09-21 | 2.3 | 0%
R.E.6B.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-01 | 2025-09-21 | 2.3 | 0%
R.E.6B.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-01 | 2025-09-21 | 2.3 | 0%
F.E.Z1.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-02 | 2025-09-17 | 5.19 | 0%
F.E.Z1.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-09-02 | 2025-09-22 | 1.6 | 0%
F.E.Z1.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-09-02 | 2025-09-22 | 0.4 | 0%
F.E.Z1.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-02 | 2025-09-22 | 1.9 | 0%
F.E.Z1.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-02 | 2025-09-22 | 2.05 | 0%
F.E.Z1.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-02 | 2025-09-22 | 2.7 | 0%
F.E.Z1.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-02 | 2025-09-22 | 2.8 | 0%
F.E.Z1.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-02 | 2025-09-22 | 1.8 | 0%
F.E.Z3.AR.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-09-02 | 2025-09-17 | 0.88 | 0%
F.E.Z3.HV.BF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-02 | 2025-09-17 | 0.88 | 0%
F.E.Z3.FF.BF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-02 | 2025-09-17 | 1.04 | 0%
F.E.Z3.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-09-02 | 2025-09-22 | 1.55 | 0%
F.E.Z3.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-02 | 2025-09-22 | 0.95 | 0%
F.E.Z3.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-02 | 2025-09-22 | 0.95 | 0%
F.E.Z3.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-02 | 2025-09-22 | 1.05 | 0%
F.E.Z3.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-02 | 2025-09-22 | 0.85 | 0%
F.E.Z6.EL.BF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-09-02 | 2025-09-17 | 0.15 | 0%
F.E.Z6.F2.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-09-02 | 2025-09-17 | 0.15 | 0%
F.E.Z8.PL.BF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-09-02 | 2025-09-17 | 0.54 | 0%
F.E.Z8.DR.BF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-09-02 | 2025-09-17 | 0.54 | 0%
F.E.Z8.HV.BF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-09-02 | 2025-09-17 | 0.62 | 0%
F.E.Z9.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-09-02 | 2025-09-22 | 2.25 | 0%
F.E.Z7.F1.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For Public Spaces | 0.54 | 2025-09-02 | 2025-09-17 | 0.96 | 0%
R.E.VL.ST.CL.SR.002 | Prepare and Submit Shop Drawings For Columns Steel Reinforcement | 0.54 | 2025-09-02 | 2025-09-17 | 0 | 0%
F.E.Z1.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-03 | 2025-09-24 | 0.9 | 0%
F.E.Z1.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-03 | 2025-09-24 | 1.05 | 0%
F.E.Z2.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-09-03 | 2025-09-24 | 6.4 | 0%
F.E.Z6.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-09-03 | 2025-09-24 | 4.55 | 0%
F.E.Z6.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-09-03 | 2025-09-24 | 4.55 | 0%
F.E.Z6.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-09-03 | 2025-09-24 | 6.7 | 0%
F.E.Z9.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-03 | 2025-09-24 | 2.15 | 0%
F.E.Z9.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-09-03 | 2025-09-24 | 3.2 | 0%
R.E.5B.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-03 | 2025-09-24 | 2.8 | 0%
R.E.5B.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-03 | 2025-09-24 | 2.8 | 0%
R.E.4B.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-04 | 2025-09-25 | 1.85 | 0%
R.E.4B.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-04 | 2025-09-25 | 1.85 | 0%
F.E.Z2.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-09-04 | 2025-09-25 | 6.45 | 0%
F.E.Z3.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-09-04 | 2025-09-25 | 2.3 | 0%
F.E.Z5.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-09-04 | 2025-09-20 | 6.42 | 0%
F.E.Z5.F2.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-09-04 | 2025-09-25 | 2.35 | 0%
F.E.Z5.F2.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-09-04 | 2025-09-25 | 2.3 | 0%
F.E.Z5.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-09-04 | 2025-09-25 | 6.45 | 0%
F.E.Z6.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-09-04 | 2025-09-25 | 4.6 | 0%
F.E.Z7.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-09-04 | 2025-09-25 | 4.5 | 0%
F.E.Z7.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-09-04 | 2025-09-25 | 4.5 | 0%
F.E.Z7.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-09-04 | 2025-09-25 | 6.3 | 0%
F.E.Z8.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-04 | 2025-09-25 | 0.35 | 0%
F.E.Z8.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-04 | 2025-09-25 | 0.35 | 0%
F.E.Z8.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-09-04 | 2025-09-25 | 0.5 | 0%
F.E.Z8.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-09-04 | 2025-09-25 | 0.5 | 0%
F.E.Z8.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-09-04 | 2025-09-25 | 0.5 | 0%
F.E.Z6.F2.2F.RP.002 | Prepare and Submit Shop Drawings For RCP For Guest Rooms | 0.54 | 2025-09-04 | 2025-09-20 | 1.62 | 0%
F.E.Z1.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-09-06 | 2025-09-21 | 5.42 | 0%
F.E.Z2.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-09-06 | 2025-09-21 | 6.38 | 0%
F.E.Z1.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-07 | 2025-09-28 | 1.9 | 0%
R.E.GE.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.75 | 2025-09-07 | 2025-09-28 | 0.65 | 0%
F.E.Z2.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-07 | 2025-09-28 | 5.65 | 0%
F.E.Z2.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-07 | 2025-09-28 | 5.7 | 0%
F.E.Z3.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-09-07 | 2025-09-22 | 5.38 | 0%
F.E.Z5.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-09-07 | 2025-09-22 | 0.19 | 0%
F.E.Z5.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-09-07 | 2025-09-22 | 6.88 | 0%
F.E.Z6.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-09-07 | 2025-09-22 | 0.85 | 0%
F.E.Z8.EL.BF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-09-07 | 2025-09-22 | 0.27 | 0%
F.E.Z8.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-09-07 | 2025-09-28 | 0.3 | 0%
F.E.Z8.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-09-07 | 2025-09-28 | 0.3 | 0%
F.E.Z8.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-09-07 | 2025-09-28 | 0.3 | 0%
F.E.Z1.F1.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.75 | 2025-09-07 | 2025-09-28 | 0.45 | 0%
F.E.Z2.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-09-08 | 2025-09-24 | 6.85 | 0%
F.E.Z3.AR.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-09-08 | 2025-09-24 | 0.85 | 0%
F.E.Z4.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-09-08 | 2025-09-29 | 7.45 | 0%
F.E.Z6.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-09-08 | 2025-09-29 | 5.35 | 0%
F.E.Z7.AR.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-09-08 | 2025-09-24 | 1.46 | 0%
F.E.Z7.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-09-08 | 2025-09-29 | 4.5 | 0%
F.E.Z7.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-09-08 | 2025-09-29 | 7.45 | 0%
F.E.Z7.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-09 | 2025-09-30 | 0.25 | 0%
F.E.Z7.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-09 | 2025-09-30 | 0.25 | 0%
F.E.Z7.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-09 | 2025-09-30 | 0.35 | 0%
F.E.Z4.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-09-10 | 2025-10-01 | 7.9 | 0%
F.E.Z6.F2.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-09-10 | 2025-10-01 | 0 | 0%
F.E.Z6.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-10 | 2025-10-01 | 0.4 | 0%
F.E.Z6.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-10 | 2025-10-01 | 0.55 | 0%
F.E.Z6.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-10 | 2025-10-01 | 0.9 | 0%
F.E.Z6.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-10 | 2025-10-01 | 0.9 | 0%
F.E.Z6.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-10 | 2025-10-01 | 1 | 0%
F.E.Z6.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-10 | 2025-10-01 | 1.55 | 0%
F.E.Z6.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-09-10 | 2025-10-01 | 5.3 | 0%
F.E.Z7.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-09-10 | 2025-09-27 | 0.69 | 0%
F.E.Z7.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-10 | 2025-09-27 | 0.12 | 0%
F.E.Z7.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-10 | 2025-09-27 | 0.46 | 0%
F.E.Z7.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-09-10 | 2025-09-27 | 1.69 | 0%
F.E.Z7.HV.RF.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-09-10 | 2025-09-27 | 1.77 | 0%
F.E.Z7.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-09-10 | 2025-09-27 | 0.92 | 0%
F.E.Z7.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-09-10 | 2025-10-01 | 5.5 | 0%
F.E.Z9.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-10 | 2025-09-27 | 2.08 | 0%
F.E.Z9.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-10 | 2025-09-27 | 2.77 | 0%
F.E.Z1.F1.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.75 | 2025-09-10 | 2025-10-01 | 1.8 | 0%
F.E.Z7.F1.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Public Spaces | 0.54 | 2025-09-10 | 2025-09-27 | 0.23 | 0%
F.E.Z8.F1.GF.RP.002 | Prepare and Submit Shop Drawings For RCP For Public Spaces | 0.54 | 2025-09-10 | 2025-09-27 | 1.69 | 0%
F.E.Z1.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-09-11 | 2025-09-28 | 2.65 | 0%
F.E.Z1.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-09-11 | 2025-10-02 | 0.4 | 0%
F.E.Z1.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-11 | 2025-10-02 | 0.75 | 0%
F.E.Z3.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-09-11 | 2025-10-02 | 1.6 | 0%
F.E.Z3.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-09-11 | 2025-10-02 | 1.65 | 0%
F.E.Z3.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-11 | 2025-10-02 | 1.65 | 0%
F.E.Z3.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-11 | 2025-10-02 | 1.8 | 0%
F.E.Z5.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-09-11 | 2025-10-02 | 5.85 | 0%
F.E.Z6.HV.2F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-11 | 2025-09-28 | 0.92 | 0%
F.E.Z6.FF.2F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-11 | 2025-09-28 | 1.15 | 0%
F.E.Z7.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-11 | 2025-10-02 | 0.15 | 0%
F.E.Z7.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-09-11 | 2025-10-02 | 5.75 | 0%
F.E.Z6.F2.2F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Guest Rooms | 0.54 | 2025-09-11 | 2025-09-28 | 1 | 0%
R.E.5B.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-09-11 | 2025-09-28 | 2.62 | 0%
R.E.5B.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-09-11 | 2025-09-28 | 2.62 | 0%
R.E.5B.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-11 | 2025-09-28 | 3.46 | 0%
R.E.5B.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-11 | 2025-09-28 | 3.46 | 0%
R.E.5B.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-11 | 2025-09-28 | 3.46 | 0%
R.E.6B.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-09-11 | 2025-09-28 | 2.12 | 0%
R.E.6B.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-09-11 | 2025-09-28 | 2.12 | 0%
F.E.Z3.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2025-09-11 | 2025-10-02 | 2.1 | 0%
R.E.4B.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-09-13 | 2025-09-29 | 1.77 | 0%
R.E.4B.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-09-13 | 2025-09-29 | 1.77 | 0%
R.E.4B.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-13 | 2025-09-29 | 3.65 | 0%
R.E.4B.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-13 | 2025-09-29 | 3.65 | 0%
R.E.4B.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-13 | 2025-09-29 | 3.65 | 0%
F.E.Z6.AR.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-09-13 | 2025-09-29 | 1.42 | 0%
F.E.Z1.F1.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Public Spaces | 0.54 | 2025-09-13 | 2025-09-29 | 2.12 | 0%
F.E.Z1.F1.BF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Public Spaces | 0.54 | 2025-09-13 | 2025-09-29 | 2.12 | 0%
F.E.Z1.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-09-14 | 2025-09-30 | 4.81 | 0%
F.E.Z2.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-09-14 | 2025-10-05 | 5.8 | 0%
F.E.Z5.F2.3F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-09-14 | 2025-09-30 | 2.31 | 0%
F.E.Z6.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-09-14 | 2025-09-30 | 1.58 | 0%
F.E.Z7.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-14 | 2025-10-05 | 0.85 | 0%
F.E.Z7.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-14 | 2025-10-05 | 0.85 | 0%
F.E.Z7.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-14 | 2025-10-05 | 0.95 | 0%
F.E.Z7.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-14 | 2025-10-05 | 0.7 | 0%
F.E.Z8.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-14 | 2025-10-05 | 0.7 | 0%
F.E.Z8.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-14 | 2025-10-05 | 0.7 | 0%
F.E.Z8.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-14 | 2025-10-05 | 0.7 | 0%
F.E.Z5.F2.2F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-09-14 | 2025-10-05 | 3.1 | 0%
F.E.Z2.F1.LG.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Public Spaces | 0.54 | 2025-09-15 | 2025-10-01 | 2 | 0%
F.E.Z2.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-15 | 2025-10-06 | 2.2 | 0%
F.E.Z3.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-09-15 | 2025-10-01 | 4.77 | 0%
F.E.Z5.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2025-09-15 | 2025-10-06 | 3.95 | 0%
F.E.Z5.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-09-15 | 2025-10-06 | 0.45 | 0%
F.E.Z5.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-15 | 2025-10-06 | 0.5 | 0%
F.E.Z5.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-15 | 2025-10-06 | 0.55 | 0%
F.E.Z6.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-15 | 2025-10-06 | 0.4 | 0%
F.E.Z6.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-15 | 2025-10-06 | 0.45 | 0%
F.E.Z6.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-15 | 2025-10-06 | 0.5 | 0%
F.E.Z7.AR.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-09-15 | 2025-10-01 | 0.81 | 0%
F.E.Z7.HV.BF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-15 | 2025-10-01 | 0.65 | 0%
F.E.Z7.FF.BF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-15 | 2025-10-01 | 1 | 0%
F.E.Z8.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-15 | 2025-10-01 | 0.35 | 0%
F.E.Z8.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-15 | 2025-10-01 | 0.35 | 0%
F.E.Z8.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-15 | 2025-10-01 | 0.35 | 0%
F.E.Z8.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-09-15 | 2025-10-01 | 2.42 | 0%
F.E.Z8.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-09-15 | 2025-10-01 | 4.58 | 0%
F.E.Z7.F1.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Public Spaces | 0.54 | 2025-09-15 | 2025-10-01 | 0.23 | 0%
F.E.Z2.F1.LG.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.75 | 2025-09-16 | 2025-10-07 | 3.1 | 0%
F.E.Z3.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-09-16 | 2025-10-07 | 1.6 | 0%
F.E.Z3.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-16 | 2025-10-07 | 1.65 | 0%
F.E.Z9.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-09-16 | 2025-10-07 | 2 | 0%
F.E.Z7.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-09-17 | 2025-10-08 | 0.8 | 0%
F.E.Z7.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-09-17 | 2025-10-08 | 0.8 | 0%
F.E.Z7.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-09-17 | 2025-10-08 | 0.8 | 0%
F.E.Z8.AR.BF.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-09-17 | 2025-10-04 | 1.38 | 0%
F.E.Z8.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-17 | 2025-10-08 | 0.55 | 0%
F.E.Z6.F2.2F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Guest Rooms | 0.54 | 2025-09-17 | 2025-10-04 | 0.81 | 0%
R.E.VL.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-09-17 | 2025-10-04 | 0 | 0%
R.E.VL.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-09-17 | 2025-10-04 | 0 | 0%
R.E.VL.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-09-17 | 2025-10-04 | 0 | 0%
R.E.VL.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-09-17 | 2025-10-04 | 0 | 0%
R.E.SS.ST.ST.GA.002 | Prepare and Submit Shop Drawings For Stairs General arrangement | 0.54 | 2025-09-17 | 2025-10-04 | 6.08 | 0%
R.E.SS.ST.ST.SR.002 | Prepare and Submit Shop Drawings For Stairs Steel Reinforcement | 0.54 | 2025-09-17 | 2025-10-04 | 6.08 | 0%
R.E.SS.ST.GF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-09-17 | 2025-10-04 | 6.08 | 0%
R.E.SS.ST.GF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-09-17 | 2025-10-04 | 6.08 | 0%
F.E.Z1.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-18 | 2025-10-09 | 5.6 | 0%
F.E.Z3.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-09-18 | 2025-10-09 | 0.95 | 0%
F.E.Z3.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-18 | 2025-10-09 | 0.95 | 0%
F.E.Z3.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-18 | 2025-10-09 | 1.1 | 0%
F.E.Z6.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-18 | 2025-10-09 | 0.15 | 0%
F.E.Z6.F2.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-09-18 | 2025-10-09 | 0.15 | 0%
F.E.Z8.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-09-18 | 2025-10-09 | 0.55 | 0%
F.E.Z8.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-18 | 2025-10-09 | 0.55 | 0%
F.E.Z8.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-18 | 2025-10-09 | 0.65 | 0%
F.E.Z7.F1.GF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.75 | 2025-09-18 | 2025-10-09 | 1 | 0%
R.E.VL.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.75 | 2025-09-18 | 2025-10-09 | 0 | 0%
F.E.Z1.AR.BF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-09-20 | 2025-10-06 | 1.88 | 0%
F.E.Z2.F1.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Public Spaces | 0.54 | 2025-09-20 | 2025-10-06 | 1.38 | 0%
F.E.Z6.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-09-20 | 2025-10-06 | 0.62 | 0%
F.E.Z6.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-09-20 | 2025-10-06 | 4.96 | 0%
F.E.Z7.AR.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-09-20 | 2025-10-06 | 0.85 | 0%
F.E.Z3.AR.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-09-21 | 2025-10-07 | 0.15 | 0%
F.E.Z5.F2.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-21 | 2025-10-07 | 0.42 | 0%
F.E.Z5.F2.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-21 | 2025-10-07 | 1.15 | 0%
F.E.Z5.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-09-21 | 2025-10-12 | 7 | 0%
F.E.Z4.F2.LG.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-21 | 2025-10-07 | 0.96 | 0%
F.E.Z4.F2.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-21 | 2025-10-07 | 0.5 | 0%
F.E.Z4.F2.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-21 | 2025-10-07 | 1.27 | 0%
F.E.Z5.F2.LG.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-21 | 2025-10-07 | 0.96 | 0%
F.E.Z6.F2.2F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.75 | 2025-09-21 | 2025-10-12 | 1.75 | 0%
R.E.5B.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-21 | 2025-10-07 | 2.88 | 0%
R.E.5B.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-21 | 2025-10-07 | 2.88 | 0%
R.E.5B.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-21 | 2025-10-07 | 2.88 | 0%
R.E.5B.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-09-21 | 2025-10-07 | 3.81 | 0%
R.E.5B.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-09-21 | 2025-10-07 | 3.81 | 0%
R.E.5B.HV.1F.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-09-21 | 2025-10-07 | 3.81 | 0%
F.E.Z1.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-09-22 | 2025-10-08 | 5.85 | 0%
F.E.Z1.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-09-22 | 2025-10-13 | 5.85 | 0%
R.E.4B.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-22 | 2025-10-08 | 3.19 | 0%
R.E.4B.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-22 | 2025-10-08 | 3.19 | 0%
R.E.4B.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-22 | 2025-10-08 | 3.19 | 0%
F.E.Z2.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-09-22 | 2025-10-13 | 6.95 | 0%
F.E.Z7.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-09-22 | 2025-10-08 | 5.31 | 0%
F.E.Z3.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-09-24 | 2025-10-14 | 5.8 | 0%
F.E.Z5.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-24 | 2025-10-14 | 0.2 | 0%
F.E.Z5.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-09-24 | 2025-10-14 | 7.45 | 0%
F.E.Z6.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-09-24 | 2025-10-14 | 0.9 | 0%
F.E.Z8.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-24 | 2025-10-14 | 0.3 | 0%
F.E.Z1.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-09-25 | 2025-10-11 | 6.31 | 0%
F.E.Z2.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-09-25 | 2025-10-15 | 7.4 | 0%
F.E.Z3.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-09-25 | 2025-10-11 | 5.77 | 0%
F.E.Z3.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-25 | 2025-10-15 | 0.9 | 0%
F.E.Z5.F2.3F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-25 | 2025-10-11 | 1.23 | 0%
F.E.Z7.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-09-25 | 2025-10-15 | 1.55 | 0%
F.E.Z8.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-25 | 2025-10-11 | 0.69 | 0%
F.E.Z8.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-25 | 2025-10-11 | 0.92 | 0%
F.E.Z8.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-09-25 | 2025-10-11 | 0.46 | 0%
F.E.Z8.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-09-25 | 2025-10-11 | 0.46 | 0%
F.E.Z8.HV.1F.CF.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-09-25 | 2025-10-11 | 0.54 | 0%
F.E.Z8.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-09-25 | 2025-10-11 | 0.81 | 0%
F.E.Z9.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-09-25 | 2025-10-11 | 4.46 | 0%
F.E.Z4.F2.2F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-25 | 2025-10-11 | 1.23 | 0%
F.E.Z5.F2.2F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-09-25 | 2025-10-11 | 1.23 | 0%
F.E.Z8.F1.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For Public Spaces | 0.54 | 2025-09-25 | 2025-10-11 | 0.46 | 0%
F.E.Z3.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-09-27 | 2025-10-12 | 6.27 | 0%
F.E.Z6.AR.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-09-27 | 2025-10-12 | 0.19 | 0%
F.E.Z6.HV.BF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-27 | 2025-10-12 | 0.54 | 0%
F.E.Z6.FF.BF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-27 | 2025-10-12 | 0.77 | 0%
F.E.Z8.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-09-27 | 2025-10-12 | 2.42 | 0%
F.E.Z8.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-09-27 | 2025-10-12 | 2.42 | 0%
F.E.Z8.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-09-27 | 2025-10-12 | 4.62 | 0%
F.E.Z1.AR.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-09-28 | 2025-10-13 | 1.65 | 0%
R.E.4B.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-09-28 | 2025-10-13 | 3.85 | 0%
R.E.4B.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-09-28 | 2025-10-13 | 3.85 | 0%
R.E.4B.HV.1F.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-09-28 | 2025-10-13 | 3.77 | 0%
F.E.Z7.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-28 | 2025-10-13 | 4.19 | 0%
F.E.Z7.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-09-28 | 2025-10-16 | 0.75 | 0%
F.E.Z7.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-28 | 2025-10-16 | 0.15 | 0%
F.E.Z7.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-28 | 2025-10-16 | 0.5 | 0%
F.E.Z7.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-09-28 | 2025-10-16 | 1.85 | 0%
F.E.Z7.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-09-28 | 2025-10-16 | 1.95 | 0%
F.E.Z7.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-09-28 | 2025-10-16 | 1 | 0%
F.E.Z7.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-09-28 | 2025-10-13 | 1.62 | 0%
F.E.Z8.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-09-28 | 2025-10-13 | 2.46 | 0%
F.E.Z9.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-28 | 2025-10-16 | 2.25 | 0%
F.E.Z9.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-28 | 2025-10-16 | 3 | 0%
F.E.Z7.F1.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.75 | 2025-09-28 | 2025-10-16 | 0.25 | 0%
F.E.Z8.F1.GF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.75 | 2025-09-28 | 2025-10-16 | 1.85 | 0%
R.E.SS.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-09-28 | 2025-10-13 | 6.08 | 0%
R.E.SS.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-09-28 | 2025-10-13 | 6.08 | 0%
R.E.SS.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-09-28 | 2025-10-13 | 6.08 | 0%
F.E.Z1.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-09-29 | 2025-10-19 | 2.9 | 0%
F.E.Z2.F1.LG.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Public Spaces | 0.54 | 2025-09-29 | 2025-10-14 | 2 | 0%
F.E.Z6.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-09-29 | 2025-10-14 | 4.35 | 0%
F.E.Z6.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-09-29 | 2025-10-19 | 1 | 0%
F.E.Z6.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-09-29 | 2025-10-19 | 1.25 | 0%
F.E.Z8.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-09-29 | 2025-10-14 | 3.73 | 0%
F.E.Z6.F2.2F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.75 | 2025-09-29 | 2025-10-19 | 1.1 | 0%
R.E.5B.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-29 | 2025-10-19 | 2.85 | 0%
R.E.5B.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-29 | 2025-10-19 | 2.85 | 0%
R.E.5B.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-09-29 | 2025-10-19 | 3.75 | 0%
R.E.5B.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-09-29 | 2025-10-19 | 3.75 | 0%
R.E.5B.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-09-29 | 2025-10-19 | 3.75 | 0%
R.E.6B.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-29 | 2025-10-19 | 2.3 | 0%
R.E.6B.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-29 | 2025-10-19 | 2.3 | 0%
F.E.Z1.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-09-30 | 2025-10-15 | 1.31 | 0%
R.E.4B.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-09-30 | 2025-10-20 | 1.9 | 0%
R.E.4B.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-09-30 | 2025-10-20 | 1.9 | 0%
R.E.4B.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-09-30 | 2025-10-20 | 3.95 | 0%
R.E.4B.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-09-30 | 2025-10-20 | 3.95 | 0%
R.E.4B.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-09-30 | 2025-10-20 | 3.95 | 0%
F.E.Z3.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-09-30 | 2025-10-15 | 1.5 | 0%
F.E.Z3.AR.RF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-09-30 | 2025-10-15 | 2.27 | 0%
F.E.Z6.F2.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-09-30 | 2025-10-15 | 1.35 | 0%
F.E.Z6.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-09-30 | 2025-10-20 | 1.55 | 0%
F.E.Z8.AR.BF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-09-30 | 2025-10-15 | 0.35 | 0%
F.E.Z8.HV.BF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-09-30 | 2025-10-15 | 0.42 | 0%
F.E.Z8.FF.BF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-09-30 | 2025-10-15 | 0.77 | 0%
F.E.Z1.F1.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.75 | 2025-09-30 | 2025-10-20 | 2.3 | 0%
F.E.Z1.F1.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.75 | 2025-09-30 | 2025-10-20 | 2.3 | 0%
F.E.Z1.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-10-01 | 2025-10-21 | 5.2 | 0%
F.E.Z5.F2.3F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-10-01 | 2025-10-21 | 2.5 | 0%
F.E.Z6.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-10-01 | 2025-10-21 | 1.7 | 0%
F.E.Z1.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-02 | 2025-10-18 | 2.38 | 0%
F.E.Z1.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-10-02 | 2025-10-18 | 2.77 | 0%
F.E.Z1.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-02 | 2025-10-18 | 2.77 | 0%
F.E.Z2.F1.LG.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.75 | 2025-10-02 | 2025-10-22 | 2.15 | 0%
F.E.Z3.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-10-02 | 2025-10-22 | 5.15 | 0%
F.E.Z7.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-10-02 | 2025-10-18 | 4.23 | 0%
F.E.Z7.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-10-02 | 2025-10-22 | 0.85 | 0%
F.E.Z7.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-10-02 | 2025-10-22 | 0.7 | 0%
F.E.Z7.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-10-02 | 2025-10-22 | 1.05 | 0%
F.E.Z8.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-10-02 | 2025-10-18 | 3.69 | 0%
F.E.Z8.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-02 | 2025-10-22 | 0.35 | 0%
F.E.Z8.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-02 | 2025-10-22 | 0.35 | 0%
F.E.Z8.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-02 | 2025-10-22 | 0.35 | 0%
F.E.Z8.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-10-02 | 2025-10-22 | 2.6 | 0%
F.E.Z8.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-10-02 | 2025-10-22 | 5 | 0%
F.E.Z7.F1.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.75 | 2025-10-02 | 2025-10-22 | 0.25 | 0%
F.E.Z8.F1.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For Public Spaces | 0.54 | 2025-10-02 | 2025-10-18 | 0.58 | 0%
R.E.4B.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-10-04 | 2025-10-19 | 3 | 0%
R.E.4B.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-10-04 | 2025-10-19 | 3 | 0%
R.E.4B.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-10-04 | 2025-10-19 | 3 | 0%
F.E.Z8.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-10-04 | 2025-10-19 | 0.35 | 0%
F.E.Z8.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-10-04 | 2025-10-19 | 4.42 | 0%
F.E.Z1.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-05 | 2025-10-20 | 0.54 | 0%
F.E.Z6.AR.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-10-05 | 2025-10-20 | 0.31 | 0%
F.E.Z8.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-10-05 | 2025-10-23 | 1.5 | 0%
F.E.Z6.F2.2F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.75 | 2025-10-05 | 2025-10-23 | 0.9 | 0%
R.E.5B.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-10-05 | 2025-10-20 | 2.69 | 0%
R.E.5B.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-10-05 | 2025-10-20 | 2.69 | 0%
R.E.5B.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-10-05 | 2025-10-20 | 2.69 | 0%
R.E.VL.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-10-05 | 2025-10-23 | 0 | 0%
R.E.VL.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-10-05 | 2025-10-23 | 0 | 0%
R.E.VL.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-10-05 | 2025-10-23 | 0 | 0%
R.E.VL.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-10-05 | 2025-10-23 | 0 | 0%
R.E.SS.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-10-05 | 2025-10-20 | 6.27 | 0%
R.E.SS.HV.GF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-10-05 | 2025-10-20 | 6.27 | 0%
R.E.SS.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.75 | 2025-10-05 | 2025-10-23 | 6.6 | 0%
R.E.SS.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.75 | 2025-10-05 | 2025-10-23 | 6.6 | 0%
R.E.SS.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-10-05 | 2025-10-23 | 6.6 | 0%
R.E.SS.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-10-05 | 2025-10-23 | 6.6 | 0%
F.E.Z7.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-10-06 | 2025-10-21 | 1.88 | 0%
F.E.Z8.AR.1F.RP.002 | Prepare and Submit Shop Drawings For RCP For BOH | 0.54 | 2025-10-06 | 2025-10-21 | 1.27 | 0%
R.E.5B.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-10-06 | 2025-10-21 | 3.12 | 0%
R.E.5B.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-10-06 | 2025-10-21 | 3.12 | 0%
R.E.5B.HV.GF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-10-06 | 2025-10-21 | 3.12 | 0%
F.E.Z1.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-10-07 | 2025-10-27 | 2.05 | 0%
R.E.4B.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-10-07 | 2025-10-22 | 3.38 | 0%
R.E.4B.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-10-07 | 2025-10-22 | 3.38 | 0%
R.E.4B.HV.GF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-10-07 | 2025-10-22 | 3.35 | 0%
F.E.Z2.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-10-07 | 2025-10-22 | 2.38 | 0%
F.E.Z2.F1.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.75 | 2025-10-07 | 2025-10-27 | 1.5 | 0%
F.E.Z3.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-07 | 2025-10-22 | 1.46 | 0%
F.E.Z6.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-10-07 | 2025-10-22 | 5.92 | 0%
F.E.Z6.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-10-07 | 2025-10-22 | 5.38 | 0%
F.E.Z6.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-10-07 | 2025-10-27 | 0.65 | 0%
F.E.Z6.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-10-07 | 2025-10-27 | 5.35 | 0%
F.E.Z7.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-10-07 | 2025-10-27 | 0.9 | 0%
F.E.Z8.EX.GE.PO.002 | Prepare and Submit Shop Drawings For Pools and Water Features | 0.54 | 2025-10-07 | 2025-10-22 | 4.73 | 0%
R.E.6B.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-10-07 | 2025-10-22 | 2.15 | 0%
R.E.6B.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-10-07 | 2025-10-22 | 2.15 | 0%
F.E.Z3.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-10-08 | 2025-10-28 | 0.15 | 0%
F.E.Z5.F2.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-08 | 2025-10-28 | 0.45 | 0%
F.E.Z5.F2.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-08 | 2025-10-28 | 1.25 | 0%
F.E.Z4.F2.LG.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-08 | 2025-10-28 | 1.05 | 0%
F.E.Z4.F2.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-08 | 2025-10-28 | 0.55 | 0%
F.E.Z4.F2.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-08 | 2025-10-28 | 1.35 | 0%
F.E.Z5.F2.LG.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-08 | 2025-10-28 | 1.05 | 0%
R.E.5B.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-08 | 2025-10-28 | 3.1 | 0%
R.E.5B.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-08 | 2025-10-28 | 3.1 | 0%
R.E.5B.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-08 | 2025-10-28 | 3.1 | 0%
R.E.5B.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-10-08 | 2025-10-28 | 4.1 | 0%
R.E.5B.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-10-08 | 2025-10-28 | 4.1 | 0%
R.E.5B.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-10-08 | 2025-10-28 | 4.1 | 0%
F.E.Z1.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-10-09 | 2025-10-25 | 2.77 | 0%
F.E.Z1.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-10-09 | 2025-10-25 | 2.77 | 0%
F.E.Z1.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-10-09 | 2025-10-29 | 6.35 | 0%
R.E.4B.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-09 | 2025-10-29 | 3.45 | 0%
R.E.4B.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-09 | 2025-10-29 | 3.45 | 0%
R.E.4B.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-09 | 2025-10-29 | 3.45 | 0%
F.E.Z2.F1.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Public Spaces | 0.54 | 2025-10-09 | 2025-10-25 | 1.38 | 0%
F.E.Z3.AR.BF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-10-09 | 2025-10-25 | 0.96 | 0%
F.E.Z5.AR.RF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-10-09 | 2025-10-25 | 1.27 | 0%
F.E.Z7.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-10-09 | 2025-10-29 | 5.75 | 0%
F.E.Z8.AR.BF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-10-09 | 2025-10-25 | 0.23 | 0%
R.E.6B.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-10-09 | 2025-10-25 | 3 | 0%
R.E.6B.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-10-09 | 2025-10-25 | 3 | 0%
R.E.6B.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-10-09 | 2025-10-25 | 3 | 0%
F.E.Z1.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-10-12 | 2025-10-30 | 6.85 | 0%
R.E.4B.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-12 | 2025-10-27 | 3.15 | 0%
R.E.4B.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-12 | 2025-10-27 | 3.27 | 0%
F.E.Z3.AR.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-10-12 | 2025-10-27 | 0.15 | 0%
F.E.Z3.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-10-12 | 2025-10-30 | 6.3 | 0%
F.E.Z5.F2.3F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-12 | 2025-10-30 | 1.35 | 0%
F.E.Z7.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-10-12 | 2025-10-27 | 5.77 | 0%
F.E.Z8.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-10-12 | 2025-10-30 | 0.75 | 0%
F.E.Z8.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-10-12 | 2025-10-30 | 1 | 0%
F.E.Z8.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-10-12 | 2025-10-30 | 0.5 | 0%
F.E.Z8.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-10-12 | 2025-10-30 | 0.5 | 0%
F.E.Z8.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-10-12 | 2025-10-30 | 0.6 | 0%
F.E.Z8.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-10-12 | 2025-10-30 | 0.9 | 0%
F.E.Z9.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-10-12 | 2025-10-30 | 4.85 | 0%
F.E.Z4.F2.2F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-12 | 2025-10-30 | 1.35 | 0%
F.E.Z5.F2.2F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-10-12 | 2025-10-30 | 1.35 | 0%
F.E.Z8.F1.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.75 | 2025-10-12 | 2025-10-30 | 0.5 | 0%
R.E.5B.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-12 | 2025-10-27 | 2.77 | 0%
R.E.5B.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-12 | 2025-10-27 | 3.08 | 0%
R.E.VL.ST.1F.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-10-12 | 2025-10-27 | 0 | 0%
R.E.VL.ST.1F.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-10-12 | 2025-10-27 | 0 | 0%
F.E.Z3.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-10-13 | 2025-11-02 | 6.8 | 0%
F.E.Z6.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-10-13 | 2025-11-02 | 0.2 | 0%
F.E.Z6.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-10-13 | 2025-11-02 | 0.6 | 0%
F.E.Z6.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-10-13 | 2025-11-02 | 0.85 | 0%
F.E.Z8.AR.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing For BOH | 0.54 | 2025-10-13 | 2025-10-28 | 0.62 | 0%
F.E.Z8.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-13 | 2025-10-28 | 0.46 | 0%
F.E.Z8.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-13 | 2025-10-28 | 0.81 | 0%
F.E.Z8.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-10-13 | 2025-11-02 | 2.65 | 0%
F.E.Z8.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-10-13 | 2025-11-02 | 2.65 | 0%
F.E.Z8.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-10-13 | 2025-11-02 | 5 | 0%
F.E.Z1.F1.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Public Spaces | 0.54 | 2025-10-13 | 2025-10-28 | 1.81 | 0%
F.E.Z1.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-10-14 | 2025-11-03 | 1.8 | 0%
R.E.4B.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-10-14 | 2025-11-03 | 4.15 | 0%
R.E.4B.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-10-14 | 2025-11-03 | 4.15 | 0%
R.E.4B.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-10-14 | 2025-11-03 | 4.1 | 0%
F.E.Z7.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-10-14 | 2025-11-03 | 4.6 | 0%
F.E.Z7.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-10-14 | 2025-11-03 | 1.75 | 0%
F.E.Z8.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-10-14 | 2025-11-03 | 2.65 | 0%
R.E.SS.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-14 | 2025-11-03 | 6.6 | 0%
R.E.SS.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-14 | 2025-11-03 | 6.6 | 0%
R.E.SS.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-14 | 2025-11-03 | 6.6 | 0%
F.E.Z2.F1.LG.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.75 | 2025-10-15 | 2025-11-04 | 2.15 | 0%
F.E.Z6.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-10-15 | 2025-11-04 | 4.7 | 0%
F.E.Z8.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-10-15 | 2025-11-04 | 4.05 | 0%
F.E.Z1.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-10-16 | 2025-11-05 | 1.4 | 0%
F.E.Z3.AR.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-16 | 2025-11-01 | 0.73 | 0%
F.E.Z3.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-16 | 2025-11-01 | 1.69 | 0%
F.E.Z3.LV.2F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-16 | 2025-11-01 | 1.69 | 0%
F.E.Z3.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-10-16 | 2025-11-05 | 1.6 | 0%
F.E.Z3.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-10-16 | 2025-11-05 | 2.45 | 0%
F.E.Z6.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-10-16 | 2025-11-01 | 0.58 | 0%
F.E.Z6.F2.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-10-16 | 2025-11-01 | 0 | 0%
F.E.Z6.F2.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-10-16 | 2025-11-05 | 1.45 | 0%
F.E.Z8.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-10-16 | 2025-11-05 | 0.35 | 0%
F.E.Z8.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-10-16 | 2025-11-05 | 0.45 | 0%
F.E.Z8.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-10-16 | 2025-11-05 | 0.8 | 0%
F.E.Z4.F2.LG.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-16 | 2025-11-01 | 0.81 | 0%
F.E.Z5.F2.LG.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-16 | 2025-11-01 | 0.81 | 0%
R.E.5B.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-10-16 | 2025-11-01 | 3 | 0%
R.E.5B.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-10-16 | 2025-11-01 | 3 | 0%
R.E.5B.HV.RF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-10-16 | 2025-11-01 | 3 | 0%
R.E.5B.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-16 | 2025-11-01 | 2.88 | 0%
R.E.SS.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-16 | 2025-11-01 | 6.08 | 0%
F.E.Z1.AR.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-10-18 | 2025-11-02 | 1.65 | 0%
R.E.4B.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-10-18 | 2025-11-02 | 3.19 | 0%
R.E.4B.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-10-18 | 2025-11-02 | 3.19 | 0%
R.E.4B.HV.RF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-10-18 | 2025-11-02 | 3.12 | 0%
R.E.4B.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-18 | 2025-11-02 | 3.08 | 0%
F.E.Z5.F2.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-18 | 2025-11-02 | 0.31 | 0%
F.E.Z8.AR.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes For BOH | 0.54 | 2025-10-18 | 2025-11-02 | 0.46 | 0%
F.E.Z4.F2.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-18 | 2025-11-02 | 0.42 | 0%
F.E.Z1.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-10-19 | 2025-11-06 | 2.6 | 0%
F.E.Z1.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-10-19 | 2025-11-06 | 3 | 0%
F.E.Z1.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-10-19 | 2025-11-06 | 3 | 0%
F.E.Z7.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-10-19 | 2025-11-06 | 4.6 | 0%
F.E.Z8.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-10-19 | 2025-11-06 | 4 | 0%
F.E.Z8.F1.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.75 | 2025-10-19 | 2025-11-06 | 0.65 | 0%
F.E.Z6.F2.2F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.54 | 2025-10-19 | 2025-11-04 | 1.65 | 0%
R.E.4B.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-20 | 2025-11-09 | 3.25 | 0%
R.E.4B.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-20 | 2025-11-09 | 3.25 | 0%
R.E.4B.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-20 | 2025-11-09 | 3.25 | 0%
F.E.Z5.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-20 | 2025-11-04 | 0.19 | 0%
F.E.Z8.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-10-20 | 2025-11-09 | 0.4 | 0%
F.E.Z8.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-10-20 | 2025-11-09 | 4.8 | 0%
F.E.Z7.F1.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Public Spaces | 0.54 | 2025-10-20 | 2025-11-04 | 0.92 | 0%
R.E.SS.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-10-20 | 2025-11-04 | 6.08 | 0%
F.E.Z1.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-10-21 | 2025-11-10 | 0.6 | 0%
F.E.Z2.EL.LG.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-10-21 | 2025-11-05 | 2 | 0%
F.E.Z6.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-10-21 | 2025-11-10 | 0.35 | 0%
R.E.5B.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-21 | 2025-11-10 | 2.9 | 0%
R.E.5B.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-21 | 2025-11-10 | 2.9 | 0%
R.E.5B.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-21 | 2025-11-10 | 2.9 | 0%
R.E.SS.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-10-21 | 2025-11-10 | 6.8 | 0%
R.E.SS.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-10-21 | 2025-11-10 | 6.8 | 0%
F.E.Z7.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-10-22 | 2025-11-11 | 2.05 | 0%
F.E.Z8.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.75 | 2025-10-22 | 2025-11-11 | 1.35 | 0%
R.E.5B.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-10-22 | 2025-11-11 | 3.35 | 0%
R.E.5B.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-10-22 | 2025-11-11 | 3.35 | 0%
R.E.5B.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-10-22 | 2025-11-11 | 3.35 | 0%
R.E.4B.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-10-23 | 2025-11-12 | 3.65 | 0%
R.E.4B.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-10-23 | 2025-11-12 | 3.65 | 0%
R.E.4B.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-10-23 | 2025-11-12 | 3.6 | 0%
F.E.Z2.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-10-23 | 2025-11-12 | 2.55 | 0%
F.E.Z3.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-10-23 | 2025-11-12 | 1.55 | 0%
F.E.Z5.F2.3F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-23 | 2025-11-08 | 1.04 | 0%
F.E.Z6.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-10-23 | 2025-11-12 | 6.4 | 0%
F.E.Z6.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-10-23 | 2025-11-12 | 5.85 | 0%
F.E.Z8.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.75 | 2025-10-23 | 2025-11-12 | 5.1 | 0%
F.E.Z9.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-10-23 | 2025-11-08 | 2 | 0%
F.E.Z4.F2.2F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-23 | 2025-11-08 | 1.04 | 0%
F.E.Z5.F2.2F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-10-23 | 2025-11-08 | 1.04 | 0%
R.E.5B.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-23 | 2025-11-08 | 6.46 | 0%
R.E.6B.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-10-23 | 2025-11-08 | 2.19 | 0%
R.E.6B.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-10-23 | 2025-11-08 | 2.19 | 0%
R.E.6B.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-10-23 | 2025-11-08 | 2.19 | 0%
R.E.6B.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-10-23 | 2025-11-12 | 2.3 | 0%
R.E.6B.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-10-23 | 2025-11-12 | 2.3 | 0%
R.E.SS.AR.GF.RP.002 | Prepare and Submit Shop Drawings For Ceiling | 0.54 | 2025-10-23 | 2025-11-08 | 6.88 | 0%
F.E.Z3.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-10-25 | 2025-11-09 | 1.69 | 0%
F.E.Z3.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-10-25 | 2025-11-09 | 1.69 | 0%
F.E.Z3.LV.2F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-10-25 | 2025-11-09 | 1.69 | 0%
F.E.Z3.LV.2F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-10-25 | 2025-11-09 | 1.69 | 0%
F.E.Z7.AR.BF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-10-25 | 2025-11-09 | 0.81 | 0%
F.E.Z7.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-10-25 | 2025-11-09 | 2.04 | 0%
F.E.Z7.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-25 | 2025-11-09 | 2.04 | 0%
R.E.5B.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-10-25 | 2025-11-09 | 3.77 | 0%
F.E.Z1.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-10-26 | 2025-11-10 | 0.54 | 0%
F.E.Z1.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-10-26 | 2025-11-13 | 3 | 0%
F.E.Z1.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-10-26 | 2025-11-13 | 3 | 0%
R.E.4B.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-26 | 2025-11-10 | 6.5 | 0%
F.E.Z2.F1.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.75 | 2025-10-26 | 2025-11-13 | 1.5 | 0%
F.E.Z3.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-10-26 | 2025-11-13 | 1.05 | 0%
F.E.Z5.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-10-26 | 2025-11-13 | 1.4 | 0%
F.E.Z7.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-26 | 2025-11-10 | 1.62 | 0%
F.E.Z8.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-10-26 | 2025-11-13 | 0.25 | 0%
F.E.Z7.F1.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Public Spaces | 0.54 | 2025-10-26 | 2025-11-10 | 0.15 | 0%
R.E.6B.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-10-26 | 2025-11-10 | 3.04 | 0%
R.E.6B.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-10-26 | 2025-11-10 | 3.04 | 0%
R.E.6B.HV.1F.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-10-26 | 2025-11-10 | 3 | 0%
R.E.6B.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-10-26 | 2025-11-10 | 2.92 | 0%
R.E.6B.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-10-26 | 2025-11-13 | 3.25 | 0%
R.E.6B.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-10-26 | 2025-11-13 | 3.25 | 0%
R.E.6B.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-10-26 | 2025-11-13 | 3.25 | 0%
R.E.4B.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-10-27 | 2025-11-11 | 3.88 | 0%
R.E.4B.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-27 | 2025-11-11 | 3.23 | 0%
R.E.4B.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-27 | 2025-11-11 | 3.23 | 0%
R.E.4B.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-27 | 2025-11-11 | 3.46 | 0%
R.E.4B.AR.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-27 | 2025-11-11 | 3.46 | 0%
R.E.4B.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-27 | 2025-11-11 | 3.46 | 0%
R.E.4B.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-27 | 2025-11-11 | 3.65 | 0%
F.E.Z3.AR.RF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-10-27 | 2025-11-11 | 1.5 | 0%
F.E.Z4.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-27 | 2025-11-11 | 1.73 | 0%
F.E.Z8.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-10-27 | 2025-11-11 | 3.77 | 0%
R.E.5B.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-27 | 2025-11-11 | 2.96 | 0%
R.E.5B.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-27 | 2025-11-11 | 2.96 | 0%
R.E.5B.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-27 | 2025-11-11 | 3.08 | 0%
R.E.5B.AR.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-27 | 2025-11-11 | 3.19 | 0%
R.E.5B.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-27 | 2025-11-11 | 3.19 | 0%
R.E.5B.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-27 | 2025-11-11 | 3.38 | 0%
F.E.Z1.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-10-28 | 2025-11-12 | 2.42 | 0%
R.E.4B.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-10-28 | 2025-11-17 | 3.4 | 0%
R.E.4B.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-10-28 | 2025-11-17 | 3.55 | 0%
F.E.Z3.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-10-28 | 2025-11-17 | 0.15 | 0%
F.E.Z7.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-10-28 | 2025-11-17 | 6.25 | 0%
R.E.5B.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-10-28 | 2025-11-17 | 3 | 0%
R.E.5B.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-10-28 | 2025-11-17 | 3.35 | 0%
R.E.VL.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-10-28 | 2025-11-17 | 0 | 0%
R.E.VL.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-10-28 | 2025-11-17 | 0 | 0%
F.E.Z8.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.75 | 2025-10-29 | 2025-11-18 | 0.65 | 0%
F.E.Z8.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-10-29 | 2025-11-18 | 0.5 | 0%
F.E.Z8.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-10-29 | 2025-11-18 | 0.85 | 0%
F.E.Z1.F1.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.75 | 2025-10-29 | 2025-11-18 | 1.95 | 0%
F.E.Z1.EL.BF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-10-30 | 2025-11-15 | 1.62 | 0%
F.E.Z2.LV.LG.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-10-30 | 2025-11-15 | 2 | 0%
F.E.Z2.LV.LG.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-30 | 2025-11-15 | 2 | 0%
F.E.Z2.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-10-30 | 2025-11-15 | 2 | 0%
F.E.Z2.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-30 | 2025-11-15 | 2 | 0%
F.E.Z4.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-30 | 2025-11-15 | 1.85 | 0%
F.E.Z5.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-10-30 | 2025-11-15 | 1.85 | 0%
F.E.Z7.AR.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-10-30 | 2025-11-15 | 0.62 | 0%
F.E.Z6.F2.2F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Guest Rooms | 0.54 | 2025-10-30 | 2025-11-15 | 0.69 | 0%
R.E.5B.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2025-10-30 | 2025-11-15 | 4.5 | 0%
R.E.5B.AR.RF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-10-30 | 2025-11-15 | 3.04 | 0%
R.E.5B.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-30 | 2025-11-15 | 3.04 | 0%
R.E.5B.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-30 | 2025-11-15 | 3.23 | 0%
R.E.SS.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-10-30 | 2025-11-15 | 6 | 0%
R.E.SS.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-10-30 | 2025-11-15 | 6.46 | 0%
F.E.Z3.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-01 | 2025-11-16 | 1.46 | 0%
F.E.Z8.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-11-01 | 2025-11-16 | 3.5 | 0%
R.E.4B.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2025-11-02 | 2025-11-17 | 4.42 | 0%
R.E.4B.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-02 | 2025-11-17 | 3.27 | 0%
R.E.4B.AR.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-02 | 2025-11-17 | 3.46 | 0%
R.E.4B.AR.RF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-11-02 | 2025-11-17 | 3.27 | 0%
R.E.4B.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-11-02 | 2025-11-17 | 3.27 | 0%
R.E.4B.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-11-02 | 2025-11-17 | 3.46 | 0%
F.E.Z2.EL.BF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-02 | 2025-11-17 | 1.38 | 0%
F.E.Z3.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-11-02 | 2025-11-20 | 0.8 | 0%
F.E.Z3.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-02 | 2025-11-20 | 1.85 | 0%
F.E.Z3.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-02 | 2025-11-20 | 1.85 | 0%
F.E.Z4.LV.2F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-02 | 2025-11-17 | 1.54 | 0%
F.E.Z5.LV.2F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-02 | 2025-11-17 | 1.54 | 0%
F.E.Z5.LV.3F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-02 | 2025-11-17 | 1.54 | 0%
F.E.Z6.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-11-02 | 2025-11-20 | 0.65 | 0%
F.E.Z6.F2.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-11-02 | 2025-11-20 | 0 | 0%
F.E.Z7.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-02 | 2025-11-17 | 2.04 | 0%
F.E.Z7.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-02 | 2025-11-17 | 2.04 | 0%
F.E.Z4.F2.LG.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-02 | 2025-11-20 | 0.9 | 0%
F.E.Z5.F2.LG.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-02 | 2025-11-20 | 0.9 | 0%
R.E.5B.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-02 | 2025-11-17 | 2.88 | 0%
R.E.5B.AR.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-02 | 2025-11-17 | 3.19 | 0%
R.E.5B.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-11-02 | 2025-11-20 | 3.25 | 0%
R.E.5B.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-11-02 | 2025-11-20 | 3.25 | 0%
R.E.5B.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-11-02 | 2025-11-20 | 3.25 | 0%
R.E.5B.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-11-02 | 2025-11-20 | 3.15 | 0%
R.E.SS.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-11-02 | 2025-11-20 | 6.6 | 0%
F.E.Z1.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-11-03 | 2025-11-23 | 1.8 | 0%
R.E.GE.EX.GE.DR.002 | Prepare and Submit Shop Drawings For Drainage Network | 0.54 | 2025-11-03 | 2025-11-18 | 0.85 | 0%
R.E.GE.EX.GE.SW.002 | Prepare and Submit Shop Drawings For Storm Water Network | 0.54 | 2025-11-03 | 2025-11-18 | 2.69 | 0%
R.E.4B.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-11-03 | 2025-11-23 | 3.45 | 0%
R.E.4B.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-11-03 | 2025-11-23 | 3.45 | 0%
R.E.4B.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-11-03 | 2025-11-23 | 3.4 | 0%
R.E.4B.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-11-03 | 2025-11-23 | 3.35 | 0%
F.E.Z5.F2.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-03 | 2025-11-23 | 0.35 | 0%
F.E.Z8.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.75 | 2025-11-03 | 2025-11-23 | 0.5 | 0%
F.E.Z4.F2.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-03 | 2025-11-23 | 0.45 | 0%
R.E.6B.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-11-03 | 2025-11-18 | 2.19 | 0%
R.E.6B.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-11-03 | 2025-11-18 | 2.19 | 0%
R.E.6B.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-11-03 | 2025-11-18 | 2.19 | 0%
F.E.Z3.AR.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-11-04 | 2025-11-19 | 0.77 | 0%
F.E.Z4.EL.LG.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-04 | 2025-11-19 | 0.81 | 0%
F.E.Z4.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-04 | 2025-11-19 | 1.69 | 0%
F.E.Z4.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-04 | 2025-11-19 | 1.69 | 0%
F.E.Z5.EL.LG.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-04 | 2025-11-19 | 0.81 | 0%
F.E.Z9.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-04 | 2025-11-19 | 2 | 0%
F.E.Z6.F2.2F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.75 | 2025-11-04 | 2025-11-25 | 1.8 | 0%
F.E.Z5.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-11-05 | 2025-11-25 | 0.2 | 0%
F.E.Z7.F1.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.75 | 2025-11-05 | 2025-11-25 | 1 | 0%
R.E.SS.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-11-05 | 2025-11-25 | 6.6 | 0%
F.E.Z2.LV.LG.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-06 | 2025-11-22 | 2.08 | 0%
F.E.Z2.LV.LG.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-06 | 2025-11-22 | 2.08 | 0%
F.E.Z2.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-06 | 2025-11-22 | 2.08 | 0%
F.E.Z2.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-06 | 2025-11-22 | 2.08 | 0%
F.E.Z2.EL.LG.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-06 | 2025-11-26 | 2.15 | 0%
F.E.Z4.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-06 | 2025-11-22 | 1.88 | 0%
F.E.Z4.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-06 | 2025-11-22 | 1.88 | 0%
F.E.Z5.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-06 | 2025-11-22 | 1.88 | 0%
F.E.Z5.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-06 | 2025-11-22 | 1.88 | 0%
R.E.5B.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-06 | 2025-11-22 | 3 | 0%
R.E.VL.ST.RF.GA.002 | Prepare and Submit Shop Drawings For Slab & beams General arrangement | 0.54 | 2025-11-06 | 2025-11-22 | 0 | 0%
R.E.VL.ST.RF.SR.002 | Prepare and Submit Shop Drawings For Slab & Beams Steel Reinforcement | 0.54 | 2025-11-06 | 2025-11-22 | 0 | 0%
R.E.VL.AR.1F.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-11-06 | 2025-11-22 | 2.15 | 0%
R.E.VL.AR.1F.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-11-06 | 2025-11-22 | 2.15 | 0%
R.E.VL.AR.1F.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-11-06 | 2025-11-22 | 2.15 | 0%
R.E.SS.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-06 | 2025-11-22 | 6.19 | 0%
R.E.SS.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-11-06 | 2025-11-22 | 8.65 | 0%
R.E.4B.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-08 | 2025-11-23 | 3.31 | 0%
R.E.4B.AR.1F.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-08 | 2025-11-23 | 3.5 | 0%
R.E.4B.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-08 | 2025-11-23 | 3.27 | 0%
R.E.5B.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-08 | 2025-11-23 | 2.96 | 0%
R.E.5B.AR.1F.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-08 | 2025-11-23 | 3.27 | 0%
F.E.Z3.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-09 | 2025-11-24 | 1.46 | 0%
F.E.Z3.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-09 | 2025-11-24 | 1.46 | 0%
F.E.Z5.F2.3F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-09 | 2025-11-27 | 1.15 | 0%
F.E.Z9.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-09 | 2025-11-27 | 2.2 | 0%
F.E.Z4.F2.2F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-09 | 2025-11-27 | 1.15 | 0%
F.E.Z5.F2.2F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-09 | 2025-11-27 | 1.15 | 0%
F.E.Z8.F1.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For Public Spaces | 0.54 | 2025-11-09 | 2025-11-24 | 2.27 | 0%
R.E.5B.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-09 | 2025-11-27 | 7 | 0%
R.E.6B.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-11-09 | 2025-11-24 | 2.31 | 0%
R.E.6B.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-11-09 | 2025-11-24 | 2.31 | 0%
R.E.6B.HV.GF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-11-09 | 2025-11-24 | 2.27 | 0%
R.E.6B.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-11-09 | 2025-11-24 | 2.23 | 0%
R.E.6B.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-11-09 | 2025-11-27 | 2.4 | 0%
R.E.6B.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-11-09 | 2025-11-27 | 2.4 | 0%
R.E.6B.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-11-09 | 2025-11-27 | 2.4 | 0%
R.E.SS.AR.GF.RP.004 | Review and Approve Shop Drawings For Ceiling | 0.75 | 2025-11-09 | 2025-11-27 | 7.45 | 0%
F.E.Z3.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-10 | 2025-11-25 | 0.15 | 0%
F.E.Z3.EL.2F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-10 | 2025-11-25 | 2 | 0%
F.E.Z3.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-10 | 2025-11-30 | 1.85 | 0%
F.E.Z3.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-10 | 2025-11-30 | 1.85 | 0%
F.E.Z3.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-10 | 2025-11-30 | 1.85 | 0%
F.E.Z3.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-10 | 2025-11-30 | 1.85 | 0%
F.E.Z4.LV.2F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-10 | 2025-11-25 | 1.5 | 0%
F.E.Z4.LV.2F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-10 | 2025-11-25 | 1.5 | 0%
F.E.Z5.LV.2F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-10 | 2025-11-25 | 1.5 | 0%
F.E.Z5.LV.2F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-10 | 2025-11-25 | 1.5 | 0%
F.E.Z5.LV.3F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-10 | 2025-11-25 | 1.5 | 0%
F.E.Z5.LV.3F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-10 | 2025-11-25 | 1.5 | 0%
F.E.Z7.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-11-10 | 2025-11-30 | 0.9 | 0%
F.E.Z7.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-11-10 | 2025-11-30 | 2.2 | 0%
F.E.Z7.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-10 | 2025-11-30 | 2.2 | 0%
F.E.Z8.AR.BF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-11-10 | 2025-11-25 | 0.42 | 0%
F.E.Z9.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-10 | 2025-11-25 | 2.04 | 0%
F.E.Z9.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-10 | 2025-11-25 | 2.04 | 0%
R.E.5B.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-11-10 | 2025-11-30 | 4.1 | 0%
F.E.Z1.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-11-11 | 2025-12-01 | 0.6 | 0%
R.E.4B.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-11 | 2025-12-01 | 7.05 | 0%
F.E.Z5.AR.RF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-11-11 | 2025-11-26 | 0.19 | 0%
F.E.Z6.F2.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-11-11 | 2025-11-26 | 0 | 0%
F.E.Z7.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-11-11 | 2025-12-01 | 1.75 | 0%
F.E.Z7.F1.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.75 | 2025-11-11 | 2025-12-01 | 0.15 | 0%
R.E.5B.AR.RF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-11 | 2025-11-26 | 3.12 | 0%
R.E.6B.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-11-11 | 2025-12-01 | 3.3 | 0%
R.E.6B.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-11-11 | 2025-12-01 | 3.3 | 0%
R.E.6B.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-11-11 | 2025-12-01 | 3.25 | 0%
R.E.6B.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-11-11 | 2025-12-01 | 3.15 | 0%
R.E.4B.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-11-12 | 2025-12-02 | 4.2 | 0%
R.E.4B.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-12 | 2025-12-02 | 3.55 | 0%
R.E.4B.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-12 | 2025-12-02 | 3.55 | 0%
R.E.4B.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-12 | 2025-12-02 | 3.75 | 0%
R.E.4B.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-12 | 2025-12-02 | 3.75 | 0%
R.E.4B.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-12 | 2025-12-02 | 3.75 | 0%
R.E.4B.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-12 | 2025-12-02 | 3.95 | 0%
F.E.Z3.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-11-12 | 2025-12-02 | 1.6 | 0%
F.E.Z4.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-12 | 2025-12-02 | 1.85 | 0%
F.E.Z8.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2025-11-12 | 2025-12-02 | 4.05 | 0%
R.E.5B.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-12 | 2025-12-02 | 3.2 | 0%
R.E.5B.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-12 | 2025-12-02 | 3.2 | 0%
R.E.5B.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-12 | 2025-12-02 | 3.35 | 0%
R.E.5B.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-12 | 2025-12-02 | 3.5 | 0%
R.E.5B.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-12 | 2025-12-02 | 3.5 | 0%
R.E.5B.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-12 | 2025-12-02 | 3.65 | 0%
F.E.Z1.LV.BF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-13 | 2025-11-29 | 1.62 | 0%
F.E.Z1.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-13 | 2025-12-03 | 2.6 | 0%
R.E.4B.AR.RF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-13 | 2025-11-29 | 3.31 | 0%
F.E.Z2.LV.BF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-13 | 2025-11-29 | 1.38 | 0%
F.E.Z2.LV.BF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-13 | 2025-11-29 | 1.38 | 0%
F.E.Z6.AR.BF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-11-13 | 2025-11-29 | 0.38 | 0%
F.E.Z8.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-11-13 | 2025-11-29 | 4.15 | 0%
F.E.Z8.F1.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For Public Spaces | 0.54 | 2025-11-13 | 2025-11-29 | 0.5 | 0%
R.E.6B.AR.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-11-13 | 2025-11-29 | 3.04 | 0%
R.E.6B.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-11-13 | 2025-11-29 | 3.04 | 0%
R.E.6B.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-11-13 | 2025-11-29 | 3.19 | 0%
R.E.SS.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2025-11-13 | 2025-11-29 | 6.19 | 0%
R.E.SS.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-11-13 | 2025-11-29 | 8.88 | 0%
F.E.Z4.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-15 | 2025-11-30 | 1.92 | 0%
F.E.Z5.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-15 | 2025-11-30 | 1.92 | 0%
F.E.Z1.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-16 | 2025-12-04 | 1.75 | 0%
R.E.GE.EX.GE.PW.002 | Prepare and Submit Shop Drawings For Potable Water Network | 0.54 | 2025-11-16 | 2025-12-01 | 1.65 | 0%
R.E.GE.EX.GE.FF.002 | Prepare and Submit Shop Drawings For Fire Fighting Network | 0.54 | 2025-11-16 | 2025-12-01 | 1.65 | 0%
R.E.GE.EX.GE.IR.002 | Prepare and Submit Shop Drawings For Irrigation Network | 0.54 | 2025-11-16 | 2025-12-01 | 4.46 | 0%
F.E.Z2.LV.LG.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-11-16 | 2025-12-04 | 2.2 | 0%
F.E.Z2.LV.LG.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-16 | 2025-12-04 | 2.2 | 0%
F.E.Z2.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-11-16 | 2025-12-04 | 2.2 | 0%
F.E.Z2.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-16 | 2025-12-04 | 2.2 | 0%
F.E.Z3.EL.BF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-16 | 2025-12-01 | 0.77 | 0%
F.E.Z4.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-16 | 2025-12-04 | 2 | 0%
F.E.Z5.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-16 | 2025-12-04 | 2 | 0%
F.E.Z7.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-11-16 | 2025-12-04 | 0.7 | 0%
F.E.Z8.AR.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-11-16 | 2025-12-01 | 0.38 | 0%
F.E.Z6.F2.2F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.75 | 2025-11-16 | 2025-12-04 | 0.75 | 0%
F.E.Z7.F1.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Public Spaces | 0.54 | 2025-11-16 | 2025-12-01 | 0.15 | 0%
R.E.5B.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2025-11-16 | 2025-12-04 | 4.9 | 0%
R.E.5B.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-16 | 2025-12-04 | 3.35 | 0%
R.E.5B.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-16 | 2025-12-04 | 3.35 | 0%
R.E.5B.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-16 | 2025-12-04 | 3.5 | 0%
R.E.SS.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-16 | 2025-12-04 | 6.55 | 0%
R.E.SS.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-16 | 2025-12-04 | 7 | 0%
F.E.Z3.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-17 | 2025-12-07 | 1.6 | 0%
F.E.Z6.AR.BF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-11-17 | 2025-12-02 | 0.15 | 0%
F.E.Z8.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-11-17 | 2025-12-02 | 4.58 | 0%
F.E.Z8.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2025-11-17 | 2025-12-07 | 3.8 | 0%
R.E.GE.EX.GE.ED.002 | Prepare and Submit Shop Drawings For Electricity Distribution Network | 0.54 | 2025-11-18 | 2025-12-03 | 2.08 | 0%
R.E.4B.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2025-11-18 | 2025-12-08 | 4.8 | 0%
R.E.4B.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-18 | 2025-12-08 | 3.55 | 0%
R.E.4B.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-18 | 2025-12-08 | 3.75 | 0%
R.E.4B.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-18 | 2025-12-08 | 3.55 | 0%
R.E.4B.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-18 | 2025-12-08 | 3.55 | 0%
R.E.4B.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-18 | 2025-12-08 | 3.75 | 0%
F.E.Z2.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-18 | 2025-12-08 | 1.5 | 0%
F.E.Z4.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-18 | 2025-12-08 | 1.65 | 0%
F.E.Z5.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-18 | 2025-12-08 | 1.65 | 0%
F.E.Z5.LV.3F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-18 | 2025-12-08 | 1.65 | 0%
F.E.Z7.AR.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-11-18 | 2025-12-03 | 0.65 | 0%
F.E.Z7.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-18 | 2025-12-08 | 2.2 | 0%
F.E.Z7.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-18 | 2025-12-08 | 2.2 | 0%
F.E.Z6.F2.2F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.54 | 2025-11-18 | 2025-12-03 | 0.77 | 0%
R.E.5B.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-18 | 2025-12-08 | 3.15 | 0%
R.E.5B.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-18 | 2025-12-08 | 3.45 | 0%
R.E.6B.AR.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-11-18 | 2025-12-03 | 3.04 | 0%
R.E.SS.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-11-18 | 2025-12-03 | 6.96 | 0%
R.E.SS.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2025-11-18 | 2025-12-03 | 6.96 | 0%
R.E.GE.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.75 | 2025-11-19 | 2025-12-09 | 0.9 | 0%
R.E.GE.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.75 | 2025-11-19 | 2025-12-09 | 2.9 | 0%
R.E.6B.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-11-19 | 2025-12-09 | 2.35 | 0%
R.E.6B.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-11-19 | 2025-12-09 | 2.35 | 0%
R.E.6B.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-11-19 | 2025-12-09 | 2.35 | 0%
F.E.Z1.LV.BF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-20 | 2025-12-06 | 1.69 | 0%
F.E.Z1.LV.BF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-20 | 2025-12-06 | 1.69 | 0%
R.E.GE.EX.GE.LV.002 | Prepare and Submit Shop Drawings For ELV Network | 0.54 | 2025-11-20 | 2025-12-06 | 2.12 | 0%
F.E.Z3.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-11-20 | 2025-12-10 | 0.8 | 0%
F.E.Z4.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-20 | 2025-12-06 | 1.73 | 0%
F.E.Z4.EL.LG.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-20 | 2025-12-10 | 0.85 | 0%
F.E.Z4.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-20 | 2025-12-10 | 1.8 | 0%
F.E.Z4.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-20 | 2025-12-10 | 1.8 | 0%
F.E.Z5.EL.LG.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-20 | 2025-12-10 | 0.85 | 0%
F.E.Z7.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-20 | 2025-12-06 | 1.65 | 0%
F.E.Z8.AR.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details For BOH | 0.54 | 2025-11-20 | 2025-12-06 | 0.62 | 0%
F.E.Z9.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-20 | 2025-12-10 | 2.15 | 0%
R.E.6B.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-11-20 | 2025-12-06 | 2.23 | 0%
R.E.6B.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-11-20 | 2025-12-06 | 2.23 | 0%
R.E.6B.HV.RF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-11-20 | 2025-12-06 | 2.19 | 0%
R.E.6B.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-11-20 | 2025-12-06 | 2.12 | 0%
F.E.Z2.LV.BF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-22 | 2025-12-07 | 1.38 | 0%
F.E.Z2.LV.BF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-22 | 2025-12-07 | 1.38 | 0%
F.E.Z5.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-22 | 2025-12-07 | 0.88 | 0%
R.E.VL.AR.GF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-11-22 | 2025-12-07 | 1.65 | 0%
R.E.VL.AR.GF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-11-22 | 2025-12-07 | 1.65 | 0%
R.E.VL.AR.GF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-11-22 | 2025-12-07 | 1.65 | 0%
R.E.VL.PL.1F.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-11-22 | 2025-12-07 | 2.23 | 0%
R.E.VL.DR.1F.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-11-22 | 2025-12-07 | 2.23 | 0%
R.E.VL.HV.1F.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-11-22 | 2025-12-07 | 2.19 | 0%
R.E.VL.EL.1F.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-11-22 | 2025-12-07 | 2.15 | 0%
R.E.GE.EX.GE.EX.002 | Prepare and Submit Shop Drawings For External Lighting | 0.54 | 2025-11-23 | 2025-12-08 | 3.23 | 0%
F.E.Z2.LV.LG.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-23 | 2025-12-11 | 2.25 | 0%
F.E.Z2.LV.LG.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-23 | 2025-12-11 | 2.25 | 0%
F.E.Z2.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-23 | 2025-12-11 | 2.25 | 0%
F.E.Z2.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-23 | 2025-12-11 | 2.25 | 0%
F.E.Z4.LV.LG.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-23 | 2025-12-08 | 0.85 | 0%
F.E.Z4.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-23 | 2025-12-11 | 2.05 | 0%
F.E.Z4.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-23 | 2025-12-11 | 2.05 | 0%
F.E.Z5.LV.LG.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-23 | 2025-12-08 | 0.85 | 0%
F.E.Z5.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-23 | 2025-12-11 | 2.05 | 0%
F.E.Z5.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-23 | 2025-12-11 | 2.05 | 0%
F.E.Z6.LV.2F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-23 | 2025-12-08 | 1.12 | 0%
F.E.Z6.LV.2F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-23 | 2025-12-08 | 1.12 | 0%
R.E.5B.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-23 | 2025-12-11 | 3.25 | 0%
R.E.VL.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.75 | 2025-11-23 | 2025-12-11 | 0 | 0%
R.E.VL.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.75 | 2025-11-23 | 2025-12-11 | 0 | 0%
R.E.VL.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-11-23 | 2025-12-11 | 2.35 | 0%
R.E.VL.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-11-23 | 2025-12-11 | 2.35 | 0%
R.E.VL.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-11-23 | 2025-12-11 | 2.35 | 0%
R.E.SS.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-23 | 2025-12-11 | 6.7 | 0%
R.E.SS.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-23 | 2025-12-11 | 9.4 | 0%
R.E.4B.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-11-24 | 2025-12-14 | 3.6 | 0%
R.E.4B.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-11-24 | 2025-12-14 | 3.8 | 0%
R.E.4B.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-11-24 | 2025-12-14 | 3.55 | 0%
F.E.Z3.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-24 | 2025-12-09 | 0.15 | 0%
R.E.5B.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-11-24 | 2025-12-14 | 3.2 | 0%
R.E.5B.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-11-24 | 2025-12-14 | 3.55 | 0%
R.E.6B.AR.1F.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-11-24 | 2025-12-09 | 3.08 | 0%
F.E.Z3.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-25 | 2025-12-10 | 1.5 | 0%
F.E.Z3.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-25 | 2025-12-15 | 1.6 | 0%
F.E.Z3.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-25 | 2025-12-15 | 1.6 | 0%
F.E.Z8.F1.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.75 | 2025-11-25 | 2025-12-15 | 2.45 | 0%
R.E.6B.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-11-25 | 2025-12-15 | 2.5 | 0%
R.E.6B.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-11-25 | 2025-12-15 | 2.5 | 0%
R.E.6B.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-11-25 | 2025-12-15 | 2.45 | 0%
R.E.6B.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-11-25 | 2025-12-15 | 2.4 | 0%
F.E.Z3.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-26 | 2025-12-16 | 0.15 | 0%
F.E.Z3.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-11-26 | 2025-12-16 | 2.15 | 0%
F.E.Z4.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-26 | 2025-12-16 | 1.6 | 0%
F.E.Z4.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-26 | 2025-12-16 | 1.6 | 0%
F.E.Z5.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-26 | 2025-12-16 | 1.6 | 0%
F.E.Z5.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-26 | 2025-12-16 | 1.6 | 0%
F.E.Z5.LV.3F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-26 | 2025-12-16 | 1.6 | 0%
F.E.Z5.LV.3F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-26 | 2025-12-16 | 1.6 | 0%
F.E.Z8.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-11-26 | 2025-12-16 | 0.45 | 0%
F.E.Z9.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-11-26 | 2025-12-16 | 2.2 | 0%
F.E.Z9.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-11-26 | 2025-12-16 | 2.2 | 0%
F.E.Z4.LV.2F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-27 | 2025-12-13 | 1.5 | 0%
F.E.Z5.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-27 | 2025-12-13 | 0.31 | 0%
F.E.Z5.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-27 | 2025-12-13 | 0.31 | 0%
F.E.Z5.LV.2F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-27 | 2025-12-13 | 1.5 | 0%
F.E.Z5.LV.3F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-27 | 2025-12-13 | 1.5 | 0%
F.E.Z5.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-11-27 | 2025-12-17 | 0.2 | 0%
F.E.Z6.F2.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-11-27 | 2025-12-17 | 0 | 0%
R.E.5B.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-11-27 | 2025-12-17 | 3.35 | 0%
R.E.6B.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-11-27 | 2025-12-13 | 2.19 | 0%
R.E.6B.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-11-27 | 2025-12-13 | 2.19 | 0%
R.E.6B.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-11-27 | 2025-12-13 | 2.42 | 0%
R.E.6B.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-11-27 | 2025-12-13 | 5.5 | 0%
R.E.VL.AR.RF.BW.002 | Prepare and Submit Shop Drawings For Blockwork | 0.54 | 2025-11-27 | 2025-12-13 | 1.42 | 0%
R.E.VL.AR.RF.CP.002 | Prepare and Submit Shop Drawings For Coordination Plan | 0.54 | 2025-11-27 | 2025-12-13 | 1.42 | 0%
R.E.VL.AR.RF.BU.002 | Prepare and Submit Shop Drawings For Builders Works | 0.54 | 2025-11-27 | 2025-12-13 | 1.42 | 0%
F.E.Z1.LV.BF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-11-29 | 2025-12-14 | 1.65 | 0%
F.E.Z1.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-29 | 2025-12-14 | 0.42 | 0%
F.E.Z8.AR.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes For BOH | 0.54 | 2025-11-29 | 2025-12-14 | 0.35 | 0%
F.E.Z1.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-30 | 2025-12-18 | 1.75 | 0%
R.E.4B.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-11-30 | 2025-12-15 | 3.69 | 0%
R.E.4B.AR.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-11-30 | 2025-12-15 | 3.81 | 0%
R.E.4B.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-11-30 | 2025-12-18 | 3.6 | 0%
F.E.Z2.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-11-30 | 2025-12-18 | 1.5 | 0%
F.E.Z2.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-11-30 | 2025-12-18 | 1.5 | 0%
F.E.Z3.LV.BF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-11-30 | 2025-12-15 | 0.77 | 0%
F.E.Z5.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-11-30 | 2025-12-15 | 0.85 | 0%
F.E.Z5.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-11-30 | 2025-12-15 | 0.85 | 0%
F.E.Z6.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-11-30 | 2025-12-18 | 0.45 | 0%
F.E.Z7.EL.BF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-11-30 | 2025-12-15 | 0.65 | 0%
F.E.Z8.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2025-11-30 | 2025-12-18 | 4.55 | 0%
F.E.Z8.F1.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.75 | 2025-11-30 | 2025-12-18 | 0.55 | 0%
R.E.5B.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-11-30 | 2025-12-15 | 3.38 | 0%
R.E.5B.AR.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-11-30 | 2025-12-15 | 3.58 | 0%
R.E.6B.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-11-30 | 2025-12-15 | 2.96 | 0%
R.E.6B.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-11-30 | 2025-12-18 | 3.3 | 0%
R.E.6B.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-11-30 | 2025-12-18 | 3.3 | 0%
R.E.6B.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-11-30 | 2025-12-18 | 3.45 | 0%
R.E.SS.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2025-11-30 | 2025-12-18 | 6.7 | 0%
R.E.SS.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-11-30 | 2025-12-18 | 9.65 | 0%
F.E.Z4.LV.LG.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-01 | 2025-12-16 | 0.81 | 0%
F.E.Z4.LV.LG.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-01 | 2025-12-16 | 0.81 | 0%
F.E.Z4.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-01 | 2025-12-16 | 0.5 | 0%
F.E.Z4.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-01 | 2025-12-16 | 1.04 | 0%
F.E.Z4.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-01 | 2025-12-21 | 2.1 | 0%
F.E.Z5.LV.LG.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-01 | 2025-12-16 | 0.81 | 0%
F.E.Z5.LV.LG.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-01 | 2025-12-16 | 0.81 | 0%
F.E.Z5.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-01 | 2025-12-21 | 2.1 | 0%
F.E.Z6.LV.2F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-01 | 2025-12-16 | 1.12 | 0%
F.E.Z6.LV.2F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-01 | 2025-12-16 | 1.12 | 0%
R.E.GE.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.75 | 2025-12-02 | 2025-12-22 | 1.8 | 0%
R.E.GE.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.75 | 2025-12-02 | 2025-12-22 | 1.8 | 0%
R.E.GE.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.75 | 2025-12-02 | 2025-12-22 | 4.85 | 0%
F.E.Z3.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-02 | 2025-12-17 | 0.15 | 0%
F.E.Z3.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-02 | 2025-12-17 | 0.15 | 0%
F.E.Z3.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-02 | 2025-12-22 | 0.85 | 0%
F.E.Z8.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-12-02 | 2025-12-22 | 0.4 | 0%
F.E.Z7.F1.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.75 | 2025-12-02 | 2025-12-22 | 0.15 | 0%
R.E.6B.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-12-02 | 2025-12-17 | 2.27 | 0%
F.E.Z6.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-12-03 | 2025-12-23 | 0.15 | 0%
F.E.Z8.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2025-12-03 | 2025-12-23 | 4.95 | 0%
R.E.GE.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.75 | 2025-12-04 | 2025-12-24 | 2.25 | 0%
F.E.Z4.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-04 | 2025-12-20 | 0.23 | 0%
F.E.Z4.EL.2F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-04 | 2025-12-20 | 1.15 | 0%
F.E.Z5.EL.2F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-04 | 2025-12-20 | 1.15 | 0%
F.E.Z5.EL.3F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-04 | 2025-12-20 | 1.15 | 0%
F.E.Z7.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-12-04 | 2025-12-24 | 0.7 | 0%
F.E.Z6.F2.2F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.75 | 2025-12-04 | 2025-12-24 | 0.8 | 0%
R.E.5B.AR.RF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-12-04 | 2025-12-20 | 3.42 | 0%
R.E.6B.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-12-04 | 2025-12-24 | 3.25 | 0%
R.E.SS.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-12-04 | 2025-12-24 | 7.5 | 0%
R.E.SS.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2025-12-04 | 2025-12-24 | 7.5 | 0%
R.E.4B.AR.RF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-12-06 | 2025-12-21 | 3.54 | 0%
F.E.Z1.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-07 | 2025-12-25 | 1.85 | 0%
F.E.Z1.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-07 | 2025-12-25 | 1.85 | 0%
R.E.GE.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.75 | 2025-12-07 | 2025-12-25 | 2.3 | 0%
F.E.Z4.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-07 | 2025-12-25 | 1.9 | 0%
F.E.Z7.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-07 | 2025-12-25 | 1.8 | 0%
F.E.Z8.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.75 | 2025-12-07 | 2025-12-25 | 0.7 | 0%
F.E.Z8.F1.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For Public Spaces | 0.54 | 2025-12-07 | 2025-12-22 | 0.5 | 0%
R.E.6B.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2025-12-07 | 2025-12-22 | 3.27 | 0%
R.E.6B.AR.RF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-12-07 | 2025-12-22 | 2.31 | 0%
R.E.6B.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-12-07 | 2025-12-22 | 2.31 | 0%
R.E.6B.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-12-07 | 2025-12-22 | 2.46 | 0%
R.E.6B.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-12-07 | 2025-12-25 | 2.45 | 0%
R.E.6B.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-12-07 | 2025-12-25 | 2.45 | 0%
R.E.6B.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-12-07 | 2025-12-25 | 2.4 | 0%
R.E.6B.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-12-07 | 2025-12-25 | 2.3 | 0%
F.E.Z2.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-08 | 2025-12-28 | 1.5 | 0%
F.E.Z2.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-08 | 2025-12-28 | 1.5 | 0%
F.E.Z3.LV.BF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-08 | 2025-12-23 | 0.81 | 0%
F.E.Z3.LV.BF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-08 | 2025-12-23 | 0.81 | 0%
F.E.Z5.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-08 | 2025-12-28 | 0.95 | 0%
F.E.Z8.AR.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-12-08 | 2025-12-23 | 0.27 | 0%
R.E.6B.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-12-08 | 2025-12-23 | 2.31 | 0%
R.E.VL.PL.GF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-12-08 | 2025-12-23 | 1.69 | 0%
R.E.VL.DR.GF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-12-08 | 2025-12-23 | 1.69 | 0%
R.E.VL.HV.GF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-12-08 | 2025-12-23 | 1.65 | 0%
R.E.VL.EL.GF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-12-08 | 2025-12-23 | 1.62 | 0%
R.E.VL.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-12-08 | 2025-12-28 | 1.8 | 0%
R.E.VL.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-12-08 | 2025-12-28 | 1.8 | 0%
R.E.VL.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-12-08 | 2025-12-28 | 1.8 | 0%
R.E.VL.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-12-08 | 2025-12-28 | 2.45 | 0%
R.E.VL.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-12-08 | 2025-12-28 | 2.45 | 0%
R.E.VL.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-12-08 | 2025-12-28 | 2.4 | 0%
R.E.VL.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-12-08 | 2025-12-28 | 2.35 | 0%
R.E.SS.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-08 | 2025-12-23 | 5.5 | 0%
R.E.GE.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.75 | 2025-12-09 | 2025-12-29 | 3.5 | 0%
F.E.Z4.LV.LG.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-09 | 2025-12-29 | 0.9 | 0%
F.E.Z5.LV.LG.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-09 | 2025-12-29 | 0.9 | 0%
F.E.Z6.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-09 | 2025-12-29 | 1.2 | 0%
F.E.Z6.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-09 | 2025-12-29 | 1.2 | 0%
R.E.VL.AR.1F.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-12-09 | 2025-12-24 | 2.27 | 0%
R.E.VL.HV.1F.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-12-09 | 2025-12-24 | 2.27 | 0%
R.E.VL.FF.1F.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-12-09 | 2025-12-24 | 2.46 | 0%
F.E.Z3.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-10 | 2025-12-30 | 0.15 | 0%
R.E.6B.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-12-10 | 2025-12-30 | 3.3 | 0%
F.E.Z3.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-11 | 2025-12-27 | 0.12 | 0%
F.E.Z3.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-11 | 2025-12-31 | 1.6 | 0%
F.E.Z1.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-13 | 2025-12-28 | 0.42 | 0%
F.E.Z1.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-13 | 2025-12-28 | 0.42 | 0%
F.E.Z6.AR.BF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-12-13 | 2025-12-28 | 0.19 | 0%
F.E.Z6.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-13 | 2025-12-28 | 0.08 | 0%
R.E.6B.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-12-13 | 2025-12-28 | 2.27 | 0%
R.E.SS.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-13 | 2025-12-28 | 5.5 | 0%
F.E.Z4.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-14 | 2026-01-01 | 1.65 | 0%
F.E.Z5.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-14 | 2026-01-01 | 0.35 | 0%
F.E.Z5.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-14 | 2026-01-01 | 0.35 | 0%
F.E.Z5.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-14 | 2026-01-01 | 1.65 | 0%
F.E.Z5.LV.3F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-14 | 2026-01-01 | 1.65 | 0%
F.E.Z7.LV.BF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-14 | 2025-12-29 | 0.65 | 0%
F.E.Z7.LV.BF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-14 | 2025-12-29 | 0.65 | 0%
F.E.Z7.EX.GE.PO.002 | Prepare and Submit Shop Drawings For Pools and Water Features | 0.54 | 2025-12-14 | 2025-12-29 | 2.54 | 0%
R.E.6B.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-12-14 | 2026-01-01 | 2.45 | 0%
R.E.6B.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-12-14 | 2026-01-01 | 2.45 | 0%
R.E.6B.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-12-14 | 2026-01-01 | 2.65 | 0%
R.E.6B.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-12-14 | 2026-01-01 | 5.95 | 0%
R.E.VL.PL.RF.WS.002 | Prepare and Submit Shop Drawings For Water Supply Network | 0.54 | 2025-12-14 | 2025-12-29 | 1.46 | 0%
R.E.VL.DR.RF.FW.002 | Prepare and Submit Shop Drawings For Drainage & Drainage Details | 0.54 | 2025-12-14 | 2025-12-29 | 1.46 | 0%
R.E.VL.HV.RF.CH.002 | Prepare and Submit Shop Drawings For Chilled Water Network | 0.54 | 2025-12-14 | 2025-12-29 | 1.46 | 0%
R.E.VL.EL.RF.PW.002 | Prepare and Submit Shop Drawings For Power | 0.54 | 2025-12-14 | 2025-12-29 | 1.38 | 0%
R.E.VL.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.75 | 2025-12-14 | 2026-01-01 | 1.55 | 0%
R.E.VL.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.75 | 2025-12-14 | 2026-01-01 | 1.55 | 0%
R.E.VL.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.75 | 2025-12-14 | 2026-01-01 | 1.55 | 0%
F.E.Z1.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-15 | 2026-01-04 | 1.8 | 0%
F.E.Z1.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-15 | 2026-01-04 | 0.45 | 0%
F.E.Z8.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.75 | 2025-12-15 | 2026-01-04 | 0.4 | 0%
R.E.VL.AR.1F.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2025-12-15 | 2025-12-30 | 2.27 | 0%
R.E.SS.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-15 | 2025-12-30 | 5.5 | 0%
R.E.SS.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-15 | 2025-12-30 | 5.5 | 0%
R.E.4B.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-12-16 | 2026-01-05 | 4 | 0%
R.E.4B.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-12-16 | 2026-01-05 | 4.15 | 0%
F.E.Z3.LV.BF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-16 | 2025-12-31 | 0.81 | 0%
F.E.Z3.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-16 | 2026-01-05 | 0.85 | 0%
F.E.Z5.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-16 | 2025-12-31 | 0.31 | 0%
F.E.Z5.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-16 | 2025-12-31 | 0.88 | 0%
F.E.Z5.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-16 | 2026-01-05 | 0.9 | 0%
F.E.Z5.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-16 | 2026-01-05 | 0.9 | 0%
F.E.Z7.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-16 | 2025-12-31 | 0.12 | 0%
F.E.Z7.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-16 | 2026-01-05 | 0.7 | 0%
R.E.5B.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-12-16 | 2026-01-05 | 3.7 | 0%
R.E.5B.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-12-16 | 2026-01-05 | 3.9 | 0%
R.E.6B.AR.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-12-16 | 2025-12-31 | 3.38 | 0%
R.E.6B.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2025-12-16 | 2026-01-05 | 3.2 | 0%
F.E.Z4.LV.LG.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-17 | 2026-01-06 | 0.85 | 0%
F.E.Z4.LV.LG.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-17 | 2026-01-06 | 0.85 | 0%
F.E.Z4.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-17 | 2026-01-06 | 0.55 | 0%
F.E.Z4.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-17 | 2026-01-06 | 1.1 | 0%
F.E.Z5.LV.LG.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-17 | 2026-01-06 | 0.85 | 0%
F.E.Z5.LV.LG.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-17 | 2026-01-06 | 0.85 | 0%
F.E.Z6.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-17 | 2026-01-06 | 1.2 | 0%
F.E.Z6.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-17 | 2026-01-06 | 1.2 | 0%
F.E.Z3.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-18 | 2026-01-03 | 0.15 | 0%
F.E.Z3.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-18 | 2026-01-07 | 0.15 | 0%
F.E.Z3.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-18 | 2026-01-07 | 0.15 | 0%
F.E.Z4.LV.LG.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-18 | 2026-01-03 | 0.81 | 0%
F.E.Z5.LV.LG.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-18 | 2026-01-03 | 0.81 | 0%
F.E.Z6.EL.2F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-18 | 2026-01-03 | 0.73 | 0%
F.E.Z8.EL.BF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-18 | 2026-01-03 | 0.23 | 0%
F.E.Z8.AR.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details For BOH | 0.54 | 2025-12-18 | 2026-01-03 | 0.35 | 0%
R.E.6B.AR.RF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-12-18 | 2026-01-03 | 2.31 | 0%
R.E.6B.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-12-18 | 2026-01-07 | 2.45 | 0%
F.E.Z1.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-21 | 2026-01-05 | 0.38 | 0%
F.E.Z1.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-21 | 2026-01-05 | 0.38 | 0%
F.E.Z4.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-21 | 2026-01-08 | 0.25 | 0%
F.E.Z4.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-21 | 2026-01-08 | 1.25 | 0%
F.E.Z5.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-21 | 2026-01-08 | 1.25 | 0%
F.E.Z5.EL.3F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-21 | 2026-01-08 | 1.25 | 0%
R.E.5B.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-12-21 | 2026-01-08 | 3.75 | 0%
R.E.VL.AR.1F.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2025-12-21 | 2026-01-05 | 2.31 | 0%
R.E.4B.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2025-12-22 | 2026-01-11 | 3.85 | 0%
F.E.Z7.LV.BF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-22 | 2026-01-06 | 0.69 | 0%
F.E.Z7.LV.BF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-22 | 2026-01-06 | 0.69 | 0%
R.E.VL.AR.RF.RW.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-12-22 | 2026-01-06 | 4.69 | 0%
F.E.Z6.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-23 | 2026-01-07 | 0 | 0%
F.E.Z8.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-23 | 2026-01-07 | 0.35 | 0%
F.E.Z8.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-23 | 2026-01-07 | 0.35 | 0%
F.E.Z8.F1.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.75 | 2025-12-23 | 2026-01-12 | 0.55 | 0%
R.E.6B.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2025-12-23 | 2026-01-12 | 3.55 | 0%
R.E.6B.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-12-23 | 2026-01-12 | 2.5 | 0%
R.E.6B.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-12-23 | 2026-01-12 | 2.5 | 0%
R.E.6B.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-12-23 | 2026-01-12 | 2.65 | 0%
F.E.Z3.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-24 | 2026-01-13 | 0.85 | 0%
F.E.Z3.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-24 | 2026-01-13 | 0.85 | 0%
F.E.Z8.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-12-24 | 2026-01-13 | 0.3 | 0%
R.E.6B.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2025-12-24 | 2026-01-13 | 2.5 | 0%
R.E.VL.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-12-24 | 2026-01-13 | 1.85 | 0%
R.E.VL.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-12-24 | 2026-01-13 | 1.85 | 0%
R.E.VL.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-12-24 | 2026-01-13 | 1.8 | 0%
R.E.VL.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-12-24 | 2026-01-13 | 1.75 | 0%
R.E.SS.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-24 | 2026-01-13 | 5.95 | 0%
F.E.Z5.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2025-12-25 | 2026-01-10 | 0.27 | 0%
F.E.Z5.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2025-12-25 | 2026-01-10 | 0.27 | 0%
F.E.Z6.EL.BF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-25 | 2026-01-10 | 0.15 | 0%
F.E.Z6.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-25 | 2026-01-10 | 0.04 | 0%
F.E.Z6.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-25 | 2026-01-10 | 0.04 | 0%
F.E.Z8.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-25 | 2026-01-10 | 0.54 | 0%
F.E.Z8.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-25 | 2026-01-10 | 0.54 | 0%
R.E.VL.FA.GE.FA.002 | Prepare and Submit Shop Drawings For Façade | 0.54 | 2025-12-25 | 2026-01-10 | 2.15 | 0%
R.E.VL.AR.GF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2025-12-25 | 2026-01-10 | 1.73 | 0%
R.E.VL.HV.GF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2025-12-25 | 2026-01-10 | 1.73 | 0%
R.E.VL.FF.GF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2025-12-25 | 2026-01-10 | 1.92 | 0%
R.E.VL.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2025-12-25 | 2026-01-14 | 2.45 | 0%
R.E.VL.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2025-12-25 | 2026-01-14 | 2.45 | 0%
R.E.VL.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2025-12-25 | 2026-01-14 | 2.65 | 0%
R.E.GE.EX.GE.LP.002 | Prepare and Submit Shop Drawings For LPG System Installation | 0.54 | 2025-12-27 | 2026-01-11 | 1.65 | 0%
F.E.Z3.LV.2F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-27 | 2026-01-11 | 0.19 | 0%
F.E.Z4.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-27 | 2026-01-11 | 0.27 | 0%
F.E.Z5.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2025-12-27 | 2026-01-11 | 0.19 | 0%
F.E.Z3.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-28 | 2026-01-15 | 0.15 | 0%
F.E.Z9.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2025-12-28 | 2026-01-12 | 2.08 | 0%
F.E.Z9.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2025-12-28 | 2026-01-12 | 2.85 | 0%
F.E.Z9.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2025-12-28 | 2026-01-12 | 2.85 | 0%
F.E.Z1.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-29 | 2026-01-18 | 0.45 | 0%
F.E.Z1.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-29 | 2026-01-18 | 0.45 | 0%
F.E.Z3.EX.GE.PO.002 | Prepare and Submit Shop Drawings For Pools and Water Features | 0.54 | 2025-12-29 | 2026-01-13 | 1.58 | 0%
F.E.Z6.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2025-12-29 | 2026-01-18 | 0.2 | 0%
F.E.Z6.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2025-12-29 | 2026-01-18 | 0.1 | 0%
F.E.Z8.LV.BF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-29 | 2026-01-13 | 0.35 | 0%
F.E.Z8.LV.BF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-29 | 2026-01-13 | 0.35 | 0%
R.E.6B.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-12-29 | 2026-01-18 | 2.45 | 0%
R.E.SS.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-29 | 2026-01-18 | 5.95 | 0%
F.E.Z7.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2025-12-30 | 2026-01-14 | 0.12 | 0%
F.E.Z7.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2025-12-30 | 2026-01-14 | 0.12 | 0%
F.E.Z7.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2025-12-30 | 2026-01-19 | 0.7 | 0%
F.E.Z7.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2025-12-30 | 2026-01-19 | 0.7 | 0%
F.E.Z7.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.75 | 2025-12-30 | 2026-01-19 | 2.75 | 0%
R.E.6B.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2025-12-30 | 2026-01-14 | 2.77 | 0%
R.E.VL.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.75 | 2025-12-30 | 2026-01-19 | 1.6 | 0%
R.E.VL.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.75 | 2025-12-30 | 2026-01-19 | 1.6 | 0%
R.E.VL.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.75 | 2025-12-30 | 2026-01-19 | 1.6 | 0%
R.E.VL.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.75 | 2025-12-30 | 2026-01-19 | 1.5 | 0%
R.E.VL.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2025-12-31 | 2026-01-20 | 2.45 | 0%
R.E.SS.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2025-12-31 | 2026-01-20 | 5.95 | 0%
R.E.SS.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2025-12-31 | 2026-01-20 | 5.95 | 0%
F.E.Z3.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-01 | 2026-01-21 | 0.85 | 0%
F.E.Z4.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-01 | 2026-01-17 | 0.31 | 0%
F.E.Z4.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-01 | 2026-01-17 | 0.31 | 0%
F.E.Z5.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-01-01 | 2026-01-17 | 0.35 | 0%
F.E.Z5.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-01 | 2026-01-21 | 0.3 | 0%
F.E.Z5.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-01 | 2026-01-21 | 0.95 | 0%
F.E.Z6.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-01 | 2026-01-17 | 0.08 | 0%
F.E.Z6.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-01 | 2026-01-17 | 0.08 | 0%
F.E.Z7.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-01 | 2026-01-21 | 0.1 | 0%
F.E.Z8.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-01 | 2026-01-17 | 0.46 | 0%
F.E.Z8.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-01 | 2026-01-17 | 0.46 | 0%
F.E.Z8.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-01-01 | 2026-01-17 | 4.92 | 0%
F.E.Z8.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-01 | 2026-01-17 | 0.35 | 0%
F.E.Z8.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-01 | 2026-01-17 | 0.35 | 0%
R.E.6B.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2026-01-01 | 2026-01-21 | 3.65 | 0%
R.E.VL.LI.GE.EL.002 | Prepare and Submit Shop Drawings For Elevator | 0.54 | 2026-01-01 | 2026-01-17 | 2.42 | 0%
R.E.VL.AR.GF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2026-01-01 | 2026-01-17 | 1.69 | 0%
R.E.VL.AR.RF.WA.002 | Prepare and Submit Shop Drawings For Waterproofing | 0.54 | 2026-01-01 | 2026-01-17 | 1.46 | 0%
R.E.VL.HV.RF.DU.002 | Prepare and Submit Shop Drawings For Ducting | 0.54 | 2026-01-01 | 2026-01-17 | 1.46 | 0%
R.E.VL.FF.RF.FN.002 | Prepare and Submit Shop Drawings For Firefighting Network | 0.54 | 2026-01-01 | 2026-01-17 | 1.65 | 0%
F.E.Z3.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-01-04 | 2026-01-19 | 0.19 | 0%
F.E.Z3.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-04 | 2026-01-22 | 0.2 | 0%
F.E.Z4.LV.LG.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-04 | 2026-01-22 | 0.9 | 0%
F.E.Z5.LV.LG.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-04 | 2026-01-22 | 0.9 | 0%
F.E.Z6.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-01-04 | 2026-01-19 | 0 | 0%
F.E.Z6.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-01-04 | 2026-01-19 | 0 | 0%
F.E.Z6.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-04 | 2026-01-22 | 0.8 | 0%
F.E.Z8.LV.BF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-04 | 2026-01-19 | 0.31 | 0%
F.E.Z8.LV.BF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-04 | 2026-01-19 | 0.31 | 0%
F.E.Z8.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-04 | 2026-01-22 | 0.25 | 0%
F.E.Z8.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.75 | 2026-01-04 | 2026-01-22 | 0.4 | 0%
R.E.6B.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2026-01-04 | 2026-01-22 | 2.5 | 0%
F.E.Z1.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-06 | 2026-01-26 | 0.4 | 0%
F.E.Z1.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-06 | 2026-01-26 | 0.4 | 0%
R.E.VL.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2026-01-06 | 2026-01-26 | 2.5 | 0%
F.E.Z7.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-07 | 2026-01-27 | 0.75 | 0%
F.E.Z7.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-07 | 2026-01-27 | 0.75 | 0%
R.E.VL.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2026-01-07 | 2026-01-27 | 5.05 | 0%
F.E.Z4.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-01-08 | 2026-01-24 | 0.23 | 0%
F.E.Z6.LV.BF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-01-08 | 2026-01-24 | 0.12 | 0%
F.E.Z6.LV.BF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-01-08 | 2026-01-24 | 0.12 | 0%
F.E.Z6.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-08 | 2026-01-28 | 0 | 0%
F.E.Z7.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-08 | 2026-01-24 | 0.12 | 0%
F.E.Z7.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-08 | 2026-01-24 | 0.12 | 0%
F.E.Z8.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-08 | 2026-01-28 | 0.35 | 0%
F.E.Z8.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-08 | 2026-01-28 | 0.35 | 0%
R.E.VL.AR.GF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2026-01-08 | 2026-01-24 | 1.69 | 0%
R.E.VL.AR.RF.WL.002 | Prepare and Submit Shop Drawings For Wall Finishes | 0.54 | 2026-01-08 | 2026-01-24 | 1.42 | 0%
F.E.Z5.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-11 | 2026-01-29 | 0.3 | 0%
F.E.Z5.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-11 | 2026-01-29 | 0.3 | 0%
F.E.Z6.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-11 | 2026-01-29 | 0.2 | 0%
F.E.Z6.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-11 | 2026-01-29 | 0.05 | 0%
F.E.Z6.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-11 | 2026-01-29 | 0.05 | 0%
F.E.Z8.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-11 | 2026-01-29 | 0.6 | 0%
F.E.Z8.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-11 | 2026-01-29 | 0.6 | 0%
R.E.6B.AR.RF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2026-01-11 | 2026-01-26 | 2.65 | 0%
R.E.VL.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.75 | 2026-01-11 | 2026-01-29 | 2.35 | 0%
R.E.VL.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2026-01-11 | 2026-01-29 | 1.9 | 0%
R.E.VL.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2026-01-11 | 2026-01-29 | 1.9 | 0%
R.E.VL.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2026-01-11 | 2026-01-29 | 2.1 | 0%
R.E.GE.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.75 | 2026-01-12 | 2026-02-01 | 1.8 | 0%
F.E.Z3.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-12 | 2026-02-01 | 0.2 | 0%
F.E.Z4.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-12 | 2026-02-01 | 0.3 | 0%
F.E.Z5.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-12 | 2026-02-01 | 0.2 | 0%
F.E.Z2.AR.BF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-01-13 | 2026-01-28 | 2.5 | 0%
F.E.Z2.AR.LG.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-01-13 | 2026-01-28 | 2.5 | 0%
F.E.Z2.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-01-13 | 2026-01-28 | 2.5 | 0%
F.E.Z6.LV.BF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-13 | 2026-01-28 | 0.12 | 0%
F.E.Z6.LV.BF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-13 | 2026-01-28 | 0.12 | 0%
F.E.Z6.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-01-13 | 2026-01-28 | 0 | 0%
F.E.Z6.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-01-13 | 2026-01-28 | 0 | 0%
F.E.Z9.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2026-01-13 | 2026-02-02 | 2.25 | 0%
F.E.Z9.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2026-01-13 | 2026-02-02 | 3.1 | 0%
F.E.Z9.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2026-01-13 | 2026-02-02 | 3.1 | 0%
R.E.VL.AR.1F.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2026-01-13 | 2026-01-28 | 2.58 | 0%
R.E.VL.AR.RF.RP.002 | Prepare and Submit Shop Drawings For RCP | 0.54 | 2026-01-13 | 2026-01-28 | 1.5 | 0%
F.E.Z3.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.75 | 2026-01-14 | 2026-02-03 | 1.7 | 0%
F.E.Z8.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-14 | 2026-02-03 | 0.35 | 0%
F.E.Z8.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-14 | 2026-02-03 | 0.35 | 0%
F.E.Z7.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-15 | 2026-02-04 | 0.1 | 0%
F.E.Z7.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-15 | 2026-02-04 | 0.1 | 0%
R.E.6B.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2026-01-15 | 2026-02-04 | 3 | 0%
F.E.Z8.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-01-17 | 2026-02-01 | 1.42 | 0%
F.E.Z4.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-18 | 2026-02-05 | 0.35 | 0%
F.E.Z4.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-18 | 2026-02-05 | 0.35 | 0%
F.E.Z5.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-18 | 2026-02-05 | 0.4 | 0%
F.E.Z6.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-18 | 2026-02-05 | 0.1 | 0%
F.E.Z6.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-18 | 2026-02-05 | 0.1 | 0%
F.E.Z8.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-18 | 2026-02-05 | 0.5 | 0%
F.E.Z8.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-18 | 2026-02-05 | 0.5 | 0%
F.E.Z8.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-01-18 | 2026-02-05 | 5.35 | 0%
F.E.Z8.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-18 | 2026-02-05 | 0.4 | 0%
F.E.Z8.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-18 | 2026-02-05 | 0.4 | 0%
R.E.VL.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.75 | 2026-01-18 | 2026-02-05 | 2.65 | 0%
R.E.VL.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2026-01-18 | 2026-02-05 | 1.85 | 0%
R.E.VL.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.75 | 2026-01-18 | 2026-02-05 | 1.6 | 0%
R.E.VL.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.75 | 2026-01-18 | 2026-02-05 | 1.6 | 0%
R.E.VL.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.75 | 2026-01-18 | 2026-02-05 | 1.8 | 0%
F.E.Z3.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-20 | 2026-02-09 | 0.2 | 0%
F.E.Z6.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-20 | 2026-02-09 | 0 | 0%
F.E.Z6.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-20 | 2026-02-09 | 0 | 0%
F.E.Z8.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-20 | 2026-02-09 | 0.35 | 0%
F.E.Z8.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-20 | 2026-02-09 | 0.35 | 0%
F.E.Z4.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-25 | 2026-02-12 | 0.25 | 0%
F.E.Z6.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-01-25 | 2026-02-12 | 0.15 | 0%
F.E.Z6.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-01-25 | 2026-02-12 | 0.15 | 0%
F.E.Z7.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-25 | 2026-02-12 | 0.15 | 0%
F.E.Z7.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-25 | 2026-02-12 | 0.15 | 0%
R.E.VL.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2026-01-25 | 2026-02-12 | 1.85 | 0%
R.E.VL.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.75 | 2026-01-25 | 2026-02-12 | 1.55 | 0%
F.E.Z1.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-01-26 | 2026-02-10 | 1.92 | 0%
F.E.Z5.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-01-27 | 2026-02-11 | 1.42 | 0%
F.E.Z5.F2.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-01-27 | 2026-02-11 | 1.42 | 0%
F.E.Z5.F2.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-01-27 | 2026-02-11 | 1.42 | 0%
F.E.Z5.F2.3F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-01-27 | 2026-02-11 | 1.42 | 0%
F.E.Z5.F2.LG.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-01-27 | 2026-02-11 | 1.42 | 0%
F.E.Z5.F2.2F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-01-27 | 2026-02-11 | 1.42 | 0%
R.E.6B.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2026-01-27 | 2026-02-16 | 2.9 | 0%
R.E.VL.AR.GF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2026-01-27 | 2026-02-11 | 2.12 | 0%
F.E.Z4.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-01-28 | 2026-02-14 | 1.62 | 0%
F.E.Z8.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-01-28 | 2026-02-14 | 1.58 | 0%
F.E.Z2.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-01-29 | 2026-02-18 | 2.7 | 0%
F.E.Z2.AR.LG.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-01-29 | 2026-02-18 | 2.7 | 0%
F.E.Z2.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-01-29 | 2026-02-18 | 2.7 | 0%
F.E.Z6.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-29 | 2026-02-18 | 0.1 | 0%
F.E.Z6.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-29 | 2026-02-18 | 0.1 | 0%
F.E.Z6.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-01-29 | 2026-02-18 | 0 | 0%
F.E.Z6.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-01-29 | 2026-02-18 | 0 | 0%
R.E.VL.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2026-01-29 | 2026-02-18 | 2.8 | 0%
R.E.VL.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.75 | 2026-01-29 | 2026-02-18 | 1.6 | 0%
R.E.4B.AR.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-01-31 | 2026-02-16 | 1.5 | 0%
R.E.5B.AR.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-01-31 | 2026-02-16 | 1.27 | 0%
R.E.6B.AR.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-01-31 | 2026-02-16 | 1.65 | 0%
R.E.VL.AR.1F.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-01-31 | 2026-02-16 | 1.73 | 0%
F.E.Z7.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-02-02 | 2026-02-18 | 1.42 | 0%
F.E.Z8.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-02-02 | 2026-02-23 | 1.55 | 0%
R.E.VL.AR.RF.WI.002 | Prepare and Submit Shop Drawings For Windows Schedule & Details | 0.54 | 2026-02-02 | 2026-02-18 | 2.04 | 0%
F.E.Z6.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-02-07 | 2026-02-23 | 1.54 | 0%
F.E.Z4.F2.LG.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-09 | 2026-02-25 | 1.23 | 0%
F.E.Z4.F2.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-09 | 2026-02-25 | 1.23 | 0%
F.E.Z4.F2.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-09 | 2026-02-25 | 1.23 | 0%
F.E.Z4.F2.2F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-09 | 2026-02-25 | 1.23 | 0%
F.E.Z1.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-02-11 | 2026-03-04 | 2.1 | 0%
F.E.Z5.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-02-12 | 2026-03-05 | 1.55 | 0%
F.E.Z5.F2.GF.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-12 | 2026-03-05 | 1.55 | 0%
F.E.Z5.F2.1F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-12 | 2026-03-05 | 1.55 | 0%
F.E.Z5.F2.3F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-12 | 2026-03-05 | 1.55 | 0%
F.E.Z5.F2.LG.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-12 | 2026-03-05 | 1.55 | 0%
F.E.Z5.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-12 | 2026-03-05 | 1.55 | 0%
R.E.VL.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2026-02-12 | 2026-03-05 | 2.3 | 0%
F.E.Z1.AR.BF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.62 | 0%
F.E.Z1.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.62 | 0%
F.E.Z1.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.62 | 0%
F.E.Z5.AR.LG.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.35 | 0%
F.E.Z5.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.35 | 0%
F.E.Z5.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.35 | 0%
F.E.Z5.AR.2F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.35 | 0%
F.E.Z5.AR.3F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.35 | 0%
F.E.Z5.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-14 | 2026-03-01 | 1.35 | 0%
F.E.Z4.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-02-15 | 2026-03-08 | 1.75 | 0%
F.E.Z8.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-02-15 | 2026-03-08 | 1.7 | 0%
R.E.4B.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-16 | 2026-03-03 | 0.92 | 0%
F.E.Z3.AR.BF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-16 | 2026-03-03 | 1.54 | 0%
F.E.Z3.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-16 | 2026-03-03 | 1.54 | 0%
F.E.Z3.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-16 | 2026-03-03 | 1.54 | 0%
F.E.Z3.F2.2F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-16 | 2026-03-03 | 1.54 | 0%
F.E.Z3.AR.2F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-16 | 2026-03-03 | 1.54 | 0%
F.E.Z3.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-16 | 2026-03-03 | 1.54 | 0%
R.E.4B.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-02-17 | 2026-03-10 | 1.6 | 0%
F.E.Z6.F2.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-17 | 2026-03-04 | 1.46 | 0%
F.E.Z6.F2.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-17 | 2026-03-04 | 1.46 | 0%
F.E.Z6.F2.2F.ID.002 | Prepare and Submit Shop Drawings For ID Details For Guest Rooms | 0.54 | 2026-02-17 | 2026-03-04 | 1.46 | 0%
R.E.5B.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-02-17 | 2026-03-10 | 1.35 | 0%
R.E.6B.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-02-17 | 2026-03-10 | 1.75 | 0%
R.E.VL.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-02-17 | 2026-03-10 | 1.85 | 0%
R.E.4B.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-19 | 2026-03-07 | 0.73 | 0%
F.E.Z6.AR.BF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-19 | 2026-03-07 | 1.42 | 0%
F.E.Z6.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-19 | 2026-03-07 | 1.42 | 0%
F.E.Z6.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-19 | 2026-03-07 | 1.42 | 0%
F.E.Z6.AR.2F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-19 | 2026-03-07 | 1.42 | 0%
F.E.Z7.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-02-19 | 2026-03-12 | 1.5 | 0%
R.E.VL.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.75 | 2026-02-19 | 2026-03-12 | 2.15 | 0%
R.E.4B.AR.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-02-21 | 2026-03-08 | 1.46 | 0%
R.E.5B.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-21 | 2026-03-08 | 0.35 | 0%
R.E.5B.AR.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-02-21 | 2026-03-08 | 1.23 | 0%
R.E.5B.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-21 | 2026-03-08 | 0.58 | 0%
R.E.6B.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-21 | 2026-03-08 | 0.69 | 0%
R.E.6B.AR.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-02-21 | 2026-03-08 | 1.54 | 0%
R.E.6B.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-21 | 2026-03-08 | 1 | 0%
R.E.VL.AR.GF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-21 | 2026-03-08 | 1.08 | 0%
R.E.VL.AR.1F.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-02-21 | 2026-03-08 | 1.69 | 0%
R.E.VL.AR.RF.FL.002 | Prepare and Submit Shop Drawings For Floor Finishes | 0.54 | 2026-02-21 | 2026-03-08 | 1.08 | 0%
R.E.4B.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-02-22 | 2026-03-09 | 5.35 | 0%
F.E.Z7.AR.BF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-22 | 2026-03-09 | 1.35 | 0%
F.E.Z7.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-22 | 2026-03-09 | 1.35 | 0%
F.E.Z7.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-22 | 2026-03-09 | 1.35 | 0%
F.E.Z8.AR.BF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-22 | 2026-03-09 | 1.35 | 0%
F.E.Z8.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-22 | 2026-03-09 | 1.35 | 0%
F.E.Z8.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-22 | 2026-03-09 | 1.35 | 0%
R.E.GE.EX.GE.HA.002 | Prepare and Submit Shop Drawings For Hard Landscaping & Furniture | 0.54 | 2026-02-23 | 2026-03-10 | 1.96 | 0%
F.E.Z4.AR.LG.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-24 | 2026-03-11 | 1.23 | 0%
F.E.Z4.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-24 | 2026-03-11 | 1.23 | 0%
F.E.Z4.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-24 | 2026-03-11 | 1.23 | 0%
F.E.Z4.AR.2F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-02-24 | 2026-03-11 | 1.23 | 0%
F.E.Z6.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-02-24 | 2026-03-16 | 1.7 | 0%
F.E.Z4.F2.LG.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-26 | 2026-03-18 | 1.35 | 0%
F.E.Z4.F2.GF.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-26 | 2026-03-18 | 1.35 | 0%
F.E.Z4.F2.1F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-26 | 2026-03-18 | 1.35 | 0%
F.E.Z4.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-02-26 | 2026-03-18 | 1.35 | 0%
R.E.5B.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-02-26 | 2026-03-14 | 5.19 | 0%
R.E.6B.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-02-26 | 2026-03-14 | 5.19 | 0%
R.E.VL.KE.GE.FA.002 | Prepare and Submit Shop Drawings For Kitchen & Laundry Equipment | 0.54 | 2026-02-26 | 2026-03-14 | 5.19 | 0%
F.E.Z1.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.8 | 0%
F.E.Z1.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.8 | 0%
F.E.Z1.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.8 | 0%
R.E.4B.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-03-02 | 2026-03-17 | 1.92 | 0%
F.E.Z5.AR.LG.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.5 | 0%
F.E.Z5.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.5 | 0%
F.E.Z5.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.5 | 0%
F.E.Z5.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.5 | 0%
F.E.Z5.AR.3F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.5 | 0%
F.E.Z5.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-02 | 2026-03-24 | 1.5 | 0%
R.E.4B.AR.RF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-04 | 2026-03-19 | 0.96 | 0%
R.E.4B.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-04 | 2026-03-26 | 1 | 0%
F.E.Z3.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-04 | 2026-03-26 | 1.7 | 0%
F.E.Z3.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-04 | 2026-03-26 | 1.7 | 0%
F.E.Z3.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-04 | 2026-03-26 | 1.7 | 0%
F.E.Z3.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-03-04 | 2026-03-26 | 1.7 | 0%
F.E.Z3.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-04 | 2026-03-26 | 1.7 | 0%
F.E.Z3.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-04 | 2026-03-26 | 1.7 | 0%
F.E.Z6.F2.1F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-03-05 | 2026-03-29 | 1.6 | 0%
F.E.Z6.F2.GF.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-03-05 | 2026-03-29 | 1.6 | 0%
F.E.Z6.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.75 | 2026-03-05 | 2026-03-29 | 1.6 | 0%
R.E.4B.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-08 | 2026-03-30 | 0.85 | 0%
F.E.Z6.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-08 | 2026-03-30 | 1.6 | 0%
F.E.Z6.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-08 | 2026-03-30 | 1.6 | 0%
F.E.Z6.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-08 | 2026-03-30 | 1.6 | 0%
F.E.Z6.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-08 | 2026-03-30 | 1.6 | 0%
R.E.4B.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-09 | 2026-03-28 | 0.73 | 0%
R.E.4B.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-09 | 2026-03-31 | 1.6 | 0%
R.E.5B.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-09 | 2026-03-28 | 0.38 | 0%
R.E.5B.AR.RF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-09 | 2026-03-28 | 0.62 | 0%
R.E.5B.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-09 | 2026-03-31 | 0.4 | 0%
R.E.5B.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-09 | 2026-03-31 | 1.35 | 0%
R.E.5B.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-09 | 2026-03-31 | 0.65 | 0%
R.E.6B.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-09 | 2026-03-28 | 0.73 | 0%
R.E.6B.AR.RF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-09 | 2026-03-28 | 1.04 | 0%
R.E.6B.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-09 | 2026-03-31 | 0.8 | 0%
R.E.6B.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-09 | 2026-03-31 | 1.7 | 0%
R.E.6B.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-09 | 2026-03-31 | 1.1 | 0%
R.E.VL.AR.GF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-09 | 2026-03-28 | 1.15 | 0%
R.E.VL.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-09 | 2026-03-31 | 1.2 | 0%
R.E.VL.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-09 | 2026-03-31 | 1.85 | 0%
R.E.VL.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.75 | 2026-03-09 | 2026-03-31 | 1.2 | 0%
R.E.4B.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-03-10 | 2026-04-01 | 5.8 | 0%
F.E.Z7.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-10 | 2026-04-01 | 1.5 | 0%
F.E.Z7.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-10 | 2026-04-01 | 1.5 | 0%
F.E.Z7.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-10 | 2026-04-01 | 1.5 | 0%
F.E.Z8.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-10 | 2026-04-01 | 1.5 | 0%
F.E.Z8.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-10 | 2026-04-01 | 1.5 | 0%
F.E.Z8.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-10 | 2026-04-01 | 1.5 | 0%
R.E.VL.AR.RF.DR.002 | Prepare and Submit Shop Drawings For Doors Schedule & Details | 0.54 | 2026-03-10 | 2026-03-29 | 1.12 | 0%
R.E.GE.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.75 | 2026-03-11 | 2026-04-02 | 2.15 | 0%
F.E.Z4.AR.LG.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-12 | 2026-04-05 | 1.35 | 0%
F.E.Z4.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-12 | 2026-04-05 | 1.35 | 0%
F.E.Z4.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-12 | 2026-04-05 | 1.35 | 0%
F.E.Z4.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-03-12 | 2026-04-05 | 1.35 | 0%
R.E.4B.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-03-14 | 2026-04-01 | 1.92 | 0%
R.E.5B.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-03-15 | 2026-04-06 | 5.65 | 0%
R.E.6B.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-03-15 | 2026-04-06 | 5.65 | 0%
R.E.VL.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.75 | 2026-03-15 | 2026-04-06 | 5.65 | 0%
R.E.5B.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-03-17 | 2026-04-05 | 1.19 | 0%
R.E.6B.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-03-17 | 2026-04-05 | 1.58 | 0%
R.E.VL.EL.1F.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-03-17 | 2026-04-05 | 1.69 | 0%
R.E.4B.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-03-18 | 2026-04-09 | 2.1 | 0%
R.E.4B.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-03-19 | 2026-04-07 | 1.92 | 0%
R.E.4B.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-03-19 | 2026-04-07 | 1.92 | 0%
R.E.4B.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-03-19 | 2026-04-07 | 1.31 | 0%
R.E.4B.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-24 | 2026-04-13 | 1.05 | 0%
R.E.4B.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-03-28 | 2026-04-12 | 1.92 | 0%
R.E.4B.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-29 | 2026-04-16 | 0.8 | 0%
R.E.5B.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-29 | 2026-04-16 | 0.45 | 0%
R.E.5B.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-29 | 2026-04-16 | 0.7 | 0%
R.E.6B.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-29 | 2026-04-16 | 0.8 | 0%
R.E.6B.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-29 | 2026-04-16 | 1.15 | 0%
R.E.VL.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-29 | 2026-04-16 | 1.25 | 0%
R.E.GE.EX.GE.SG.002 | Prepare and Submit Shop Drawings For Signage and Wayfinding | 0.54 | 2026-03-30 | 2026-04-14 | 1.65 | 0%
R.E.5B.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-03-30 | 2026-04-14 | 1.19 | 0%
R.E.VL.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.75 | 2026-03-30 | 2026-04-19 | 1.2 | 0%
R.E.6B.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-03-31 | 2026-04-15 | 1.58 | 0%
R.E.4B.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-02 | 2026-04-18 | 1.27 | 0%
R.E.4B.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-04-02 | 2026-04-22 | 2.05 | 0%
R.E.VL.LV.1F.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-02 | 2026-04-18 | 1.65 | 0%
R.E.4B.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-06 | 2026-04-21 | 1.38 | 0%
R.E.4B.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-06 | 2026-04-21 | 1.38 | 0%
R.E.GE.EX.GE.SO.002 | Prepare and Submit Shop Drawings For Soft Landscaping | 0.54 | 2026-04-06 | 2026-04-21 | 1.65 | 0%
R.E.5B.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-06 | 2026-04-21 | 1.27 | 0%
R.E.5B.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-06 | 2026-04-21 | 1.27 | 0%
R.E.5B.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-06 | 2026-04-26 | 1.3 | 0%
R.E.6B.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-06 | 2026-04-21 | 1.62 | 0%
R.E.6B.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-06 | 2026-04-21 | 1.62 | 0%
R.E.6B.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-06 | 2026-04-26 | 1.7 | 0%
R.E.VL.LV.1F.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-06 | 2026-04-21 | 1.69 | 0%
R.E.VL.LV.1F.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-06 | 2026-04-21 | 1.69 | 0%
R.E.VL.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-06 | 2026-04-26 | 1.8 | 0%
R.E.4B.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-07 | 2026-04-22 | 0.81 | 0%
R.E.5B.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-07 | 2026-04-22 | 0.42 | 0%
R.E.5B.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-07 | 2026-04-22 | 0.62 | 0%
R.E.4B.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-04-08 | 2026-04-28 | 2.05 | 0%
R.E.4B.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-04-08 | 2026-04-28 | 2.05 | 0%
R.E.4B.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-08 | 2026-04-28 | 1.4 | 0%
R.E.6B.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-09 | 2026-04-25 | 1.04 | 0%
R.E.VL.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-09 | 2026-04-25 | 1.08 | 0%
R.E.5B.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-11 | 2026-04-26 | 1.27 | 0%
R.E.VL.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-11 | 2026-04-26 | 1.69 | 0%
R.E.VL.EL.RF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-11 | 2026-04-26 | 1.08 | 0%
R.E.4B.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-04-13 | 2026-05-03 | 2.05 | 0%
R.E.6B.EL.GF.LI.002 | Prepare and Submit Shop Drawings For Lighting | 0.54 | 2026-04-13 | 2026-04-28 | 0.69 | 0%
R.E.GE.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.75 | 2026-04-15 | 2026-05-05 | 1.75 | 0%
R.E.5B.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-04-15 | 2026-05-05 | 1.3 | 0%
R.E.4B.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-16 | 2026-05-02 | 1.38 | 0%
R.E.5B.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-16 | 2026-05-02 | 0.81 | 0%
R.E.6B.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-04-16 | 2026-05-06 | 1.65 | 0%
R.E.4B.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-18 | 2026-05-03 | 0.85 | 0%
R.E.6B.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-18 | 2026-05-03 | 1.04 | 0%
R.E.4B.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-04-19 | 2026-05-07 | 1.35 | 0%
R.E.5B.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-19 | 2026-05-04 | 0.46 | 0%
R.E.VL.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-19 | 2026-05-04 | 1.12 | 0%
R.E.VL.LV.RF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-19 | 2026-05-04 | 1.12 | 0%
R.E.VL.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-04-19 | 2026-05-07 | 1.8 | 0%
R.E.5B.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-20 | 2026-05-05 | 0.81 | 0%
R.E.5B.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-20 | 2026-05-05 | 0.81 | 0%
R.E.6B.LV.GF.TN.002 | Prepare and Submit Shop Drawings For Telecom Network | 0.54 | 2026-04-21 | 2026-05-06 | 0.77 | 0%
R.E.6B.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-21 | 2026-05-06 | 1.12 | 0%
R.E.6B.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-21 | 2026-05-06 | 1.12 | 0%
R.E.4B.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-04-22 | 2026-05-12 | 1.45 | 0%
R.E.4B.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-04-22 | 2026-05-12 | 1.45 | 0%
R.E.GE.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.75 | 2026-04-22 | 2026-05-12 | 1.75 | 0%
R.E.5B.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-04-22 | 2026-05-12 | 1.35 | 0%
R.E.5B.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-04-22 | 2026-05-12 | 1.35 | 0%
R.E.6B.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-04-22 | 2026-05-12 | 1.7 | 0%
R.E.6B.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-04-22 | 2026-05-12 | 1.7 | 0%
R.E.VL.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-04-22 | 2026-05-12 | 1.8 | 0%
R.E.VL.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-04-22 | 2026-05-12 | 1.8 | 0%
R.E.4B.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-23 | 2026-05-09 | 0.85 | 0%
R.E.4B.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-23 | 2026-05-09 | 0.85 | 0%
R.E.4B.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-23 | 2026-05-13 | 0.85 | 0%
R.E.5B.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-23 | 2026-05-13 | 0.45 | 0%
R.E.5B.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-23 | 2026-05-13 | 0.65 | 0%
R.E.VL.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-23 | 2026-05-09 | 1.12 | 0%
R.E.VL.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-23 | 2026-05-09 | 1.12 | 0%
R.E.5B.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-25 | 2026-05-10 | 0.46 | 0%
R.E.5B.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-25 | 2026-05-10 | 0.46 | 0%
R.E.VL.LV.RF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-25 | 2026-05-10 | 1.08 | 0%
R.E.VL.LV.RF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-25 | 2026-05-10 | 1.08 | 0%
R.E.6B.LV.GF.FS.002 | Prepare and Submit Shop Drawings For Fire Alarm System | 0.54 | 2026-04-26 | 2026-05-11 | 0.77 | 0%
R.E.6B.LV.GF.SC.002 | Prepare and Submit Shop Drawings For Security | 0.54 | 2026-04-26 | 2026-05-11 | 0.77 | 0%
R.E.6B.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-26 | 2026-05-14 | 1.1 | 0%
R.E.VL.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-26 | 2026-05-14 | 1.15 | 0%
R.E.4B.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-27 | 2026-05-12 | 0.92 | 0%
R.E.5B.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-04-27 | 2026-05-17 | 1.35 | 0%
R.E.VL.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-27 | 2026-05-12 | 1.15 | 0%
R.E.VL.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-04-27 | 2026-05-17 | 1.8 | 0%
R.E.VL.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-27 | 2026-05-17 | 1.15 | 0%
R.E.5B.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-28 | 2026-05-13 | 0.5 | 0%
R.E.6B.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.75 | 2026-04-29 | 2026-05-19 | 0.75 | 0%
R.E.5B.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-04-30 | 2026-05-16 | 0.81 | 0%
R.E.6B.LV.GF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-05-02 | 2026-05-17 | 0.77 | 0%
R.E.4B.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-03 | 2026-05-21 | 1.5 | 0%
R.E.5B.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-03 | 2026-05-21 | 0.85 | 0%
R.E.VL.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-05-03 | 2026-05-18 | 1.12 | 0%
R.E.4B.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-04 | 2026-05-24 | 0.9 | 0%
R.E.6B.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-04 | 2026-05-24 | 1.1 | 0%
R.E.5B.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-05 | 2026-05-25 | 0.5 | 0%
R.E.6B.LV.1F.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-05-05 | 2026-05-20 | 0.77 | 0%
R.E.VL.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-05 | 2026-05-25 | 1.2 | 0%
R.E.VL.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-05 | 2026-05-25 | 1.2 | 0%
R.E.5B.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-06 | 2026-05-31 | 0.85 | 0%
R.E.5B.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-06 | 2026-05-31 | 0.85 | 0%
R.E.6B.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.75 | 2026-05-07 | 2026-06-01 | 0.8 | 0%
R.E.6B.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-07 | 2026-06-01 | 1.15 | 0%
R.E.6B.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-07 | 2026-06-01 | 1.15 | 0%
R.E.4B.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-10 | 2026-06-02 | 0.9 | 0%
R.E.4B.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-10 | 2026-06-02 | 0.9 | 0%
R.E.VL.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-10 | 2026-06-02 | 1.2 | 0%
R.E.VL.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-10 | 2026-06-02 | 1.2 | 0%
R.E.5B.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-11 | 2026-06-03 | 0.5 | 0%
R.E.5B.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-11 | 2026-06-03 | 0.5 | 0%
R.E.6B.LV.RF.IC.002 | Prepare and Submit Shop Drawings For ICT | 0.54 | 2026-05-11 | 2026-05-30 | 0.73 | 0%
R.E.VL.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-11 | 2026-06-03 | 1.15 | 0%
R.E.VL.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-11 | 2026-06-03 | 1.15 | 0%
R.E.6B.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.75 | 2026-05-12 | 2026-06-04 | 0.8 | 0%
R.E.6B.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.75 | 2026-05-12 | 2026-06-04 | 0.8 | 0%
R.E.4B.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-13 | 2026-06-07 | 0.95 | 0%
R.E.VL.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-13 | 2026-06-07 | 1.2 | 0%
R.E.5B.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-14 | 2026-06-08 | 0.5 | 0%
R.E.5B.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-17 | 2026-06-09 | 0.85 | 0%
R.E.6B.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-18 | 2026-06-10 | 0.8 | 0%
R.E.VL.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-19 | 2026-06-11 | 1.2 | 0%
R.E.6B.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-21 | 2026-06-15 | 0.8 | 0%
R.E.5B.AR.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-30 | 2026-06-14 | 1.42 | 0%
R.E.5B.AR.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-30 | 2026-06-14 | 1.42 | 0%
R.E.5B.AR.RF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-30 | 2026-06-14 | 1.42 | 0%
R.E.VL.AR.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-30 | 2026-06-14 | 1.42 | 0%
R.E.VL.AR.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-30 | 2026-06-14 | 1.42 | 0%
R.E.VL.AR.RF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-30 | 2026-06-14 | 1.42 | 0%
R.E.4B.AR.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-31 | 2026-06-15 | 1.38 | 0%
R.E.4B.AR.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-31 | 2026-06-15 | 1.38 | 0%
R.E.4B.AR.RF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-05-31 | 2026-06-15 | 1.38 | 0%
R.E.6B.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.75 | 2026-05-31 | 2026-06-18 | 0.8 | 0%
R.E.6B.AR.GF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-06-07 | 2026-06-22 | 1.15 | 0%
R.E.6B.AR.1F.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-06-07 | 2026-06-22 | 1.15 | 0%
R.E.6B.AR.RF.ID.002 | Prepare and Submit Shop Drawings For ID Details | 0.54 | 2026-06-07 | 2026-06-22 | 1.15 | 0%
R.E.5B.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-11 | 2026-06-27 | 1.42 | 0%
R.E.5B.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-11 | 2026-06-27 | 1.42 | 0%
R.E.5B.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-11 | 2026-06-27 | 1.42 | 0%
R.E.VL.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-11 | 2026-06-27 | 1.42 | 0%
R.E.VL.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-11 | 2026-06-27 | 1.42 | 0%
R.E.VL.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-11 | 2026-06-27 | 1.42 | 0%
R.E.4B.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-13 | 2026-06-28 | 1.38 | 0%
R.E.4B.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-13 | 2026-06-28 | 1.38 | 0%
R.E.4B.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-13 | 2026-06-28 | 1.38 | 0%
R.E.5B.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-15 | 2026-07-05 | 1.55 | 0%
R.E.5B.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-15 | 2026-07-05 | 1.55 | 0%
R.E.5B.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-15 | 2026-07-05 | 1.55 | 0%
R.E.VL.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-15 | 2026-07-05 | 1.55 | 0%
R.E.VL.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-15 | 2026-07-05 | 1.55 | 0%
R.E.VL.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-15 | 2026-07-05 | 1.55 | 0%
R.E.4B.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-16 | 2026-07-06 | 1.5 | 0%
R.E.4B.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-16 | 2026-07-06 | 1.5 | 0%
R.E.4B.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-16 | 2026-07-06 | 1.5 | 0%
R.E.6B.AR.GF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-20 | 2026-07-05 | 1.15 | 0%
R.E.6B.AR.1F.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-20 | 2026-07-05 | 1.15 | 0%
R.E.6B.AR.RF.SG.002 | Prepare and Submit Shop Drawings For Signage | 0.54 | 2026-06-20 | 2026-07-05 | 1.15 | 0%
R.E.6B.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-23 | 2026-07-13 | 1.25 | 0%
R.E.6B.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-23 | 2026-07-13 | 1.25 | 0%
R.E.6B.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.75 | 2026-06-23 | 2026-07-13 | 1.25 | 0%
R.E.5B.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-28 | 2026-07-16 | 1.55 | 0%
R.E.5B.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-28 | 2026-07-16 | 1.55 | 0%
R.E.5B.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-28 | 2026-07-16 | 1.55 | 0%
R.E.VL.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-28 | 2026-07-16 | 1.55 | 0%
R.E.VL.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-28 | 2026-07-16 | 1.55 | 0%
R.E.VL.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-28 | 2026-07-16 | 1.55 | 0%
R.E.4B.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-29 | 2026-07-19 | 1.5 | 0%
R.E.4B.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-29 | 2026-07-19 | 1.5 | 0%
R.E.4B.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-06-29 | 2026-07-19 | 1.5 | 0%
R.E.6B.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-07-06 | 2026-07-26 | 1.25 | 0%
R.E.6B.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-07-06 | 2026-07-26 | 1.25 | 0%
R.E.6B.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.75 | 2026-07-06 | 2026-07-26 | 1.25 | 0%

## Sheet6 (hidden)
838 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Drawing List | EL | Electrical | MEP | N/A | ElectricalN/A | General | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L
839 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Electrical Legends and Symbols | EL | Electrical | MEP | N/A | ElectricalN/A | General | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L
840 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Electrical General Notes & Abbreviations | EL | Electrical | MEP | N/A | ElectricalN/A | General | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L
841 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Electrical Naming Convention | EL | Electrical | MEP | N/A | ElectricalN/A | General | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L
844 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Maintenance Strategy - Basement | EL | Electrical | MEP | N/A | ElectricalN/A | Basement | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L
845 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Maintenance Strategy - Ground Floor | EL | Electrical | MEP | N/A | ElectricalN/A | Ground floor | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L
846 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Maintenance Strategy - Sections | EL | Electrical | MEP | N/A | ElectricalN/A | General | BUJ | V3 | 2025-09-30 08:00 | 2025-08-01 08:00 | TBS | L
847 | 0 | 'WS-WSH-687-0000-UBJ-SDW-EL-600-000000 | 0 | Maintenance Strategy - Substation Type-1 | EL | Electrical | MEP | N/A | ElectricalN/A | General | BUJ | V3 | 2025-05-24 08:00 | 2025-03-25 08:00 | TBS | L

## External (hidden)
Activity ID | Activity Name | Original Duration | BL Project Start | BL Project Finish | Start | Finish | Total Float | Nonlabor Units % Complete
F.E.Z4.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2024-12-22 | 2024-12-29 | 2024-12-22 | 2024-12-29 | 0 | 0%
F.E.Z4.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2024-12-30 | 2025-01-20 | 2024-12-30 | 2025-01-20 | 0 | 0%
F.E.Z5.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-01-04 | 2025-01-11 | 2025-01-04 | 2025-01-11 | 0 | 0%
F.E.Z3.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-01-07 | 2025-01-14 | 2025-01-07 | 2025-01-14 | 0 | 0%
F.E.Z4.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-01-07 | 2025-01-14 | 2025-01-07 | 2025-01-14 | 0.04 | 0%
F.E.Z4.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-01-07 | 2025-01-14 | 2025-01-07 | 2025-01-14 | 0.04 | 0%
F.E.Z5.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-01-12 | 2025-02-02 | 2025-01-12 | 2025-02-02 | 0 | 0%
F.E.Z3.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-01-15 | 2025-02-05 | 2025-01-15 | 2025-02-05 | 0 | 0%
F.E.Z4.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-01-15 | 2025-02-05 | 2025-01-15 | 2025-02-05 | 0.04 | 0%
F.E.Z4.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-01-15 | 2025-02-05 | 2025-01-15 | 2025-02-05 | 0.04 | 0%
F.E.Z4.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-01-18 | 2025-01-25 | 2025-01-18 | 2025-01-25 | 0.38 | 0%
F.E.Z5.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-01-18 | 2025-01-25 | 2025-01-18 | 2025-01-25 | 0.19 | 0%
F.E.Z5.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-01-18 | 2025-01-25 | 2025-01-18 | 2025-01-25 | 0.19 | 0%
F.E.Z4.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-01-26 | 2025-02-17 | 2025-01-26 | 2025-02-17 | 0.38 | 0%
F.E.Z5.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-01-26 | 2025-02-17 | 2025-01-26 | 2025-02-17 | 0.19 | 0%
F.E.Z5.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-01-26 | 2025-02-17 | 2025-01-26 | 2025-02-17 | 0.19 | 0%
F.E.Z4.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-01-27 | 2025-02-03 | 2025-01-27 | 2025-02-03 | 0.46 | 0%
F.E.Z4.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-01-27 | 2025-02-03 | 2025-01-27 | 2025-02-03 | 0.46 | 0%
F.E.Z4.ST.LG.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-01-27 | 2025-02-03 | 2025-01-27 | 2025-02-03 | 0.46 | 0%
F.M.ENG.TC.1 | Prepare and Submit Calculation Sheet for Tower Cranes | 0.27 | 2025-01-30 | 2025-02-06 | 2025-01-30 | 2025-02-06 | 16.92 | 0%
F.E.Z3.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-02-01 | 2025-02-08 | 2025-02-01 | 2025-02-08 | 0 | 0%
F.E.Z3.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-02-01 | 2025-02-08 | 2025-02-01 | 2025-02-08 | 0 | 0%
F.E.Z4.ST.LG.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-02-01 | 2025-02-08 | 2025-02-01 | 2025-02-08 | 0.31 | 0%
F.E.Z4.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-02-04 | 2025-02-26 | 2025-02-04 | 2025-02-26 | 0.46 | 0%
F.E.Z4.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-02-04 | 2025-02-26 | 2025-02-04 | 2025-02-26 | 0.46 | 0%
F.E.Z4.ST.LG.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-02-04 | 2025-02-26 | 2025-02-04 | 2025-02-26 | 0.46 | 0%
F.M.ENG.TC.2 | Review and Approve Calculation Sheet for Tower Cranes | 0.73 | 2025-02-08 | 2025-03-02 | 2025-02-08 | 2025-03-02 | 16.92 | 0%
F.E.Z3.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-02-09 | 2025-03-03 | 2025-02-09 | 2025-03-03 | 0 | 0%
F.E.Z3.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-02-09 | 2025-03-03 | 2025-02-09 | 2025-03-03 | 0 | 0%
F.E.Z4.ST.LG.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-02-09 | 2025-03-03 | 2025-02-09 | 2025-03-03 | 0.31 | 0%
F.E.Z3.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-02-16 | 2025-02-23 | 2025-02-16 | 2025-02-23 | 0.62 | 0%
F.E.Z4.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-02-16 | 2025-02-23 | 2025-02-16 | 2025-02-23 | 0.65 | 0%
F.E.Z3.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-02-22 | 2025-03-01 | 2025-02-22 | 2025-03-01 | 1.27 | 0%
F.E.Z3.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-02-22 | 2025-03-01 | 2025-02-22 | 2025-03-01 | 1.27 | 0%
F.E.Z3.ST.BF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-02-22 | 2025-03-01 | 2025-02-22 | 2025-03-01 | 1.27 | 0%
F.E.Z3.ST.BF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-02-24 | 2025-03-03 | 2025-02-24 | 2025-03-03 | 1.19 | 0%
F.E.Z3.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-02-24 | 2025-03-17 | 2025-02-24 | 2025-03-17 | 0.62 | 0%
F.E.Z4.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-02-24 | 2025-03-03 | 2025-02-24 | 2025-03-03 | 0.38 | 0%
F.E.Z4.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-02-24 | 2025-03-17 | 2025-02-24 | 2025-03-17 | 0.65 | 0%
F.E.Z5.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-03-01 | 2025-03-08 | 2025-03-01 | 2025-03-08 | 0.85 | 0%
F.E.Z6.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-03-01 | 2025-03-08 | 2025-03-01 | 2025-03-08 | 0.88 | 0%
F.E.Z3.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-03-02 | 2025-03-23 | 2025-03-02 | 2025-03-23 | 1.27 | 0%
F.E.Z3.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-03-02 | 2025-03-23 | 2025-03-02 | 2025-03-23 | 1.27 | 0%
F.E.Z3.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-03-02 | 2025-03-23 | 2025-03-02 | 2025-03-23 | 1.27 | 0%
F.E.Z3.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-03-04 | 2025-03-25 | 2025-03-04 | 2025-03-25 | 1.19 | 0%
F.E.Z4.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-03-04 | 2025-03-25 | 2025-03-04 | 2025-03-25 | 0.38 | 0%
F.E.Z4.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-03-09 | 2025-03-16 | 2025-03-09 | 2025-03-16 | 0.77 | 0%
F.E.Z5.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-03-09 | 2025-04-03 | 2025-03-09 | 2025-04-03 | 0.85 | 0%
F.E.Z6.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-03-09 | 2025-04-03 | 2025-03-09 | 2025-04-03 | 0.88 | 0%
F.E.Z4.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-03-11 | 2025-03-18 | 2025-03-11 | 2025-03-18 | 0.69 | 0%
F.E.Z5.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-03-12 | 2025-03-19 | 2025-03-12 | 2025-03-19 | 0.92 | 0%
F.E.Z5.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-03-12 | 2025-03-19 | 2025-03-12 | 2025-03-19 | 0.92 | 0%
F.E.Z5.ST.LG.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-03-12 | 2025-03-19 | 2025-03-12 | 2025-03-19 | 0.92 | 0%
F.E.Z5.ST.LG.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-03-15 | 2025-03-22 | 2025-03-15 | 2025-03-22 | 0.85 | 0%
F.E.Z4.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-03-17 | 2025-04-12 | 2025-03-17 | 2025-04-12 | 0.77 | 0%
F.E.Z4.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-03-19 | 2025-04-14 | 2025-03-19 | 2025-04-14 | 0.69 | 0%
F.E.Z1.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-03-20 | 2025-03-27 | 2025-03-20 | 2025-03-27 | 2.23 | 0%
F.E.Z5.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-03-20 | 2025-04-15 | 2025-03-20 | 2025-04-15 | 0.92 | 0%
F.E.Z5.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-03-20 | 2025-04-15 | 2025-03-20 | 2025-04-15 | 0.92 | 0%
F.E.Z5.ST.LG.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-03-20 | 2025-04-15 | 2025-03-20 | 2025-04-15 | 0.92 | 0%
F.E.Z3.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-03-22 | 2025-03-29 | 2025-03-22 | 2025-03-29 | 1.31 | 0%
F.E.Z3.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-03-22 | 2025-03-29 | 2025-03-22 | 2025-03-29 | 1.31 | 0%
F.E.Z5.ST.LG.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-03-23 | 2025-04-17 | 2025-03-23 | 2025-04-17 | 0.85 | 0%
F.E.Z6.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-03-24 | 2025-04-05 | 2025-03-24 | 2025-04-05 | 0.92 | 0%
F.E.Z6.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-03-26 | 2025-04-07 | 2025-03-26 | 2025-04-07 | 0.85 | 0%
F.E.Z1.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-03-29 | 2025-04-23 | 2025-03-29 | 2025-04-23 | 2.23 | 0%
F.E.Z3.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-04-03 | 2025-04-24 | 2025-04-03 | 2025-04-24 | 1.31 | 0%
F.E.Z3.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-04-03 | 2025-04-24 | 2025-04-03 | 2025-04-24 | 1.31 | 0%
F.E.Z4.ST.2F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-04-03 | 2025-04-10 | 2025-04-03 | 2025-04-10 | 0.88 | 0%
F.E.Z4.ST.2F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-04-03 | 2025-04-10 | 2025-04-03 | 2025-04-10 | 0.88 | 0%
F.E.Z7.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-04-03 | 2025-04-10 | 2025-04-03 | 2025-04-10 | 1.77 | 0%
F.E.Z6.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-04-06 | 2025-04-27 | 2025-04-06 | 2025-04-27 | 0.92 | 0%
F.E.Z5.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-04-07 | 2025-04-14 | 2025-04-07 | 2025-04-14 | 1.12 | 0%
F.E.Z6.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-04-08 | 2025-04-29 | 2025-04-08 | 2025-04-29 | 0.85 | 0%
F.E.Z5.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-04-10 | 2025-04-17 | 2025-04-10 | 2025-04-17 | 1 | 0%
F.E.Z4.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-04-12 | 2025-05-03 | 2025-04-12 | 2025-05-03 | 0.88 | 0%
F.E.Z4.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-04-12 | 2025-05-03 | 2025-04-12 | 2025-05-03 | 0.88 | 0%
F.E.Z7.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-04-12 | 2025-05-03 | 2025-04-12 | 2025-05-03 | 1.77 | 0%
F.E.Z5.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-04-15 | 2025-05-06 | 2025-04-15 | 2025-05-06 | 1.12 | 0%
F.E.Z3.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-04-16 | 2025-04-23 | 2025-04-16 | 2025-04-23 | 1.58 | 0%
F.E.Z3.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-04-19 | 2025-04-26 | 2025-04-19 | 2025-04-26 | 1.5 | 0%
F.E.Z5.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-04-19 | 2025-05-10 | 2025-04-19 | 2025-05-10 | 1 | 0%
F.E.Z6.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-04-19 | 2025-04-26 | 2025-04-19 | 2025-04-26 | 1.15 | 0%
F.E.Z3.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 3.31 | 0%
F.E.Z3.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 6.15 | 0%
F.E.Z3.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 3.31 | 0%
F.E.Z3.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-04-24 | 2025-05-15 | 2025-04-24 | 2025-05-15 | 1.58 | 0%
F.E.Z4.AR.LG.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 5.77 | 0%
F.E.Z4.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 1.31 | 0%
F.E.Z4.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 1.31 | 0%
F.E.Z4.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 5.23 | 0%
F.E.Z4.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 2.23 | 0%
F.E.Z4.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 7.12 | 0%
F.E.Z4.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 2.23 | 0%
F.E.Z4.AR.2F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-04-24 | 2025-05-01 | 2025-04-24 | 2025-05-01 | 6.85 | 0%
F.E.Z3.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-04-27 | 2025-05-18 | 2025-04-27 | 2025-05-18 | 1.5 | 0%
F.E.Z6.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-04-27 | 2025-05-18 | 2025-04-27 | 2025-05-18 | 1.15 | 0%
F.E.Z4.AR.LG.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-04-28 | 2025-05-05 | 2025-04-28 | 2025-05-05 | 5.65 | 0%
F.E.Z5.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-04-28 | 2025-05-05 | 2025-04-28 | 2025-05-05 | 1.81 | 0%
F.E.Z4.AR.2F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-04-29 | 2025-05-06 | 2025-04-29 | 2025-05-06 | 2.96 | 0%
F.E.Z4.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-04-30 | 2025-05-07 | 2025-04-30 | 2025-05-07 | 0.81 | 0%
F.E.Z4.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-05-01 | 2025-05-08 | 2025-05-01 | 2025-05-08 | 0.77 | 0%
F.E.Z3.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 3.31 | 0%
F.E.Z3.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 6.15 | 0%
F.E.Z3.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 3.31 | 0%
F.E.Z4.AR.LG.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 5.77 | 0%
F.E.Z4.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 1.31 | 0%
F.E.Z4.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 1.31 | 0%
F.E.Z4.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 5.23 | 0%
F.E.Z4.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 2.23 | 0%
F.E.Z4.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 7.12 | 0%
F.E.Z4.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 2.23 | 0%
F.E.Z4.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-05-03 | 2025-05-24 | 2025-05-03 | 2025-05-24 | 6.85 | 0%
F.E.Z5.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-05-03 | 2025-05-10 | 2025-05-03 | 2025-05-10 | 1.65 | 0%
F.E.Z4.HV.LG.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-05-04 | 2025-05-11 | 2025-05-04 | 2025-05-11 | 5.92 | 0%
F.E.Z5.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-05-04 | 2025-05-11 | 2025-05-04 | 2025-05-11 | 1.04 | 0%
F.E.Z3.AR.BF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-05-05 | 2025-05-12 | 2025-05-05 | 2025-05-12 | 14.04 | 0%
F.E.Z4.AR.LG.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-06 | 2025-05-27 | 2025-05-06 | 2025-05-27 | 5.65 | 0%
F.E.Z5.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-05-06 | 2025-05-13 | 2025-05-06 | 2025-05-13 | 0.96 | 0%
F.E.Z5.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-06 | 2025-05-27 | 2025-05-06 | 2025-05-27 | 1.81 | 0%
F.E.Z1.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-05-07 | 2025-05-14 | 2025-05-07 | 2025-05-14 | 1.5 | 0%
F.E.Z4.HV.1F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-05-07 | 2025-05-14 | 2025-05-07 | 2025-05-14 | 4.42 | 0%
F.E.Z4.AR.2F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-05-07 | 2025-05-14 | 2025-05-07 | 2025-05-14 | 2.69 | 0%
F.E.Z4.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-07 | 2025-05-28 | 2025-05-07 | 2025-05-28 | 2.96 | 0%
F.E.Z8.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-05-07 | 2025-05-14 | 2025-05-07 | 2025-05-14 | 2.15 | 0%
F.E.Z4.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-05-08 | 2025-05-29 | 2025-05-08 | 2025-05-29 | 0.81 | 0%
F.E.Z4.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-05-10 | 2025-05-31 | 2025-05-10 | 2025-05-31 | 0.77 | 0%
F.E.Z4.AR.LG.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-05-11 | 2025-05-18 | 2025-05-11 | 2025-05-18 | 6.81 | 0%
F.E.Z4.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-05-11 | 2025-05-18 | 2025-05-11 | 2025-05-18 | 5.81 | 0%
F.E.Z5.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-11 | 2025-06-01 | 2025-05-11 | 2025-06-01 | 1.65 | 0%
F.E.Z3.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-05-12 | 2025-05-19 | 2025-05-12 | 2025-05-19 | 5.12 | 0%
F.E.Z4.HV.LG.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-05-12 | 2025-06-02 | 2025-05-12 | 2025-06-02 | 5.92 | 0%
F.E.Z5.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-05-12 | 2025-06-02 | 2025-05-12 | 2025-06-02 | 1.04 | 0%
F.E.Z3.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-05-13 | 2025-06-03 | 2025-05-13 | 2025-06-03 | 14.04 | 0%
F.E.Z6.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-05-13 | 2025-05-20 | 2025-05-13 | 2025-05-20 | 1.19 | 0%
F.E.Z1.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-05-14 | 2025-05-21 | 2025-05-14 | 2025-05-21 | 1.27 | 0%
F.E.Z3.ST.2F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-05-14 | 2025-05-21 | 2025-05-14 | 2025-05-21 | 1.62 | 0%
F.E.Z3.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-05-14 | 2025-05-21 | 2025-05-14 | 2025-05-21 | 3.46 | 0%
F.E.Z3.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-05-14 | 2025-05-21 | 2025-05-14 | 2025-05-21 | 3.46 | 0%
F.E.Z4.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-05-14 | 2025-05-21 | 2025-05-14 | 2025-05-21 | 6.38 | 0%
F.E.Z5.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-05-14 | 2025-06-04 | 2025-05-14 | 2025-06-04 | 0.96 | 0%
F.E.Z1.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-05-15 | 2025-06-09 | 2025-05-15 | 2025-06-09 | 1.5 | 0%
F.E.Z3.ST.2F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-05-15 | 2025-05-22 | 2025-05-15 | 2025-05-22 | 1.58 | 0%
F.E.Z4.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-05-15 | 2025-06-09 | 2025-05-15 | 2025-06-09 | 4.42 | 0%
F.E.Z4.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-15 | 2025-06-09 | 2025-05-15 | 2025-06-09 | 2.69 | 0%
F.E.Z6.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-05-15 | 2025-05-22 | 2025-05-15 | 2025-05-22 | 1.12 | 0%
F.E.Z7.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-05-15 | 2025-05-22 | 2025-05-15 | 2025-05-22 | 1 | 0%
F.E.Z8.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-05-15 | 2025-06-09 | 2025-05-15 | 2025-06-09 | 2.15 | 0%
F.E.Z7.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-05-17 | 2025-05-24 | 2025-05-17 | 2025-05-24 | 0.96 | 0%
F.E.Z3.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-05-19 | 2025-05-26 | 2025-05-19 | 2025-05-26 | 5.5 | 0%
F.E.Z4.AR.LG.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-05-19 | 2025-06-12 | 2025-05-19 | 2025-06-12 | 6.81 | 0%
F.E.Z4.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-05-19 | 2025-06-12 | 2025-05-19 | 2025-06-12 | 5.81 | 0%
F.E.Z3.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-05-20 | 2025-06-14 | 2025-05-20 | 2025-06-14 | 5.12 | 0%
F.E.Z4.HV.2F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-05-21 | 2025-05-28 | 2025-05-21 | 2025-05-28 | 4.38 | 0%
F.E.Z6.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-05-21 | 2025-06-15 | 2025-05-21 | 2025-06-15 | 1.19 | 0%
F.E.Z1.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-05-22 | 2025-06-16 | 2025-05-22 | 2025-06-16 | 1.27 | 0%
F.E.Z3.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-05-22 | 2025-06-16 | 2025-05-22 | 2025-06-16 | 1.62 | 0%
F.E.Z3.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-05-22 | 2025-06-16 | 2025-05-22 | 2025-06-16 | 3.46 | 0%
F.E.Z3.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-05-22 | 2025-06-16 | 2025-05-22 | 2025-06-16 | 3.46 | 0%
F.E.Z4.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-05-22 | 2025-06-16 | 2025-05-22 | 2025-06-16 | 6.38 | 0%
F.E.Z6.ST.BF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-05-22 | 2025-05-29 | 2025-05-22 | 2025-05-29 | 0.88 | 0%
F.E.Z3.AR.1F.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-05-24 | 2025-05-31 | 2025-05-24 | 2025-05-31 | 5.35 | 0%
F.E.Z3.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-05-24 | 2025-06-17 | 2025-05-24 | 2025-06-17 | 1.58 | 0%
F.E.Z5.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-05-24 | 2025-05-31 | 2025-05-24 | 2025-05-31 | 5.92 | 0%
F.E.Z5.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-05-24 | 2025-05-31 | 2025-05-24 | 2025-05-31 | 6.58 | 0%
F.E.Z6.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-05-24 | 2025-06-17 | 2025-05-24 | 2025-06-17 | 1.12 | 0%
F.E.Z7.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-05-24 | 2025-06-17 | 2025-05-24 | 2025-06-17 | 1 | 0%
F.E.Z5.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-05-25 | 2025-06-01 | 2025-05-25 | 2025-06-01 | 1.85 | 0%
F.E.Z6.ST.BF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-05-25 | 2025-06-01 | 2025-05-25 | 2025-06-01 | 0.81 | 0%
F.E.Z7.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-05-25 | 2025-06-18 | 2025-05-25 | 2025-06-18 | 0.96 | 0%
F.E.Z8.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-05-25 | 2025-06-01 | 2025-05-25 | 2025-06-01 | 2.27 | 0%
F.E.Z8.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-05-25 | 2025-06-01 | 2025-05-25 | 2025-06-01 | 2.27 | 0%
F.E.Z5.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-05-26 | 2025-06-02 | 2025-05-26 | 2025-06-02 | 1.81 | 0%
F.E.Z3.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.54 | 0%
F.E.Z3.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.54 | 0%
F.E.Z3.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.42 | 0%
F.E.Z3.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.54 | 0%
F.E.Z3.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.54 | 0%
F.E.Z3.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.42 | 0%
F.E.Z3.AR.2F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 6.69 | 0%
F.E.Z3.PL.2F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 6.15 | 0%
F.E.Z3.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-05-27 | 2025-06-21 | 2025-05-27 | 2025-06-21 | 5.5 | 0%
F.E.Z4.PL.LG.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 5.27 | 0%
F.E.Z4.DR.LG.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 5.31 | 0%
F.E.Z4.EL.LG.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 5.15 | 0%
F.E.Z4.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.19 | 0%
F.E.Z4.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.19 | 0%
F.E.Z4.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 3.88 | 0%
F.E.Z4.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 3.92 | 0%
F.E.Z4.PL.2F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.19 | 0%
F.E.Z4.DR.2F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.19 | 0%
F.E.Z4.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.73 | 0%
F.E.Z5.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.42 | 0%
F.E.Z5.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-05-27 | 2025-06-03 | 2025-05-27 | 2025-06-03 | 4.38 | 0%
R.E.4B.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.04 | 0%
R.E.4B.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.62 | 0%
R.E.4B.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.62 | 0%
F.E.Z4.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 2.85 | 0%
F.E.Z5.ST.2F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.04 | 0%
R.E.5B.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.04 | 0%
R.E.5B.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.73 | 0%
R.E.5B.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.73 | 0%
R.E.6B.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.04 | 0%
R.E.6B.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.62 | 0%
R.E.6B.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 1.62 | 0%
R.E.GE.EX.CU.IR.002 | Submission of Shop Drawings For Leveling Works | 0.27 | 2025-05-28 | 2025-06-04 | 2025-05-28 | 2025-06-04 | 0 | 0%
F.E.Z4.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-05-29 | 2025-06-09 | 2025-05-29 | 2025-06-09 | 4.08 | 0%
F.E.Z4.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-05-29 | 2025-06-23 | 2025-05-29 | 2025-06-23 | 4.38 | 0%
F.E.Z5.ST.2F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-05-29 | 2025-06-09 | 2025-05-29 | 2025-06-09 | 1 | 0%
F.E.Z5.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-05-29 | 2025-06-09 | 2025-05-29 | 2025-06-09 | 4.35 | 0%
F.E.Z4.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-05-31 | 2025-06-10 | 2025-05-31 | 2025-06-10 | 2.77 | 0%
F.E.Z6.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-05-31 | 2025-06-24 | 2025-05-31 | 2025-06-24 | 0.88 | 0%
F.E.Z3.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-06-01 | 2025-06-25 | 2025-06-01 | 2025-06-25 | 5.35 | 0%
F.E.Z5.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-06-01 | 2025-06-25 | 2025-06-01 | 2025-06-25 | 5.92 | 0%
F.E.Z5.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-06-01 | 2025-06-25 | 2025-06-01 | 2025-06-25 | 6.58 | 0%
F.E.Z1.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-06-02 | 2025-06-12 | 2025-06-02 | 2025-06-12 | 1.77 | 0%
F.E.Z3.AR.GF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-06-02 | 2025-06-12 | 2025-06-02 | 2025-06-12 | 5.27 | 0%
F.E.Z5.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-06-02 | 2025-06-26 | 2025-06-02 | 2025-06-26 | 1.85 | 0%
F.E.Z6.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-06-02 | 2025-06-26 | 2025-06-02 | 2025-06-26 | 0.81 | 0%
F.E.Z8.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-06-02 | 2025-06-26 | 2025-06-02 | 2025-06-26 | 2.27 | 0%
F.E.Z8.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-06-02 | 2025-06-26 | 2025-06-02 | 2025-06-26 | 2.27 | 0%
F.E.Z5.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-06-03 | 2025-06-28 | 2025-06-03 | 2025-06-28 | 1.81 | 0%
F.E.Z3.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.54 | 0%
F.E.Z3.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.54 | 0%
F.E.Z3.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.42 | 0%
F.E.Z3.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.54 | 0%
F.E.Z3.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.54 | 0%
F.E.Z3.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.42 | 0%
F.E.Z3.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 6.69 | 0%
F.E.Z3.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 6.15 | 0%
F.E.Z4.PL.LG.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 5.27 | 0%
F.E.Z4.DR.LG.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 5.31 | 0%
F.E.Z4.EL.LG.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 5.15 | 0%
F.E.Z4.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.19 | 0%
F.E.Z4.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.19 | 0%
F.E.Z4.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 3.88 | 0%
F.E.Z4.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 3.92 | 0%
F.E.Z4.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.19 | 0%
F.E.Z4.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.19 | 0%
F.E.Z4.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.73 | 0%
F.E.Z5.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.42 | 0%
F.E.Z5.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 4.38 | 0%
R.E.4B.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.04 | 0%
R.E.4B.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.62 | 0%
R.E.4B.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.62 | 0%
F.E.Z3.HV.1F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 4.31 | 0%
F.E.Z3.AR.2F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 3.54 | 0%
F.E.Z3.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 5.38 | 0%
F.E.Z4.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 5.77 | 0%
F.E.Z4.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 3.85 | 0%
F.E.Z4.EL.2F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 5.46 | 0%
F.E.Z4.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-06-09 | 2025-06-16 | 2025-06-09 | 2025-06-16 | 4.42 | 0%
F.E.Z4.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 2.85 | 0%
F.E.Z5.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.04 | 0%
R.E.5B.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.04 | 0%
R.E.5B.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.73 | 0%
R.E.5B.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.73 | 0%
R.E.6B.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.04 | 0%
R.E.6B.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.62 | 0%
R.E.6B.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 1.62 | 0%
R.E.GE.EX.GE.CU.004 | Review and Approve Shop Drawings For Leveling Works | 0.73 | 2025-06-09 | 2025-06-30 | 2025-06-09 | 2025-06-30 | 0 | 0%
F.E.Z2.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-06-10 | 2025-06-17 | 2025-06-10 | 2025-06-17 | 2.27 | 0%
F.E.Z4.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-10 | 2025-07-01 | 2025-06-10 | 2025-07-01 | 4.08 | 0%
F.E.Z5.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-10 | 2025-06-17 | 2025-06-10 | 2025-06-17 | 4.04 | 0%
F.E.Z5.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-06-10 | 2025-06-17 | 2025-06-10 | 2025-06-17 | 4.38 | 0%
F.E.Z5.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-06-10 | 2025-07-01 | 2025-06-10 | 2025-07-01 | 1 | 0%
F.E.Z5.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-10 | 2025-07-01 | 2025-06-10 | 2025-07-01 | 4.35 | 0%
F.E.Z7.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-06-10 | 2025-06-17 | 2025-06-10 | 2025-06-17 | 1.35 | 0%
R.E.4B.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-06-11 | 2025-06-18 | 2025-06-11 | 2025-06-18 | 2.04 | 0%
F.E.Z3.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-06-11 | 2025-06-18 | 2025-06-11 | 2025-06-18 | 4.69 | 0%
F.E.Z4.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-06-11 | 2025-07-02 | 2025-06-11 | 2025-07-02 | 2.77 | 0%
R.E.6B.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-06-11 | 2025-06-18 | 2025-06-11 | 2025-06-18 | 2.04 | 0%
F.E.Z3.PL.BF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-06-12 | 2025-06-19 | 2025-06-12 | 2025-06-19 | 5.58 | 0%
F.E.Z3.AR.1F.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-06-12 | 2025-06-19 | 2025-06-12 | 2025-06-19 | 5.04 | 0%
F.E.Z3.DR.2F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-06-12 | 2025-06-19 | 2025-06-12 | 2025-06-19 | 5.73 | 0%
F.E.Z4.FF.2F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-06-12 | 2025-06-19 | 2025-06-12 | 2025-06-19 | 5.35 | 0%
F.E.Z4.HV.RF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-06-12 | 2025-06-19 | 2025-06-12 | 2025-06-19 | 4.31 | 0%
F.E.Z4.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-12 | 2025-06-19 | 2025-06-12 | 2025-06-19 | 5.65 | 0%
F.E.Z1.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-06-14 | 2025-07-05 | 2025-06-14 | 2025-07-05 | 1.77 | 0%
F.E.Z3.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-06-14 | 2025-07-05 | 2025-06-14 | 2025-07-05 | 5.27 | 0%
F.E.Z3.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-06-15 | 2025-06-22 | 2025-06-15 | 2025-06-22 | 1.65 | 0%
F.E.Z3.AR.2F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-06-15 | 2025-06-22 | 2025-06-15 | 2025-06-22 | 3.35 | 0%
F.E.Z3.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-06-16 | 2025-06-23 | 2025-06-16 | 2025-06-23 | 1.62 | 0%
F.E.Z3.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-06-17 | 2025-06-24 | 2025-06-17 | 2025-06-24 | 4.65 | 0%
F.E.Z3.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-06-17 | 2025-06-24 | 2025-06-17 | 2025-06-24 | 4.65 | 0%
F.E.Z3.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 4.31 | 0%
F.E.Z3.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 3.54 | 0%
F.E.Z3.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 5.38 | 0%
F.E.Z4.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-06-17 | 2025-06-24 | 2025-06-17 | 2025-06-24 | 5.46 | 0%
F.E.Z4.HV.2F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-06-17 | 2025-06-24 | 2025-06-17 | 2025-06-24 | 5.19 | 0%
F.E.Z4.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 5.77 | 0%
F.E.Z4.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 3.85 | 0%
F.E.Z4.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 5.46 | 0%
F.E.Z4.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-17 | 2025-07-08 | 2025-06-17 | 2025-07-08 | 4.42 | 0%
F.E.Z5.AR.2F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-06-17 | 2025-06-24 | 2025-06-17 | 2025-06-24 | 6.04 | 0%
R.E.5B.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-06-17 | 2025-06-24 | 2025-06-17 | 2025-06-24 | 2.04 | 0%
F.E.Z2.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-06-18 | 2025-07-09 | 2025-06-18 | 2025-07-09 | 2.27 | 0%
F.E.Z5.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-18 | 2025-07-09 | 2025-06-18 | 2025-07-09 | 4.04 | 0%
F.E.Z5.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-18 | 2025-07-09 | 2025-06-18 | 2025-07-09 | 4.38 | 0%
F.E.Z7.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-06-18 | 2025-07-09 | 2025-06-18 | 2025-07-09 | 1.35 | 0%
R.E.4B.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-06-19 | 2025-07-10 | 2025-06-19 | 2025-07-10 | 2.04 | 0%
F.E.Z3.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-06-26 | 4.42 | 0%
F.E.Z3.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-06-26 | 5.58 | 0%
F.E.Z3.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-06-19 | 2025-07-10 | 2025-06-19 | 2025-07-10 | 4.69 | 0%
F.E.Z5.AR.2F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-06-19 | 2025-06-26 | 2025-06-19 | 2025-06-26 | 2.04 | 0%
R.E.6B.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-06-19 | 2025-07-10 | 2025-06-19 | 2025-07-10 | 2.04 | 0%
F.E.Z3.AR.1F.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-06-21 | 2025-06-28 | 2025-06-21 | 2025-06-28 | 4.38 | 0%
F.E.Z3.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-06-21 | 2025-07-12 | 2025-06-21 | 2025-07-12 | 5.58 | 0%
F.E.Z3.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-06-21 | 2025-07-12 | 2025-06-21 | 2025-07-12 | 5.04 | 0%
F.E.Z3.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-21 | 2025-07-12 | 2025-06-21 | 2025-07-12 | 5.73 | 0%
F.E.Z4.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-06-21 | 2025-07-12 | 2025-06-21 | 2025-07-12 | 5.35 | 0%
F.E.Z4.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-06-21 | 2025-07-12 | 2025-06-21 | 2025-07-12 | 4.31 | 0%
F.E.Z4.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-21 | 2025-07-12 | 2025-06-21 | 2025-07-12 | 5.65 | 0%
F.E.Z5.AR.2F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-06-21 | 2025-06-28 | 2025-06-21 | 2025-06-28 | 2 | 0%
F.E.Z8.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-06-21 | 2025-06-28 | 2025-06-21 | 2025-06-28 | 2.54 | 0%
F.E.Z3.EL.BF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-22 | 2025-06-29 | 2025-06-22 | 2025-06-29 | 5.15 | 0%
F.E.Z3.EL.2F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-22 | 2025-06-29 | 2025-06-22 | 2025-06-29 | 5.96 | 0%
F.E.Z5.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-06-22 | 2025-06-29 | 2025-06-22 | 2025-06-29 | 4.04 | 0%
F.E.Z9.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-06-22 | 2025-06-29 | 2025-06-22 | 2025-06-29 | 2.31 | 0%
F.E.Z3.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-06-23 | 2025-07-14 | 2025-06-23 | 2025-07-14 | 1.65 | 0%
F.E.Z3.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-06-23 | 2025-07-14 | 2025-06-23 | 2025-07-14 | 3.35 | 0%
F.E.Z5.F2.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.08 | 0%
F.E.Z5.F2.GF.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.5 | 0%
F.E.Z5.F2.1F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.73 | 0%
F.E.Z5.F2.1F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 6.15 | 0%
F.E.Z5.HV.1F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 3.85 | 0%
F.E.Z4.F2.LG.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.5 | 0%
F.E.Z4.F2.LG.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.54 | 0%
F.E.Z4.F2.LG.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.96 | 0%
F.E.Z4.F2.GF.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 4.54 | 0%
F.E.Z4.F2.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 4.54 | 0%
F.E.Z4.F2.GF.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.08 | 0%
F.E.Z4.F2.1F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 3.88 | 0%
F.E.Z4.F2.1F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.31 | 0%
F.E.Z4.F2.1F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.73 | 0%
F.E.Z4.F2.2F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 4.35 | 0%
F.E.Z4.F2.2F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.19 | 0%
F.E.Z4.F2.2F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | 5.46 | 0%
F.E.Z3.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-06-24 | 2025-07-01 | 2025-06-24 | 2025-07-01 | 4.27 | 0%
F.E.Z3.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-06-24 | 2025-07-01 | 2025-06-24 | 2025-07-01 | 4.27 | 0%
F.E.Z3.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-06-24 | 2025-07-15 | 2025-06-24 | 2025-07-15 | 1.62 | 0%
R.E.4B.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
R.E.4B.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
R.E.4B.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
R.E.4B.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
F.E.Z3.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-06-25 | 2025-07-16 | 2025-06-25 | 2025-07-16 | 4.65 | 0%
F.E.Z3.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-06-25 | 2025-07-16 | 2025-06-25 | 2025-07-16 | 4.65 | 0%
F.E.Z4.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-06-25 | 2025-07-16 | 2025-06-25 | 2025-07-16 | 5.46 | 0%
F.E.Z4.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-06-25 | 2025-07-16 | 2025-06-25 | 2025-07-16 | 5.19 | 0%
F.E.Z5.ST.3F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 1.04 | 0%
F.E.Z5.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 3.54 | 0%
F.E.Z5.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-06-25 | 2025-07-16 | 2025-06-25 | 2025-07-16 | 6.04 | 0%
F.E.Z6.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 0.96 | 0%
R.E.5B.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-06-25 | 2025-07-16 | 2025-06-25 | 2025-07-16 | 2.04 | 0%
R.E.6B.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
R.E.6B.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
R.E.6B.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
R.E.6B.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-06-25 | 2025-07-02 | 2025-06-25 | 2025-07-02 | 2.04 | 0%
F.E.Z2.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-06-26 | 2025-07-03 | 2025-06-26 | 2025-07-03 | 2.35 | 0%
F.E.Z2.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-06-26 | 2025-07-03 | 2025-06-26 | 2025-07-03 | 2.35 | 0%
F.E.Z5.ST.3F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-06-26 | 2025-07-03 | 2025-06-26 | 2025-07-03 | 1 | 0%
F.E.Z6.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-06-26 | 2025-07-03 | 2025-06-26 | 2025-07-03 | 4.77 | 0%
F.E.Z3.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-06-28 | 2025-07-19 | 2025-06-28 | 2025-07-19 | 4.42 | 0%
F.E.Z3.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-06-28 | 2025-07-19 | 2025-06-28 | 2025-07-19 | 5.58 | 0%
F.E.Z5.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-06-28 | 2025-07-19 | 2025-06-28 | 2025-07-19 | 2.04 | 0%
F.E.Z5.F2.LG.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-06-28 | 2025-07-05 | 2025-06-28 | 2025-07-05 | 5.38 | 0%
F.E.Z3.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-06-29 | 2025-07-20 | 2025-06-29 | 2025-07-20 | 4.38 | 0%
F.E.Z5.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-06-29 | 2025-07-20 | 2025-06-29 | 2025-07-20 | 2 | 0%
F.E.Z8.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-06-29 | 2025-07-20 | 2025-06-29 | 2025-07-20 | 2.54 | 0%
F.E.Z1.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-06-30 | 2025-07-07 | 2025-06-30 | 2025-07-07 | 1.96 | 0%
F.E.Z3.AR.BF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-06-30 | 2025-07-07 | 2025-06-30 | 2025-07-07 | 4.35 | 0%
F.E.Z3.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-30 | 2025-07-21 | 2025-06-30 | 2025-07-21 | 5.15 | 0%
F.E.Z3.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-06-30 | 2025-07-21 | 2025-06-30 | 2025-07-21 | 5.96 | 0%
F.E.Z4.HV.LG.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-06-30 | 2025-07-07 | 2025-06-30 | 2025-07-07 | 5.27 | 0%
F.E.Z5.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-06-30 | 2025-07-21 | 2025-06-30 | 2025-07-21 | 4.04 | 0%
F.E.Z9.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-06-30 | 2025-07-21 | 2025-06-30 | 2025-07-21 | 2.31 | 0%
F.E.Z3.HV.2F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 5.19 | 0%
F.E.Z4.FF.LG.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 5.27 | 0%
F.E.Z4.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 4.27 | 0%
F.E.Z5.F2.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.08 | 0%
F.E.Z5.F2.GF.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.5 | 0%
F.E.Z5.F2.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.73 | 0%
F.E.Z5.F2.1F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 6.15 | 0%
F.E.Z5.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 3.85 | 0%
F.E.Z6.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 0.77 | 0%
F.E.Z4.F2.LG.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.5 | 0%
F.E.Z4.F2.LG.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.54 | 0%
F.E.Z4.F2.LG.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.96 | 0%
F.E.Z4.F2.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 4.54 | 0%
F.E.Z4.F2.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 4.54 | 0%
F.E.Z4.F2.GF.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.08 | 0%
F.E.Z4.F2.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 6.46 | 0%
F.E.Z4.F2.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 3.88 | 0%
F.E.Z4.F2.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.31 | 0%
F.E.Z4.F2.1F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.73 | 0%
F.E.Z4.F2.2F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 4.35 | 0%
F.E.Z4.F2.2F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.19 | 0%
F.E.Z4.F2.2F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-22 | 5.46 | 0%
R.E.5B.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 2.04 | 0%
R.E.5B.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 2.04 | 0%
R.E.5B.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 2.04 | 0%
R.E.5B.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-01 | 2025-07-08 | 2025-07-01 | 2025-07-08 | 2.04 | 0%
F.E.Z1.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-07-02 | 2025-07-09 | 2025-07-02 | 2025-07-09 | 1.88 | 0%
F.E.Z3.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-02 | 2025-07-23 | 2025-07-02 | 2025-07-23 | 4.27 | 0%
F.E.Z3.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-02 | 2025-07-23 | 2025-07-02 | 2025-07-23 | 4.27 | 0%
F.E.Z5.F2.GF.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-07-02 | 2025-07-09 | 2025-07-02 | 2025-07-09 | 4.19 | 0%
F.E.Z4.F2.LG.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-07-02 | 2025-07-09 | 2025-07-02 | 2025-07-09 | 6.54 | 0%
R.E.4B.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
R.E.4B.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
R.E.4B.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
R.E.4B.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
F.E.Z4.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-07-03 | 2025-07-10 | 2025-07-03 | 2025-07-10 | 4.15 | 0%
F.E.Z5.ST.3F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 1.04 | 0%
F.E.Z5.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 3.54 | 0%
F.E.Z6.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 0.96 | 0%
R.E.6B.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
R.E.6B.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
R.E.6B.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
R.E.6B.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-03 | 2025-07-24 | 2025-07-03 | 2025-07-24 | 2.04 | 0%
F.E.Z9.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-07-03 | 2025-07-10 | 2025-07-03 | 2025-07-10 | 2.96 | 0%
F.E.Z9.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-07-03 | 2025-07-10 | 2025-07-03 | 2025-07-10 | 2.96 | 0%
F.E.Z2.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-07-05 | 2025-07-26 | 2025-07-05 | 2025-07-26 | 2.35 | 0%
F.E.Z2.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-07-05 | 2025-07-26 | 2025-07-05 | 2025-07-26 | 2.35 | 0%
F.E.Z3.AR.BF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-07-05 | 2025-07-12 | 2025-07-05 | 2025-07-12 | 4.19 | 0%
F.E.Z3.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-07-05 | 2025-07-12 | 2025-07-05 | 2025-07-12 | 4.54 | 0%
F.E.Z4.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-07-05 | 2025-07-12 | 2025-07-05 | 2025-07-12 | 4.85 | 0%
F.E.Z5.PL.2F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-07-05 | 2025-07-12 | 2025-07-05 | 2025-07-12 | 3.65 | 0%
F.E.Z5.ST.3F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-05 | 2025-07-26 | 2025-07-05 | 2025-07-26 | 1 | 0%
F.E.Z6.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-07-05 | 2025-07-26 | 2025-07-05 | 2025-07-26 | 4.77 | 0%
F.E.Z4.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-07-06 | 2025-07-13 | 2025-07-06 | 2025-07-13 | 5.12 | 0%
F.E.Z5.F2.LG.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-06 | 2025-07-27 | 2025-07-06 | 2025-07-27 | 5.38 | 0%
F.E.Z3.AR.BF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-07-07 | 2025-07-14 | 2025-07-07 | 2025-07-14 | 5.69 | 0%
F.E.Z1.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-07-08 | 2025-07-29 | 2025-07-08 | 2025-07-29 | 1.96 | 0%
F.E.Z3.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-07-08 | 2025-07-29 | 2025-07-08 | 2025-07-29 | 4.35 | 0%
F.E.Z4.HV.LG.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-08 | 2025-07-29 | 2025-07-08 | 2025-07-29 | 5.27 | 0%
F.E.Z7.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-07-08 | 2025-07-15 | 2025-07-08 | 2025-07-15 | 1.42 | 0%
F.E.Z3.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-07-09 | 2025-07-16 | 2025-07-09 | 2025-07-16 | 3.35 | 0%
F.E.Z3.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 5.19 | 0%
F.E.Z4.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-07-09 | 2025-07-16 | 2025-07-09 | 2025-07-16 | 4.65 | 0%
F.E.Z4.FF.LG.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 5.27 | 0%
F.E.Z4.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 4.27 | 0%
F.E.Z6.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-07-09 | 2025-07-16 | 2025-07-09 | 2025-07-16 | 2.42 | 0%
F.E.Z6.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 0.77 | 0%
F.E.Z4.F2.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 6.46 | 0%
R.E.5B.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 2.04 | 0%
R.E.5B.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 2.04 | 0%
R.E.5B.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 2.04 | 0%
R.E.5B.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-09 | 2025-07-30 | 2025-07-09 | 2025-07-30 | 2.04 | 0%
F.E.Z1.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-07-10 | 2025-07-31 | 2025-07-10 | 2025-07-31 | 1.88 | 0%
F.E.Z3.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | 3.31 | 0%
F.E.Z5.AR.LG.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | 3.12 | 0%
F.E.Z5.F2.1F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | 4.15 | 0%
F.E.Z5.F2.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-07-10 | 2025-07-31 | 2025-07-10 | 2025-07-31 | 4.19 | 0%
F.E.Z7.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | 1.35 | 0%
F.E.Z4.F2.LG.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-07-10 | 2025-07-31 | 2025-07-10 | 2025-07-31 | 6.54 | 0%
F.E.Z5.F2.LG.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | 5.38 | 0%
F.E.Z1.ST.BF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-12 | 2025-07-19 | 2025-07-12 | 2025-07-19 | 1.58 | 0%
F.E.Z3.DR.BF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-07-12 | 2025-07-19 | 2025-07-12 | 2025-07-19 | 4.62 | 0%
F.E.Z3.FF.2F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-07-12 | 2025-07-19 | 2025-07-12 | 2025-07-19 | 5.46 | 0%
F.E.Z4.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-12 | 2025-08-02 | 2025-07-12 | 2025-08-02 | 4.15 | 0%
F.E.Z5.AR.LG.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-07-12 | 2025-07-19 | 2025-07-12 | 2025-07-19 | 4.88 | 0%
F.E.Z5.AR.3F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-07-12 | 2025-07-19 | 2025-07-12 | 2025-07-19 | 5.23 | 0%
F.E.Z6.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-07-12 | 2025-07-19 | 2025-07-12 | 2025-07-19 | 2.35 | 0%
F.E.Z9.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-07-12 | 2025-08-02 | 2025-07-12 | 2025-08-02 | 2.96 | 0%
F.E.Z9.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-07-12 | 2025-08-02 | 2025-07-12 | 2025-08-02 | 2.96 | 0%
F.E.Z3.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-07-13 | 2025-08-03 | 2025-07-13 | 2025-08-03 | 4.19 | 0%
F.E.Z3.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-07-13 | 2025-08-03 | 2025-07-13 | 2025-08-03 | 4.54 | 0%
F.E.Z4.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-07-13 | 2025-08-03 | 2025-07-13 | 2025-08-03 | 4.85 | 0%
F.E.Z5.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-07-13 | 2025-08-03 | 2025-07-13 | 2025-08-03 | 3.65 | 0%
F.E.Z1.ST.BF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-21 | 1.5 | 0%
F.E.Z4.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-07-14 | 2025-08-04 | 2025-07-14 | 2025-08-04 | 5.12 | 0%
F.E.Z5.AR.LG.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-21 | 3 | 0%
F.E.Z3.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-07-15 | 2025-08-05 | 2025-07-15 | 2025-08-05 | 5.69 | 0%
F.E.Z5.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-07-15 | 2025-07-22 | 2025-07-15 | 2025-07-22 | 4.31 | 0%
F.E.Z5.AR.3F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-07-15 | 2025-07-22 | 2025-07-15 | 2025-07-22 | 2.12 | 0%
F.E.Z5.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-07-16 | 2025-07-23 | 2025-07-16 | 2025-07-23 | 4.31 | 0%
F.E.Z5.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-07-16 | 2025-07-23 | 2025-07-16 | 2025-07-23 | 4.96 | 0%
F.E.Z5.DR.2F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-07-16 | 2025-07-23 | 2025-07-16 | 2025-07-23 | 3.27 | 0%
F.E.Z5.AR.3F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-07-16 | 2025-07-23 | 2025-07-16 | 2025-07-23 | 2.08 | 0%
F.E.Z7.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-07-16 | 2025-08-06 | 2025-07-16 | 2025-08-06 | 1.42 | 0%
F.E.Z3.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-07-17 | 2025-08-07 | 2025-07-17 | 2025-08-07 | 3.35 | 0%
F.E.Z4.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-17 | 2025-08-07 | 2025-07-17 | 2025-08-07 | 4.65 | 0%
F.E.Z6.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-07-17 | 2025-08-07 | 2025-07-17 | 2025-08-07 | 2.42 | 0%
F.E.Z7.ST.BF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-17 | 2025-07-24 | 2025-07-17 | 2025-07-24 | 1.12 | 0%
F.E.Z8.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-07-17 | 2025-07-24 | 2025-07-17 | 2025-07-24 | 2.65 | 0%
F.E.Z8.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-07-17 | 2025-07-24 | 2025-07-17 | 2025-07-24 | 2.65 | 0%
F.E.Z8.ST.BF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-17 | 2025-07-24 | 2025-07-17 | 2025-07-24 | 2.65 | 0%
F.E.Z8.ST.BF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-17 | 2025-07-24 | 2025-07-17 | 2025-07-24 | 2.65 | 0%
F.E.Z3.HV.2F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-07-19 | 2025-07-26 | 2025-07-19 | 2025-07-26 | 5.08 | 0%
F.E.Z3.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-07-19 | 2025-08-09 | 2025-07-19 | 2025-08-09 | 3.31 | 0%
F.E.Z5.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-19 | 2025-07-26 | 2025-07-19 | 2025-07-26 | 1.31 | 0%
F.E.Z5.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-07-19 | 2025-07-26 | 2025-07-19 | 2025-07-26 | 4.85 | 0%
F.E.Z5.AR.LG.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-07-19 | 2025-08-09 | 2025-07-19 | 2025-08-09 | 3.12 | 0%
F.E.Z5.F2.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-07-19 | 2025-08-09 | 2025-07-19 | 2025-08-09 | 4.15 | 0%
F.E.Z7.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-07-19 | 2025-08-09 | 2025-07-19 | 2025-08-09 | 1.35 | 0%
F.E.Z5.F2.LG.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-07-19 | 2025-08-09 | 2025-07-19 | 2025-08-09 | 5.38 | 0%
F.E.Z5.F2.2F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-07-19 | 2025-07-26 | 2025-07-19 | 2025-07-26 | 5.19 | 0%
F.E.Z1.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-20 | 2025-08-10 | 2025-07-20 | 2025-08-10 | 1.58 | 0%
F.E.Z3.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-07-20 | 2025-07-27 | 2025-07-20 | 2025-07-27 | 5.27 | 0%
F.E.Z3.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-07-20 | 2025-07-27 | 2025-07-20 | 2025-07-27 | 4.73 | 0%
F.E.Z3.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-07-20 | 2025-08-10 | 2025-07-20 | 2025-08-10 | 4.62 | 0%
F.E.Z3.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-07-20 | 2025-08-10 | 2025-07-20 | 2025-08-10 | 5.46 | 0%
F.E.Z5.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-20 | 2025-07-27 | 2025-07-20 | 2025-07-27 | 1.27 | 0%
F.E.Z5.AR.LG.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-07-20 | 2025-08-10 | 2025-07-20 | 2025-08-10 | 4.88 | 0%
F.E.Z5.AR.3F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-07-20 | 2025-08-10 | 2025-07-20 | 2025-08-10 | 5.23 | 0%
F.E.Z6.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-07-20 | 2025-07-27 | 2025-07-20 | 2025-07-27 | 4.77 | 0%
F.E.Z6.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-07-20 | 2025-08-10 | 2025-07-20 | 2025-08-10 | 2.35 | 0%
F.E.Z7.ST.BF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-20 | 2025-07-27 | 2025-07-20 | 2025-07-27 | 1.04 | 0%
F.E.Z1.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-22 | 2025-08-12 | 2025-07-22 | 2025-08-12 | 1.5 | 0%
R.E.4B.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 2.04 | 0%
R.E.4B.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 2.04 | 0%
F.E.Z2.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 2.5 | 0%
F.E.Z5.F2.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 6.19 | 0%
F.E.Z5.AR.LG.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-07-22 | 2025-08-12 | 2025-07-22 | 2025-08-12 | 3 | 0%
F.E.Z4.F2.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 5.77 | 0%
R.E.6B.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 2.04 | 0%
R.E.6B.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-22 | 2025-07-29 | 2025-07-22 | 2025-07-29 | 2.04 | 0%
F.E.Z3.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 4.58 | 0%
F.E.Z5.HV.2F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 3.04 | 0%
F.E.Z5.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-08-13 | 4.31 | 0%
F.E.Z5.AR.3F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-08-13 | 2.12 | 0%
F.E.Z3.HV.RF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-07-24 | 2025-07-31 | 2025-07-24 | 2025-07-31 | 3.96 | 0%
F.E.Z3.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-07-24 | 2025-07-31 | 2025-07-24 | 2025-07-31 | 4.42 | 0%
F.E.Z3.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-07-24 | 2025-07-31 | 2025-07-24 | 2025-07-31 | 7.5 | 0%
F.E.Z3.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-07-24 | 2025-07-31 | 2025-07-24 | 2025-07-31 | 9.23 | 0%
F.E.Z5.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-07-24 | 2025-08-14 | 2025-07-24 | 2025-08-14 | 4.31 | 0%
F.E.Z5.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-07-24 | 2025-08-14 | 2025-07-24 | 2025-08-14 | 4.96 | 0%
F.E.Z5.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-07-24 | 2025-08-14 | 2025-07-24 | 2025-08-14 | 3.27 | 0%
F.E.Z5.AR.3F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-07-24 | 2025-08-14 | 2025-07-24 | 2025-08-14 | 2.08 | 0%
F.E.Z4.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-07-26 | 2025-08-02 | 2025-07-26 | 2025-08-02 | 7.5 | 0%
F.E.Z4.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-07-26 | 2025-08-02 | 2025-07-26 | 2025-08-02 | 9.19 | 0%
F.E.Z5.EL.2F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-07-26 | 2025-08-02 | 2025-07-26 | 2025-08-02 | 4.77 | 0%
F.E.Z6.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-26 | 2025-08-02 | 2025-07-26 | 2025-08-02 | 0.77 | 0%
F.E.Z7.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-26 | 2025-08-16 | 2025-07-26 | 2025-08-16 | 1.12 | 0%
F.E.Z8.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-07-26 | 2025-08-16 | 2025-07-26 | 2025-08-16 | 2.65 | 0%
F.E.Z8.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-07-26 | 2025-08-16 | 2025-07-26 | 2025-08-16 | 2.65 | 0%
F.E.Z8.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-26 | 2025-08-16 | 2025-07-26 | 2025-08-16 | 2.65 | 0%
F.E.Z8.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-26 | 2025-08-16 | 2025-07-26 | 2025-08-16 | 2.65 | 0%
F.E.Z3.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-27 | 2025-08-17 | 2025-07-27 | 2025-08-17 | 5.08 | 0%
F.E.Z5.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-27 | 2025-08-17 | 2025-07-27 | 2025-08-17 | 1.31 | 0%
F.E.Z5.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-07-27 | 2025-08-17 | 2025-07-27 | 2025-08-17 | 4.85 | 0%
F.E.Z5.F2.2F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-07-27 | 2025-08-17 | 2025-07-27 | 2025-08-17 | 5.19 | 0%
F.E.Z3.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-07-28 | 2025-08-18 | 2025-07-28 | 2025-08-18 | 5.27 | 0%
F.E.Z3.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-07-28 | 2025-08-18 | 2025-07-28 | 2025-08-18 | 4.73 | 0%
F.E.Z5.PL.3F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-07-28 | 2025-08-04 | 2025-07-28 | 2025-08-04 | 3.42 | 0%
F.E.Z5.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-28 | 2025-08-18 | 2025-07-28 | 2025-08-18 | 1.27 | 0%
F.E.Z6.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-28 | 2025-08-04 | 2025-07-28 | 2025-08-04 | 0.69 | 0%
F.E.Z6.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-07-28 | 2025-08-18 | 2025-07-28 | 2025-08-18 | 4.77 | 0%
F.E.Z7.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-28 | 2025-08-18 | 2025-07-28 | 2025-08-18 | 1.04 | 0%
R.E.5B.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-07-28 | 2025-08-04 | 2025-07-28 | 2025-08-04 | 2.04 | 0%
R.E.5B.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-07-28 | 2025-08-04 | 2025-07-28 | 2025-08-04 | 2.04 | 0%
R.E.4B.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 2.04 | 0%
R.E.4B.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 2.04 | 0%
F.E.Z2.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 2.5 | 0%
F.E.Z5.PL.LG.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-07-30 | 2025-08-06 | 2025-07-30 | 2025-08-06 | 3.04 | 0%
F.E.Z5.HV.LG.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-07-30 | 2025-08-06 | 2025-07-30 | 2025-08-06 | 2.92 | 0%
F.E.Z5.F2.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 6.19 | 0%
F.E.Z4.F2.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 5.77 | 0%
R.E.6B.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 2.04 | 0%
R.E.6B.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-07-30 | 2025-08-20 | 2025-07-30 | 2025-08-20 | 2.04 | 0%
F.E.Z3.HV.BF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-07-31 | 2025-08-07 | 2025-07-31 | 2025-08-07 | 4.04 | 0%
F.E.Z3.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-07-31 | 2025-08-21 | 2025-07-31 | 2025-08-21 | 4.58 | 0%
F.E.Z5.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-07-31 | 2025-08-21 | 2025-07-31 | 2025-08-21 | 3.04 | 0%
F.E.Z5.F2.2F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-07-31 | 2025-08-07 | 2025-07-31 | 2025-08-07 | 5.04 | 0%
F.E.Z2.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-09 | 2.54 | 0%
F.E.Z2.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-09 | 2.54 | 0%
F.E.Z2.ST.BF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-09 | 2.54 | 0%
F.E.Z2.ST.BF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-09 | 2.54 | 0%
F.E.Z3.AR.BF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-09 | 5.73 | 0%
F.E.Z3.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-08-02 | 2025-08-23 | 2025-08-02 | 2025-08-23 | 3.96 | 0%
F.E.Z3.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-08-02 | 2025-08-23 | 2025-08-02 | 2025-08-23 | 4.42 | 0%
F.E.Z3.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-08-02 | 2025-08-23 | 2025-08-02 | 2025-08-23 | 7.5 | 0%
F.E.Z3.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-08-02 | 2025-08-23 | 2025-08-02 | 2025-08-23 | 9.23 | 0%
F.E.Z5.F2.2F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-08-02 | 2025-08-09 | 2025-08-02 | 2025-08-09 | 3.65 | 0%
F.E.Z4.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-08-03 | 2025-08-24 | 2025-08-03 | 2025-08-24 | 7.5 | 0%
F.E.Z4.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-08-03 | 2025-08-24 | 2025-08-03 | 2025-08-24 | 9.19 | 0%
F.E.Z5.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-08-03 | 2025-08-24 | 2025-08-03 | 2025-08-24 | 4.77 | 0%
F.E.Z6.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-03 | 2025-08-24 | 2025-08-03 | 2025-08-24 | 0.77 | 0%
F.E.Z3.AR.BF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 4.38 | 0%
F.E.Z3.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 4.23 | 0%
F.E.Z5.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 4.42 | 0%
F.E.Z6.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 2.35 | 0%
F.E.Z6.AR.2F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 5.31 | 0%
F.E.Z4.F2.LG.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 5.58 | 0%
F.E.Z5.PL.3F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-08-05 | 2025-08-26 | 2025-08-05 | 2025-08-26 | 3.42 | 0%
F.E.Z6.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-08-05 | 2025-08-12 | 2025-08-05 | 2025-08-12 | 2.46 | 0%
F.E.Z6.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-05 | 2025-08-26 | 2025-08-05 | 2025-08-26 | 0.69 | 0%
R.E.5B.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-05 | 2025-08-26 | 2025-08-05 | 2025-08-26 | 2.04 | 0%
R.E.5B.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-05 | 2025-08-26 | 2025-08-05 | 2025-08-26 | 2.04 | 0%
F.E.Z3.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-13 | 7.5 | 0%
F.E.Z3.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-13 | 7.5 | 0%
F.E.Z5.F2.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-13 | 5.65 | 0%
F.E.Z6.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-13 | 2.31 | 0%
F.E.Z3.AR.RF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-08-07 | 2025-08-14 | 2025-08-07 | 2025-08-14 | 4.35 | 0%
F.E.Z5.PL.LG.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-08-07 | 2025-08-28 | 2025-08-07 | 2025-08-28 | 3.04 | 0%
F.E.Z5.HV.LG.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-08-07 | 2025-08-28 | 2025-08-07 | 2025-08-28 | 2.92 | 0%
F.E.Z6.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-08-07 | 2025-08-14 | 2025-08-07 | 2025-08-14 | 2.38 | 0%
F.E.Z3.AR.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 4.62 | 0%
F.E.Z3.AR.RF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 3.92 | 0%
F.E.Z3.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 9.58 | 0%
F.E.Z3.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-08-09 | 2025-08-30 | 2025-08-09 | 2025-08-30 | 4.04 | 0%
F.E.Z4.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 7.46 | 0%
F.E.Z4.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 7.46 | 0%
F.E.Z5.EL.LG.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 2.62 | 0%
F.E.Z5.DR.3F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 3.04 | 0%
F.E.Z5.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 2.23 | 0%
F.E.Z6.AR.BF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-08-09 | 2025-08-16 | 2025-08-09 | 2025-08-16 | 6.23 | 0%
F.E.Z5.F2.2F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-08-09 | 2025-08-30 | 2025-08-09 | 2025-08-30 | 5.04 | 0%
F.E.Z1.AR.BF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-08-10 | 2025-08-17 | 2025-08-10 | 2025-08-17 | 4.81 | 0%
F.E.Z2.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-08-10 | 2025-08-31 | 2025-08-10 | 2025-08-31 | 2.54 | 0%
F.E.Z2.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-08-10 | 2025-08-31 | 2025-08-10 | 2025-08-31 | 2.54 | 0%
F.E.Z2.ST.BF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-10 | 2025-08-31 | 2025-08-10 | 2025-08-31 | 2.54 | 0%
F.E.Z2.ST.BF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-10 | 2025-08-31 | 2025-08-10 | 2025-08-31 | 2.54 | 0%
F.E.Z3.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-08-10 | 2025-08-31 | 2025-08-10 | 2025-08-31 | 5.73 | 0%
F.E.Z5.FF.2F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-08-10 | 2025-08-17 | 2025-08-10 | 2025-08-17 | 4.27 | 0%
F.E.Z6.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-08-10 | 2025-08-17 | 2025-08-10 | 2025-08-17 | 2.15 | 0%
F.E.Z5.F2.2F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-08-10 | 2025-08-31 | 2025-08-10 | 2025-08-31 | 3.65 | 0%
R.E.VL.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-08-10 | 2025-08-17 | 2025-08-10 | 2025-08-17 | 2.04 | 0%
F.E.Z3.FF.BF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-18 | 4.31 | 0%
F.E.Z3.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-18 | 3.85 | 0%
F.E.Z5.DR.LG.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-18 | 2.69 | 0%
F.E.Z9.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-18 | 3.19 | 0%
F.E.Z4.F2.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-18 | 5.08 | 0%
F.E.Z5.F2.LG.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-08-11 | 2025-08-18 | 2025-08-11 | 2025-08-18 | 5.23 | 0%
F.E.Z3.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-08-12 | 2025-09-02 | 2025-08-12 | 2025-09-02 | 4.38 | 0%
F.E.Z3.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-08-12 | 2025-09-02 | 2025-08-12 | 2025-09-02 | 4.23 | 0%
F.E.Z5.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-08-12 | 2025-08-19 | 2025-08-12 | 2025-08-19 | 2.12 | 0%
F.E.Z5.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-08-12 | 2025-09-02 | 2025-08-12 | 2025-09-02 | 4.42 | 0%
F.E.Z6.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-08-12 | 2025-09-02 | 2025-08-12 | 2025-09-02 | 2.35 | 0%
F.E.Z6.AR.2F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-08-12 | 2025-09-02 | 2025-08-12 | 2025-09-02 | 5.31 | 0%
F.E.Z4.F2.LG.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-08-12 | 2025-09-02 | 2025-08-12 | 2025-09-02 | 5.58 | 0%
F.E.Z6.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-08-13 | 2025-09-03 | 2025-08-13 | 2025-09-03 | 2.46 | 0%
F.E.Z3.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-08-14 | 2025-08-21 | 2025-08-14 | 2025-08-21 | 4.65 | 0%
F.E.Z3.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-08-14 | 2025-09-04 | 2025-08-14 | 2025-09-04 | 7.5 | 0%
F.E.Z3.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-08-14 | 2025-09-04 | 2025-08-14 | 2025-09-04 | 7.5 | 0%
F.E.Z5.F2.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-08-14 | 2025-09-04 | 2025-08-14 | 2025-09-04 | 5.65 | 0%
F.E.Z6.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-08-14 | 2025-09-04 | 2025-08-14 | 2025-09-04 | 2.31 | 0%
F.E.Z3.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-08-16 | 2025-09-06 | 2025-08-16 | 2025-09-06 | 4.35 | 0%
F.E.Z6.AR.BF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-08-16 | 2025-08-23 | 2025-08-16 | 2025-08-23 | 4.73 | 0%
F.E.Z6.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-08-16 | 2025-09-06 | 2025-08-16 | 2025-09-06 | 2.38 | 0%
F.E.Z8.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-16 | 2025-08-23 | 2025-08-16 | 2025-08-23 | 2.81 | 0%
F.E.Z8.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-16 | 2025-08-23 | 2025-08-16 | 2025-08-23 | 2.81 | 0%
F.E.Z3.AR.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-08-17 | 2025-08-24 | 2025-08-17 | 2025-08-24 | 5.23 | 0%
F.E.Z3.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 4.62 | 0%
F.E.Z3.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 3.92 | 0%
F.E.Z3.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 9.58 | 0%
F.E.Z4.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 7.46 | 0%
F.E.Z4.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 7.46 | 0%
F.E.Z5.F2.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-08-17 | 2025-08-24 | 2025-08-17 | 2025-08-24 | 5.35 | 0%
F.E.Z5.EL.LG.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 2.62 | 0%
F.E.Z5.DR.3F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 3.04 | 0%
F.E.Z5.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 2.23 | 0%
F.E.Z6.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-08-17 | 2025-09-07 | 2025-08-17 | 2025-09-07 | 6.23 | 0%
F.E.Z1.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 3.92 | 0%
F.E.Z1.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-08-18 | 2025-09-08 | 2025-08-18 | 2025-09-08 | 4.81 | 0%
R.E.4B.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 3.73 | 0%
R.E.4B.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 3.73 | 0%
F.E.Z3.HV.BF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 3.92 | 0%
F.E.Z5.HV.2F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 4 | 0%
F.E.Z5.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-08-18 | 2025-09-08 | 2025-08-18 | 2025-09-08 | 4.27 | 0%
F.E.Z6.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-08-18 | 2025-09-08 | 2025-08-18 | 2025-09-08 | 2.15 | 0%
R.E.6B.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 3.65 | 0%
R.E.6B.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-18 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 3.65 | 0%
R.E.VL.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-08-18 | 2025-09-08 | 2025-08-18 | 2025-09-08 | 2.04 | 0%
F.E.Z3.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-08-19 | 2025-09-09 | 2025-08-19 | 2025-09-09 | 4.31 | 0%
F.E.Z3.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-08-19 | 2025-09-09 | 2025-08-19 | 2025-09-09 | 3.85 | 0%
F.E.Z5.F2.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-26 | 4.58 | 0%
F.E.Z5.HV.3F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-08-19 | 2025-08-26 | 2025-08-19 | 2025-08-26 | 2.69 | 0%
F.E.Z5.DR.LG.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-08-19 | 2025-09-09 | 2025-08-19 | 2025-09-09 | 2.69 | 0%
F.E.Z4.F2.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-08-19 | 2025-09-09 | 2025-08-19 | 2025-09-09 | 5.08 | 0%
F.E.Z5.F2.LG.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-08-19 | 2025-09-09 | 2025-08-19 | 2025-09-09 | 5.23 | 0%
F.E.Z9.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-08-19 | 2025-09-09 | 2025-08-19 | 2025-09-09 | 3.19 | 0%
F.E.Z3.AR.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 4 | 0%
F.E.Z3.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 7.35 | 0%
F.E.Z3.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 8.35 | 0%
F.E.Z3.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 8.42 | 0%
F.E.Z4.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 8.42 | 0%
F.E.Z4.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 9.19 | 0%
F.E.Z5.EL.3F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 3.92 | 0%
F.E.Z5.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-08-20 | 2025-09-10 | 2025-08-20 | 2025-09-10 | 2.12 | 0%
F.E.Z6.ST.2F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 0.73 | 0%
F.E.Z6.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 1.81 | 0%
F.E.Z5.F2.LG.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-08-20 | 2025-08-27 | 2025-08-20 | 2025-08-27 | 3.12 | 0%
F.E.Z5.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-08-21 | 2025-08-28 | 2025-08-21 | 2025-08-28 | 2.65 | 0%
F.E.Z6.ST.2F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-21 | 2025-08-28 | 2025-08-21 | 2025-08-28 | 0.69 | 0%
F.E.Z7.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-21 | 2025-08-28 | 2025-08-21 | 2025-08-28 | 1.08 | 0%
F.E.Z7.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-08-21 | 2025-08-28 | 2025-08-21 | 2025-08-28 | 3.85 | 0%
F.E.Z2.ST.LG.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-30 | 3.08 | 0%
F.E.Z2.ST.LG.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-30 | 3.08 | 0%
F.E.Z3.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-08-23 | 2025-09-13 | 2025-08-23 | 2025-09-13 | 4.65 | 0%
F.E.Z5.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-30 | 6 | 0%
F.E.Z5.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-30 | 8.27 | 0%
F.E.Z6.AR.BF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-30 | 2.77 | 0%
F.E.Z6.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-08-24 | 2025-09-14 | 2025-08-24 | 2025-09-14 | 4.73 | 0%
F.E.Z8.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-24 | 2025-09-14 | 2025-08-24 | 2025-09-14 | 2.81 | 0%
F.E.Z8.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-24 | 2025-09-14 | 2025-08-24 | 2025-09-14 | 2.81 | 0%
F.E.Z4.F2.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-08-24 | 2025-08-31 | 2025-08-24 | 2025-08-31 | 4 | 0%
R.E.5B.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-24 | 2025-08-31 | 2025-08-24 | 2025-08-31 | 4.35 | 0%
R.E.5B.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-24 | 2025-08-31 | 2025-08-24 | 2025-08-31 | 4.35 | 0%
F.E.Z3.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-08-25 | 2025-09-15 | 2025-08-25 | 2025-09-15 | 5.23 | 0%
F.E.Z4.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-08-25 | 2025-09-01 | 2025-08-25 | 2025-09-01 | 7.19 | 0%
F.E.Z5.F2.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-08-25 | 2025-09-15 | 2025-08-25 | 2025-09-15 | 5.35 | 0%
F.E.Z6.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-08-25 | 2025-09-01 | 2025-08-25 | 2025-09-01 | 3 | 0%
F.E.Z1.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-09-02 | 1.62 | 0%
F.E.Z1.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 3.92 | 0%
R.E.4B.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 3.73 | 0%
R.E.4B.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 3.73 | 0%
F.E.Z3.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 3.92 | 0%
F.E.Z5.F2.3F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-09-02 | 3.92 | 0%
F.E.Z5.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 4 | 0%
F.E.Z4.F2.2F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-08-26 | 2025-09-02 | 2025-08-26 | 2025-09-02 | 5.19 | 0%
R.E.6B.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 3.65 | 0%
R.E.6B.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-26 | 2025-09-16 | 2025-08-26 | 2025-09-16 | 3.65 | 0%
F.E.Z5.F2.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-08-27 | 2025-09-17 | 2025-08-27 | 2025-09-17 | 4.58 | 0%
F.E.Z5.HV.3F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-08-27 | 2025-09-17 | 2025-08-27 | 2025-09-17 | 2.69 | 0%
F.E.Z6.AR.GF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-08-27 | 2025-09-03 | 2025-08-27 | 2025-09-03 | 3.77 | 0%
F.E.Z7.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-27 | 2025-09-03 | 2025-08-27 | 2025-09-03 | 0.88 | 0%
F.E.Z3.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 4 | 0%
F.E.Z3.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 7.35 | 0%
F.E.Z3.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 8.35 | 0%
F.E.Z3.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 8.42 | 0%
F.E.Z4.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 8.42 | 0%
F.E.Z4.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 9.19 | 0%
F.E.Z5.F2.3F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-08-28 | 2025-09-04 | 2025-08-28 | 2025-09-04 | 4.12 | 0%
F.E.Z5.EL.3F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 3.92 | 0%
F.E.Z6.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-08-28 | 2025-09-04 | 2025-08-28 | 2025-09-04 | 2.31 | 0%
F.E.Z6.ST.2F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 0.73 | 0%
F.E.Z6.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 1.81 | 0%
F.E.Z5.F2.LG.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-08-28 | 2025-09-18 | 2025-08-28 | 2025-09-18 | 3.12 | 0%
F.E.Z1.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 1.5 | 0%
F.E.Z1.AR.BF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 2.19 | 0%
F.E.Z3.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 4 | 0%
F.E.Z5.F2.3F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 3.27 | 0%
F.E.Z5.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-08-30 | 2025-09-20 | 2025-08-30 | 2025-09-20 | 2.65 | 0%
F.E.Z6.AR.BF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 2.54 | 0%
F.E.Z6.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 2.31 | 0%
F.E.Z6.ST.2F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-30 | 2025-09-20 | 2025-08-30 | 2025-09-20 | 0.69 | 0%
F.E.Z7.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-30 | 2025-09-20 | 2025-08-30 | 2025-09-20 | 1.08 | 0%
F.E.Z7.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-08-30 | 2025-09-20 | 2025-08-30 | 2025-09-20 | 3.85 | 0%
F.E.Z5.F2.LG.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 4.73 | 0%
F.E.Z2.ST.LG.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-08-31 | 2025-09-21 | 2025-08-31 | 2025-09-21 | 3.08 | 0%
F.E.Z2.ST.LG.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-08-31 | 2025-09-21 | 2025-08-31 | 2025-09-21 | 3.08 | 0%
F.E.Z5.HV.LG.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-08-31 | 2025-09-07 | 2025-08-31 | 2025-09-07 | 3.23 | 0%
F.E.Z5.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-08-31 | 2025-09-21 | 2025-08-31 | 2025-09-21 | 6 | 0%
F.E.Z5.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-08-31 | 2025-09-21 | 2025-08-31 | 2025-09-21 | 8.27 | 0%
F.E.Z6.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-08-31 | 2025-09-21 | 2025-08-31 | 2025-09-21 | 2.77 | 0%
R.E.VL.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-08-31 | 2025-09-07 | 2025-08-31 | 2025-09-07 | 2.04 | 0%
R.E.VL.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-08-31 | 2025-09-07 | 2025-08-31 | 2025-09-07 | 2.04 | 0%
F.E.Z1.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-01 | 2025-09-08 | 2025-09-01 | 2025-09-08 | 5.62 | 0%
F.E.Z6.AR.2F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-01 | 2025-09-08 | 2025-09-01 | 2025-09-08 | 2.5 | 0%
F.E.Z4.F2.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-09-01 | 2025-09-22 | 2025-09-01 | 2025-09-22 | 4 | 0%
R.E.5B.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-09-01 | 2025-09-22 | 2025-09-01 | 2025-09-22 | 4.35 | 0%
R.E.5B.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-09-01 | 2025-09-22 | 2025-09-01 | 2025-09-22 | 4.35 | 0%
F.E.Z4.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-09-02 | 2025-09-24 | 2025-09-02 | 2025-09-24 | 7.19 | 0%
F.E.Z5.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-02 | 2025-09-09 | 2025-09-02 | 2025-09-09 | 2.27 | 0%
F.E.Z6.AR.2F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-02 | 2025-09-09 | 2025-09-02 | 2025-09-09 | 2.46 | 0%
F.E.Z6.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-09-02 | 2025-09-24 | 2025-09-02 | 2025-09-24 | 3 | 0%
F.E.Z1.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-09-03 | 2025-09-25 | 2025-09-03 | 2025-09-25 | 1.62 | 0%
R.E.4B.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 5.81 | 0%
R.E.4B.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 5.81 | 0%
F.E.Z5.F2.1F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 4.81 | 0%
F.E.Z5.FF.3F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 3.46 | 0%
F.E.Z5.F2.3F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-09-03 | 2025-09-25 | 2025-09-03 | 2025-09-25 | 3.92 | 0%
F.E.Z4.F2.1F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 4.38 | 0%
F.E.Z4.F2.2F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-09-03 | 2025-09-25 | 2025-09-03 | 2025-09-25 | 5.19 | 0%
R.E.6B.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 5.96 | 0%
R.E.6B.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-03 | 2025-09-10 | 2025-09-03 | 2025-09-10 | 5.96 | 0%
F.E.Z5.FF.LG.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-09-04 | 2025-09-11 | 2025-09-04 | 2025-09-11 | 3.12 | 0%
F.E.Z6.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-09-04 | 2025-09-11 | 2025-09-04 | 2025-09-11 | 2.62 | 0%
F.E.Z6.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-09-04 | 2025-09-27 | 2025-09-04 | 2025-09-27 | 3.77 | 0%
F.E.Z7.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-04 | 2025-09-11 | 2025-09-04 | 2025-09-11 | 7.27 | 0%
F.E.Z7.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-09-04 | 2025-09-27 | 2025-09-04 | 2025-09-27 | 0.88 | 0%
F.E.Z4.F2.LG.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-09-04 | 2025-09-11 | 2025-09-04 | 2025-09-11 | 5.19 | 0%
F.E.Z1.AR.BF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 1.96 | 0%
F.E.Z5.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 5.96 | 0%
F.E.Z5.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 5.96 | 0%
F.E.Z5.F2.3F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-09-06 | 2025-09-28 | 2025-09-06 | 2025-09-28 | 4.12 | 0%
F.E.Z6.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 2.58 | 0%
F.E.Z6.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 2.42 | 0%
F.E.Z6.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-09-06 | 2025-09-28 | 2025-09-06 | 2025-09-28 | 2.31 | 0%
F.E.Z8.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 2.92 | 0%
F.E.Z8.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 2.92 | 0%
F.E.Z8.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 3.19 | 0%
F.E.Z8.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 4.73 | 0%
F.E.Z8.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-06 | 2025-09-13 | 2025-09-06 | 2025-09-13 | 3.19 | 0%
F.E.Z1.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 1.5 | 0%
F.E.Z1.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 2.19 | 0%
F.E.Z3.AR.BF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-07 | 2025-09-14 | 2025-09-07 | 2025-09-14 | 3.27 | 0%
F.E.Z3.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 4 | 0%
F.E.Z5.F2.3F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 3.27 | 0%
F.E.Z6.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 2.54 | 0%
F.E.Z6.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 2.31 | 0%
F.E.Z8.AR.BF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-07 | 2025-09-14 | 2025-09-07 | 2025-09-14 | 3.04 | 0%
F.E.Z5.F2.LG.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-09-07 | 2025-09-29 | 2025-09-07 | 2025-09-29 | 4.73 | 0%
R.E.5B.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-07 | 2025-09-14 | 2025-09-07 | 2025-09-14 | 5.42 | 0%
R.E.5B.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-07 | 2025-09-14 | 2025-09-07 | 2025-09-14 | 5.42 | 0%
F.E.Z5.HV.LG.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-09-08 | 2025-09-30 | 2025-09-08 | 2025-09-30 | 3.23 | 0%
F.E.Z8.AR.BF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-08 | 2025-09-15 | 2025-09-08 | 2025-09-15 | 3 | 0%
F.E.Z8.AR.BF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-08 | 2025-09-15 | 2025-09-08 | 2025-09-15 | 4.42 | 0%
F.E.Z9.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-09-08 | 2025-09-15 | 2025-09-08 | 2025-09-15 | 2.65 | 0%
R.E.VL.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-09-08 | 2025-09-30 | 2025-09-08 | 2025-09-30 | 2.04 | 0%
R.E.VL.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-09-08 | 2025-09-30 | 2025-09-08 | 2025-09-30 | 2.04 | 0%
F.E.Z1.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-09 | 2025-10-01 | 2025-09-09 | 2025-10-01 | 5.62 | 0%
F.E.Z4.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-09-09 | 2025-09-16 | 2025-09-09 | 2025-09-16 | 7.69 | 0%
F.E.Z6.HV.1F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-09 | 2025-09-16 | 2025-09-09 | 2025-09-16 | 1.92 | 0%
F.E.Z6.AR.2F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-09 | 2025-10-01 | 2025-09-09 | 2025-10-01 | 2.5 | 0%
F.E.Z7.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-09 | 2025-09-16 | 2025-09-09 | 2025-09-16 | 2.12 | 0%
F.E.Z3.AR.RF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-09-10 | 2025-09-17 | 2025-09-10 | 2025-09-17 | 4.69 | 0%
F.E.Z5.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-09-10 | 2025-10-02 | 2025-09-10 | 2025-10-02 | 2.27 | 0%
F.E.Z6.AR.2F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-10 | 2025-10-02 | 2025-09-10 | 2025-10-02 | 2.46 | 0%
R.E.4B.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 5.81 | 0%
R.E.4B.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 5.81 | 0%
F.E.Z3.AR.1F.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-09-11 | 2025-09-18 | 2025-09-11 | 2025-09-18 | 2.92 | 0%
F.E.Z5.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-09-11 | 2025-09-18 | 2025-09-11 | 2025-09-18 | 8.46 | 0%
F.E.Z5.F2.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 4.81 | 0%
F.E.Z5.FF.3F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 3.46 | 0%
F.E.Z6.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-09-11 | 2025-09-18 | 2025-09-11 | 2025-09-18 | 1.85 | 0%
F.E.Z4.F2.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 4.38 | 0%
R.E.6B.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 5.96 | 0%
R.E.6B.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-11 | 2025-10-04 | 2025-09-11 | 2025-10-04 | 5.96 | 0%
F.E.Z1.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 2 | 0%
F.E.Z2.AR.LG.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 3.19 | 0%
F.E.Z2.AR.LG.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 4.31 | 0%
F.E.Z2.AR.LG.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 3.19 | 0%
F.E.Z5.HV.3F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 3.15 | 0%
F.E.Z5.FF.LG.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-09-13 | 2025-10-05 | 2025-09-13 | 2025-10-05 | 3.12 | 0%
F.E.Z6.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-09-13 | 2025-10-05 | 2025-09-13 | 2025-10-05 | 2.62 | 0%
F.E.Z7.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 2 | 0%
F.E.Z7.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-13 | 2025-10-05 | 2025-09-13 | 2025-10-05 | 7.27 | 0%
F.E.Z4.F2.LG.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-09-13 | 2025-10-05 | 2025-09-13 | 2025-10-05 | 5.19 | 0%
F.E.Z5.F2.2F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-09-13 | 2025-09-20 | 2025-09-13 | 2025-09-20 | 5.46 | 0%
F.E.Z1.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 1.96 | 0%
F.E.Z5.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 5.96 | 0%
F.E.Z5.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 5.96 | 0%
F.E.Z6.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-09-14 | 2025-09-21 | 2025-09-14 | 2025-09-21 | 5.92 | 0%
F.E.Z6.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-09-14 | 2025-09-21 | 2025-09-14 | 2025-09-21 | 7.54 | 0%
F.E.Z6.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 2.58 | 0%
F.E.Z6.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 2.42 | 0%
F.E.Z8.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 2.92 | 0%
F.E.Z8.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 2.92 | 0%
F.E.Z8.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 3.19 | 0%
F.E.Z8.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 4.73 | 0%
F.E.Z8.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-14 | 2025-10-06 | 2025-09-14 | 2025-10-06 | 3.19 | 0%
F.E.Z1.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-15 | 2025-09-22 | 2025-09-15 | 2025-09-22 | 1.92 | 0%
F.E.Z3.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-15 | 2025-10-07 | 2025-09-15 | 2025-10-07 | 3.27 | 0%
F.E.Z5.HV.RF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-15 | 2025-09-22 | 2025-09-15 | 2025-09-22 | 1.85 | 0%
F.E.Z8.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-15 | 2025-10-07 | 2025-09-15 | 2025-10-07 | 3.04 | 0%
F.E.Z4.F2.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-09-15 | 2025-09-22 | 2025-09-15 | 2025-09-22 | 4 | 0%
R.E.5B.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-15 | 2025-10-07 | 2025-09-15 | 2025-10-07 | 5.42 | 0%
R.E.5B.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-15 | 2025-10-07 | 2025-09-15 | 2025-10-07 | 5.42 | 0%
F.E.Z2.AR.BF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-16 | 2025-09-24 | 2025-09-16 | 2025-09-24 | 2.81 | 0%
F.E.Z5.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-09-16 | 2025-09-24 | 2025-09-16 | 2025-09-24 | 3.12 | 0%
F.E.Z5.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-09-16 | 2025-09-24 | 2025-09-16 | 2025-09-24 | 7.54 | 0%
F.E.Z7.AR.BF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-16 | 2025-09-24 | 2025-09-16 | 2025-09-24 | 3.69 | 0%
F.E.Z8.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-10-08 | 3 | 0%
F.E.Z8.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-10-08 | 4.42 | 0%
F.E.Z9.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-10-08 | 2.65 | 0%
F.E.Z1.PL.BF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-17 | 2025-09-25 | 2025-09-17 | 2025-09-25 | 1.96 | 0%
F.E.Z2.AR.BF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-17 | 2025-09-25 | 2025-09-17 | 2025-09-25 | 2.77 | 0%
F.E.Z2.AR.BF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-17 | 2025-09-25 | 2025-09-17 | 2025-09-25 | 3.69 | 0%
F.E.Z4.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-09-17 | 2025-10-09 | 2025-09-17 | 2025-10-09 | 7.69 | 0%
F.E.Z6.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-09-17 | 2025-10-09 | 2025-09-17 | 2025-10-09 | 1.92 | 0%
F.E.Z7.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-17 | 2025-10-09 | 2025-09-17 | 2025-10-09 | 2.12 | 0%
F.E.Z3.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-09-18 | 2025-10-11 | 2025-09-18 | 2025-10-11 | 4.69 | 0%
F.E.Z3.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-09-20 | 2025-09-28 | 2025-09-20 | 2025-09-28 | 3.81 | 0%
F.E.Z3.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-09-20 | 2025-10-12 | 2025-09-20 | 2025-10-12 | 2.92 | 0%
F.E.Z5.F2.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-09-20 | 2025-09-28 | 2025-09-20 | 2025-09-28 | 4.27 | 0%
F.E.Z5.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-09-20 | 2025-09-28 | 2025-09-20 | 2025-09-28 | 5.58 | 0%
F.E.Z5.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-09-20 | 2025-09-28 | 2025-09-20 | 2025-09-28 | 7.35 | 0%
F.E.Z5.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-09-20 | 2025-10-12 | 2025-09-20 | 2025-10-12 | 8.46 | 0%
F.E.Z6.PL.2F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-20 | 2025-09-28 | 2025-09-20 | 2025-09-28 | 3.12 | 0%
F.E.Z6.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-09-20 | 2025-10-12 | 2025-09-20 | 2025-10-12 | 1.85 | 0%
F.E.Z4.F2.2F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-09-20 | 2025-09-28 | 2025-09-20 | 2025-09-28 | 3.65 | 0%
F.E.Z1.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 2 | 0%
F.E.Z2.AR.LG.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 3.19 | 0%
F.E.Z2.AR.LG.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 4.31 | 0%
F.E.Z2.AR.LG.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 3.19 | 0%
F.E.Z5.HV.3F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 3.15 | 0%
F.E.Z6.F2.1F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-09-21 | 2025-09-29 | 2025-09-21 | 2025-09-29 | 2.31 | 0%
F.E.Z7.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 2 | 0%
F.E.Z5.F2.2F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-09-21 | 2025-10-13 | 2025-09-21 | 2025-10-13 | 5.46 | 0%
F.E.Z2.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | 5.65 | 0%
F.E.Z2.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | 7.27 | 0%
F.E.Z3.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | 7.31 | 0%
F.E.Z6.DR.2F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | 3.04 | 0%
F.E.Z6.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-09-22 | 2025-10-14 | 2025-09-22 | 2025-10-14 | 5.92 | 0%
F.E.Z6.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-09-22 | 2025-10-14 | 2025-09-22 | 2025-10-14 | 7.54 | 0%
F.E.Z5.F2.2F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-09-22 | 2025-09-30 | 2025-09-22 | 2025-09-30 | 4.42 | 0%
F.E.Z1.DR.BF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 1.77 | 0%
F.E.Z1.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-24 | 2025-10-15 | 2025-09-24 | 2025-10-15 | 1.92 | 0%
F.E.Z2.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 3.31 | 0%
F.E.Z5.AR.RF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 2.73 | 0%
F.E.Z5.AR.RF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 3.27 | 0%
F.E.Z5.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-09-24 | 2025-10-15 | 2025-09-24 | 2025-10-15 | 1.85 | 0%
F.E.Z6.PL.BF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 2.42 | 0%
F.E.Z8.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 3.19 | 0%
F.E.Z8.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 3.19 | 0%
F.E.Z8.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-24 | 2025-10-01 | 2025-09-24 | 2025-10-01 | 3.19 | 0%
F.E.Z4.F2.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-09-24 | 2025-10-15 | 2025-09-24 | 2025-10-15 | 4 | 0%
F.E.Z1.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 2.04 | 0%
R.E.4B.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 5.12 | 0%
F.E.Z2.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 3.27 | 0%
F.E.Z2.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 6.92 | 0%
F.E.Z2.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-09-25 | 2025-10-16 | 2025-09-25 | 2025-10-16 | 2.81 | 0%
F.E.Z5.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-09-25 | 2025-10-16 | 2025-09-25 | 2025-10-16 | 3.12 | 0%
F.E.Z5.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-09-25 | 2025-10-16 | 2025-09-25 | 2025-10-16 | 7.54 | 0%
F.E.Z6.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 6 | 0%
F.E.Z7.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-25 | 2025-10-16 | 2025-09-25 | 2025-10-16 | 3.69 | 0%
R.E.5B.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 4.85 | 0%
R.E.6B.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-25 | 2025-10-02 | 2025-09-25 | 2025-10-02 | 5.27 | 0%
F.E.Z1.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-09-27 | 2025-10-18 | 2025-09-27 | 2025-10-18 | 1.96 | 0%
F.E.Z2.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-09-27 | 2025-10-18 | 2025-09-27 | 2025-10-18 | 2.77 | 0%
F.E.Z2.AR.BF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-09-27 | 2025-10-18 | 2025-09-27 | 2025-10-18 | 3.69 | 0%
F.E.Z4.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-09-27 | 2025-10-04 | 2025-09-27 | 2025-10-04 | 7.23 | 0%
F.E.Z5.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-09-27 | 2025-10-04 | 2025-09-27 | 2025-10-04 | 2.73 | 0%
F.E.Z6.DR.BF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-27 | 2025-10-04 | 2025-09-27 | 2025-10-04 | 2.38 | 0%
F.E.Z6.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-09-27 | 2025-10-04 | 2025-09-27 | 2025-10-04 | 5.96 | 0%
F.E.Z6.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-09-27 | 2025-10-04 | 2025-09-27 | 2025-10-04 | 6.15 | 0%
F.E.Z8.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-09-27 | 2025-10-04 | 2025-09-27 | 2025-10-04 | 3.12 | 0%
F.E.Z1.HV.BF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 1.54 | 0%
F.E.Z1.EL.BF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 1.54 | 0%
F.E.Z2.PL.LG.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.42 | 0%
F.E.Z2.DR.LG.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.42 | 0%
F.E.Z2.HV.LG.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.46 | 0%
F.E.Z6.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 2.65 | 0%
F.E.Z7.AR.BF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 2.23 | 0%
F.E.Z8.PL.BF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.04 | 0%
F.E.Z8.DR.BF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.04 | 0%
F.E.Z8.HV.BF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.12 | 0%
F.E.Z8.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 3.04 | 0%
R.E.VL.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-09-28 | 2025-10-05 | 2025-09-28 | 2025-10-05 | 2.04 | 0%
R.E.4B.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 5.81 | 0%
R.E.4B.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 5.81 | 0%
R.E.4B.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 5.81 | 0%
F.E.Z2.EL.LG.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 3.35 | 0%
F.E.Z3.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-09-29 | 2025-10-20 | 2025-09-29 | 2025-10-20 | 3.81 | 0%
F.E.Z5.F2.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-09-29 | 2025-10-20 | 2025-09-29 | 2025-10-20 | 4.27 | 0%
F.E.Z5.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-09-29 | 2025-10-20 | 2025-09-29 | 2025-10-20 | 5.58 | 0%
F.E.Z5.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-09-29 | 2025-10-20 | 2025-09-29 | 2025-10-20 | 7.35 | 0%
F.E.Z6.HV.BF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 2.35 | 0%
F.E.Z6.F2.1F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 2.92 | 0%
F.E.Z6.PL.2F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-09-29 | 2025-10-20 | 2025-09-29 | 2025-10-20 | 3.12 | 0%
F.E.Z8.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 3 | 0%
F.E.Z8.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 3.88 | 0%
F.E.Z4.F2.2F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-09-29 | 2025-10-20 | 2025-09-29 | 2025-10-20 | 3.65 | 0%
R.E.6B.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 5.96 | 0%
R.E.6B.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 5.96 | 0%
R.E.6B.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 5.96 | 0%
F.E.Z1.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-09-30 | 2025-10-07 | 2025-09-30 | 2025-10-07 | 2.62 | 0%
F.E.Z3.AR.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-09-30 | 2025-10-07 | 2025-09-30 | 2025-10-07 | 4.46 | 0%
F.E.Z5.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-09-30 | 2025-10-07 | 2025-09-30 | 2025-10-07 | 2.69 | 0%
F.E.Z6.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-09-30 | 2025-10-07 | 2025-09-30 | 2025-10-07 | 7.04 | 0%
F.E.Z6.F2.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-09-30 | 2025-10-21 | 2025-09-30 | 2025-10-21 | 2.31 | 0%
F.E.Z5.F2.LG.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-09-30 | 2025-10-07 | 2025-09-30 | 2025-10-07 | 4.38 | 0%
F.E.Z2.EX.GE.PO.002 | Submission of Shop Drawings For Pools and Water Features | 0.27 | 2025-10-01 | 2025-10-08 | 2025-10-01 | 2025-10-08 | 7 | 0%
F.E.Z2.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-10-01 | 2025-10-22 | 2025-10-01 | 2025-10-22 | 5.65 | 0%
F.E.Z2.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-10-01 | 2025-10-22 | 2025-10-01 | 2025-10-22 | 7.27 | 0%
F.E.Z3.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-10-01 | 2025-10-22 | 2025-10-01 | 2025-10-22 | 7.31 | 0%
F.E.Z6.DR.2F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-01 | 2025-10-22 | 2025-10-01 | 2025-10-22 | 3.04 | 0%
F.E.Z8.EL.BF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-01 | 2025-10-08 | 2025-10-01 | 2025-10-08 | 2.81 | 0%
F.E.Z5.F2.2F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-10-01 | 2025-10-22 | 2025-10-01 | 2025-10-22 | 4.42 | 0%
F.E.Z1.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 1.81 | 0%
F.E.Z1.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 1.77 | 0%
F.E.Z2.PL.BF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.65 | 0%
F.E.Z2.DR.BF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.65 | 0%
F.E.Z2.HV.BF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.73 | 0%
F.E.Z2.EL.BF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.54 | 0%
F.E.Z2.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 3.31 | 0%
F.E.Z5.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 2.73 | 0%
F.E.Z5.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 3.27 | 0%
F.E.Z6.EL.BF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.04 | 0%
F.E.Z6.F2.1F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.38 | 0%
F.E.Z6.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 2.42 | 0%
F.E.Z8.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 3.19 | 0%
F.E.Z8.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 3.19 | 0%
F.E.Z8.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-02 | 2025-10-23 | 2025-10-02 | 2025-10-23 | 3.19 | 0%
F.E.Z9.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 2.81 | 0%
R.E.5B.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 5.42 | 0%
R.E.5B.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 5.42 | 0%
R.E.5B.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-10-02 | 2025-10-09 | 2025-10-02 | 2025-10-09 | 5.42 | 0%
F.E.Z1.AR.BF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 1.92 | 0%
F.E.Z1.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 2.5 | 0%
F.E.Z1.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 2.04 | 0%
R.E.4B.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 5.12 | 0%
F.E.Z2.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 4.38 | 0%
F.E.Z2.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 5.73 | 0%
F.E.Z2.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 5.73 | 0%
F.E.Z2.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 7.77 | 0%
F.E.Z2.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 3.27 | 0%
F.E.Z2.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 6.92 | 0%
F.E.Z6.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 2.31 | 0%
F.E.Z6.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 6 | 0%
F.E.Z7.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 2.27 | 0%
F.E.Z7.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 5.31 | 0%
F.E.Z7.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 6.92 | 0%
F.E.Z9.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 2.77 | 0%
F.E.Z9.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 4.12 | 0%
F.E.Z8.F1.GF.RP.002 | Submission of Shop Drawings For RCP For Public Spaces | 0.27 | 2025-10-04 | 2025-10-11 | 2025-10-04 | 2025-10-11 | 4.38 | 0%
R.E.5B.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 4.85 | 0%
R.E.6B.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-04 | 2025-10-25 | 2025-10-04 | 2025-10-25 | 5.27 | 0%
F.E.Z2.F1.LG.RP.002 | Submission of Shop Drawings For RCP For Public Spaces | 0.27 | 2025-10-05 | 2025-10-12 | 2025-10-05 | 2025-10-12 | 4.31 | 0%
F.E.Z2.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-10-05 | 2025-10-12 | 2025-10-05 | 2025-10-12 | 5.88 | 0%
F.E.Z4.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-10-05 | 2025-10-26 | 2025-10-05 | 2025-10-26 | 7.23 | 0%
F.E.Z5.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-10-05 | 2025-10-12 | 2025-10-05 | 2025-10-12 | 2.42 | 0%
F.E.Z5.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-05 | 2025-10-26 | 2025-10-05 | 2025-10-26 | 2.73 | 0%
F.E.Z6.EL.2F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-05 | 2025-10-12 | 2025-10-05 | 2025-10-12 | 3.38 | 0%
F.E.Z6.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-05 | 2025-10-26 | 2025-10-05 | 2025-10-26 | 2.38 | 0%
F.E.Z6.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-10-05 | 2025-10-26 | 2025-10-05 | 2025-10-26 | 5.96 | 0%
F.E.Z6.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-10-05 | 2025-10-26 | 2025-10-05 | 2025-10-26 | 6.15 | 0%
F.E.Z7.AR.BF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-05 | 2025-10-12 | 2025-10-05 | 2025-10-12 | 2 | 0%
F.E.Z8.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-05 | 2025-10-26 | 2025-10-05 | 2025-10-26 | 3.12 | 0%
F.E.Z1.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 1.54 | 0%
F.E.Z1.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 1.54 | 0%
F.E.Z2.PL.LG.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.42 | 0%
F.E.Z2.DR.LG.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.42 | 0%
F.E.Z2.HV.LG.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.46 | 0%
F.E.Z6.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 2.65 | 0%
F.E.Z7.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-06 | 2025-10-13 | 2025-10-06 | 2025-10-13 | 2.19 | 0%
F.E.Z7.AR.BF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 2.23 | 0%
F.E.Z8.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.04 | 0%
F.E.Z8.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.04 | 0%
F.E.Z8.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.12 | 0%
F.E.Z8.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 3.04 | 0%
R.E.VL.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-10-06 | 2025-10-27 | 2025-10-06 | 2025-10-27 | 2.04 | 0%
F.E.Z1.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-10-07 | 2025-10-14 | 2025-10-07 | 2025-10-14 | 5.08 | 0%
F.E.Z1.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-10-07 | 2025-10-14 | 2025-10-07 | 2025-10-14 | 6.81 | 0%
R.E.4B.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 5.81 | 0%
R.E.4B.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 5.81 | 0%
R.E.4B.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 5.81 | 0%
F.E.Z2.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-10-07 | 2025-10-14 | 2025-10-07 | 2025-10-14 | 6.81 | 0%
F.E.Z2.EL.LG.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 3.35 | 0%
F.E.Z3.AR.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-10-07 | 2025-10-14 | 2025-10-07 | 2025-10-14 | 2.77 | 0%
F.E.Z6.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 2.35 | 0%
F.E.Z6.F2.1F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 2.92 | 0%
F.E.Z8.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 3 | 0%
F.E.Z8.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 3.88 | 0%
F.E.Z1.F1.BF.WA.002 | Submission of Shop Drawings For Waterproofing For Public Spaces | 0.27 | 2025-10-07 | 2025-10-14 | 2025-10-07 | 2025-10-14 | 1.96 | 0%
R.E.6B.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 5.96 | 0%
R.E.6B.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 5.96 | 0%
R.E.6B.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-07 | 2025-10-28 | 2025-10-07 | 2025-10-28 | 5.96 | 0%
F.E.Z1.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-08 | 2025-10-29 | 2025-10-08 | 2025-10-29 | 2.62 | 0%
F.E.Z3.AR.RF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-10-08 | 2025-10-15 | 2025-10-08 | 2025-10-15 | 3.88 | 0%
F.E.Z3.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-10-08 | 2025-10-29 | 2025-10-08 | 2025-10-29 | 4.46 | 0%
F.E.Z5.F2.3F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-10-08 | 2025-10-15 | 2025-10-08 | 2025-10-15 | 4.65 | 0%
F.E.Z5.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-10-08 | 2025-10-29 | 2025-10-08 | 2025-10-29 | 2.69 | 0%
F.E.Z6.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-10-08 | 2025-10-29 | 2025-10-08 | 2025-10-29 | 7.04 | 0%
F.E.Z8.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-10-08 | 2025-10-15 | 2025-10-08 | 2025-10-15 | 4.81 | 0%
F.E.Z8.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-10-08 | 2025-10-15 | 2025-10-08 | 2025-10-15 | 6.77 | 0%
F.E.Z5.F2.LG.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-10-08 | 2025-10-29 | 2025-10-08 | 2025-10-29 | 4.38 | 0%
F.E.Z1.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 1.46 | 0%
F.E.Z1.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 1.46 | 0%
F.E.Z2.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 6.81 | 0%
F.E.Z2.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.73 | 2025-10-09 | 2025-10-30 | 2025-10-09 | 2025-10-30 | 7 | 0%
F.E.Z6.AR.BF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 2.58 | 0%
F.E.Z6.HV.2F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 2.58 | 0%
F.E.Z7.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 1.81 | 0%
F.E.Z8.AR.BF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 3.96 | 0%
F.E.Z8.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-09 | 2025-10-30 | 2025-10-09 | 2025-10-30 | 2.81 | 0%
F.E.Z6.F2.2F.WA.002 | Submission of Shop Drawings For Waterproofing For Guest Rooms | 0.27 | 2025-10-09 | 2025-10-16 | 2025-10-09 | 2025-10-16 | 3.23 | 0%
F.E.Z1.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 1.81 | 0%
F.E.Z2.F1.BF.RP.002 | Submission of Shop Drawings For RCP For Public Spaces | 0.27 | 2025-10-11 | 2025-10-18 | 2025-10-11 | 2025-10-18 | 3.19 | 0%
F.E.Z2.F1.LG.WA.002 | Submission of Shop Drawings For Waterproofing For Public Spaces | 0.27 | 2025-10-11 | 2025-10-18 | 2025-10-11 | 2025-10-18 | 3.77 | 0%
F.E.Z2.HV.LG.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-11 | 2025-10-18 | 2025-10-11 | 2025-10-18 | 3.42 | 0%
F.E.Z2.FF.LG.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-11 | 2025-10-18 | 2025-10-11 | 2025-10-18 | 3.88 | 0%
F.E.Z2.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.65 | 0%
F.E.Z2.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.65 | 0%
F.E.Z2.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.73 | 0%
F.E.Z2.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.54 | 0%
F.E.Z5.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-11 | 2025-10-18 | 2025-10-11 | 2025-10-18 | 2.23 | 0%
F.E.Z6.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.04 | 0%
F.E.Z6.F2.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.38 | 0%
F.E.Z9.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 2.81 | 0%
R.E.5B.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 5.42 | 0%
R.E.5B.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 5.42 | 0%
R.E.5B.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-11 | 2025-11-01 | 2025-10-11 | 2025-11-01 | 5.42 | 0%
F.E.Z1.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 1.92 | 0%
F.E.Z1.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 2.5 | 0%
F.E.Z2.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 4.38 | 0%
F.E.Z2.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 5.73 | 0%
F.E.Z2.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 5.73 | 0%
F.E.Z2.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 7.77 | 0%
F.E.Z6.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 3.96 | 0%
F.E.Z6.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 2.31 | 0%
F.E.Z7.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 1.73 | 0%
F.E.Z7.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 2.27 | 0%
F.E.Z7.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 5.31 | 0%
F.E.Z7.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 6.92 | 0%
F.E.Z9.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 2.77 | 0%
F.E.Z9.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 3 | 0%
F.E.Z9.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 2.77 | 0%
F.E.Z9.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 4.12 | 0%
F.E.Z8.F1.GF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.73 | 2025-10-12 | 2025-11-02 | 2025-10-12 | 2025-11-02 | 4.38 | 0%
R.E.VL.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 2.04 | 0%
R.E.VL.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 2.04 | 0%
R.E.VL.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 2.04 | 0%
R.E.VL.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-10-12 | 2025-10-19 | 2025-10-12 | 2025-10-19 | 2.04 | 0%
F.E.Z1.AR.BF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 3.08 | 0%
F.E.Z1.FF.BF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 2.85 | 0%
F.E.Z2.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 3.42 | 0%
F.E.Z2.HV.RF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 3.42 | 0%
F.E.Z2.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 3.04 | 0%
F.E.Z2.F1.LG.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.73 | 2025-10-13 | 2025-11-03 | 2025-10-13 | 2025-11-03 | 4.31 | 0%
F.E.Z2.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-10-13 | 2025-11-03 | 2025-10-13 | 2025-11-03 | 5.88 | 0%
F.E.Z5.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 6.73 | 0%
F.E.Z5.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-10-13 | 2025-11-03 | 2025-10-13 | 2025-11-03 | 2.42 | 0%
F.E.Z6.FF.2F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 3.27 | 0%
F.E.Z6.EL.2F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-13 | 2025-11-03 | 2025-10-13 | 2025-11-03 | 3.38 | 0%
F.E.Z7.AR.BF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-13 | 2025-11-03 | 2025-10-13 | 2025-11-03 | 2 | 0%
F.E.Z1.F1.BF.RP.002 | Submission of Shop Drawings For RCP For Public Spaces | 0.27 | 2025-10-13 | 2025-10-20 | 2025-10-13 | 2025-10-20 | 3.12 | 0%
F.E.Z3.EL.BF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-21 | 4.38 | 0%
F.E.Z6.AR.BF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-21 | 3.27 | 0%
F.E.Z7.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-10-14 | 2025-11-04 | 2025-10-14 | 2025-11-04 | 2.19 | 0%
F.E.Z4.F2.2F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-21 | 3.62 | 0%
F.E.Z5.F2.2F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-21 | 4.46 | 0%
F.E.Z1.AR.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 2.77 | 0%
F.E.Z1.HV.BF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 2.65 | 0%
F.E.Z1.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-11-05 | 5.08 | 0%
F.E.Z1.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-11-05 | 6.81 | 0%
F.E.Z2.F1.BF.WA.002 | Submission of Shop Drawings For Waterproofing For Public Spaces | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 2.73 | 0%
F.E.Z2.HV.BF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 2.81 | 0%
F.E.Z2.FF.BF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 2.85 | 0%
F.E.Z2.F1.LG.WL.002 | Submission of Shop Drawings For Wall Finishes For Public Spaces | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 3.77 | 0%
F.E.Z2.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-11-05 | 6.81 | 0%
F.E.Z3.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-11-05 | 2.77 | 0%
F.E.Z8.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 3.46 | 0%
F.E.Z8.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 3.69 | 0%
F.E.Z1.F1.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.73 | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-11-05 | 1.96 | 0%
F.E.Z8.F1.GF.WA.002 | Submission of Shop Drawings For Waterproofing For Public Spaces | 0.27 | 2025-10-15 | 2025-10-22 | 2025-10-15 | 2025-10-22 | 3.23 | 0%
F.E.Z1.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-16 | 2025-10-23 | 2025-10-16 | 2025-10-23 | 2.92 | 0%
F.E.Z3.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-10-16 | 2025-11-06 | 2025-10-16 | 2025-11-06 | 3.88 | 0%
F.E.Z5.F2.3F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-10-16 | 2025-11-06 | 2025-10-16 | 2025-11-06 | 4.65 | 0%
F.E.Z8.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-16 | 2025-10-23 | 2025-10-16 | 2025-10-23 | 2.85 | 0%
F.E.Z8.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-16 | 2025-10-23 | 2025-10-16 | 2025-10-23 | 2.85 | 0%
F.E.Z8.HV.1F.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-16 | 2025-10-23 | 2025-10-16 | 2025-10-23 | 2.92 | 0%
F.E.Z8.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-16 | 2025-10-23 | 2025-10-16 | 2025-10-23 | 3.54 | 0%
F.E.Z8.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-10-16 | 2025-11-06 | 2025-10-16 | 2025-11-06 | 4.81 | 0%
F.E.Z8.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-10-16 | 2025-11-06 | 2025-10-16 | 2025-11-06 | 6.77 | 0%
R.E.SS.ST.FO.EX.002 | Submission of Shop Drawings For Excavation and Setting out | 0.27 | 2025-10-16 | 2025-10-23 | 2025-10-16 | 2025-10-23 | 6.38 | 0%
F.E.Z1.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 1.77 | 0%
F.E.Z1.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 1.46 | 0%
F.E.Z1.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 1.46 | 0%
F.E.Z2.F1.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For Public Spaces | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 2.77 | 0%
F.E.Z2.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 6.81 | 0%
F.E.Z5.F2.3F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 3.62 | 0%
F.E.Z6.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 2.58 | 0%
F.E.Z6.HV.2F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 2.58 | 0%
F.E.Z7.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 1.62 | 0%
F.E.Z7.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 1.81 | 0%
F.E.Z8.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 4.85 | 0%
F.E.Z8.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 4.85 | 0%
F.E.Z8.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 4.88 | 0%
F.E.Z8.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 7.31 | 0%
F.E.Z8.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 3.96 | 0%
F.E.Z1.F1.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For Public Spaces | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 2.73 | 0%
F.E.Z6.F2.2F.WL.002 | Submission of Shop Drawings For Wall Finishes For Guest Rooms | 0.27 | 2025-10-18 | 2025-10-25 | 2025-10-18 | 2025-10-25 | 2.96 | 0%
F.E.Z6.F2.2F.WA.004 | Review and Approve Shop Drawings For Waterproofing For Guest Rooms | 0.73 | 2025-10-18 | 2025-11-08 | 2025-10-18 | 2025-11-08 | 3.23 | 0%
F.E.Z2.F1.BF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.73 | 2025-10-19 | 2025-11-09 | 2025-10-19 | 2025-11-09 | 3.19 | 0%
F.E.Z2.F1.LG.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.73 | 2025-10-19 | 2025-11-09 | 2025-10-19 | 2025-11-09 | 3.77 | 0%
F.E.Z2.HV.LG.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-19 | 2025-11-09 | 2025-10-19 | 2025-11-09 | 3.42 | 0%
F.E.Z2.FF.LG.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-19 | 2025-11-09 | 2025-10-19 | 2025-11-09 | 3.88 | 0%
F.E.Z5.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-19 | 2025-11-09 | 2025-10-19 | 2025-11-09 | 2.23 | 0%
F.E.Z6.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-10-19 | 2025-10-26 | 2025-10-19 | 2025-10-26 | 6.5 | 0%
F.E.Z8.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-10-19 | 2025-10-26 | 2025-10-19 | 2025-10-26 | 6.42 | 0%
F.E.Z6.F2.2F.RP.002 | Submission of Shop Drawings For RCP For Guest Rooms | 0.27 | 2025-10-19 | 2025-10-26 | 2025-10-19 | 2025-10-26 | 3.31 | 0%
F.E.Z1.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 5.38 | 0%
R.E.GE.EX.GE.PO.002 | Submission of Shop Drawings For Pools and Water Features | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 2.12 | 0%
F.E.Z6.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 2.88 | 0%
F.E.Z6.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 3.96 | 0%
F.E.Z7.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 1.73 | 0%
F.E.Z8.AR.BF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 3 | 0%
F.E.Z8.HV.BF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 3.08 | 0%
F.E.Z8.FF.BF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 3.42 | 0%
F.E.Z9.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 2.77 | 0%
F.E.Z9.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 3 | 0%
F.E.Z7.F1.GF.WA.002 | Submission of Shop Drawings For Waterproofing For Public Spaces | 0.27 | 2025-10-20 | 2025-10-27 | 2025-10-20 | 2025-10-27 | 2.04 | 0%
R.E.VL.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 2.04 | 0%
R.E.VL.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 2.04 | 0%
R.E.VL.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 2.04 | 0%
R.E.VL.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-10-20 | 2025-11-10 | 2025-10-20 | 2025-11-10 | 2.04 | 0%
F.E.Z1.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-21 | 2025-10-28 | 2025-10-21 | 2025-10-28 | 1.96 | 0%
F.E.Z1.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 3.08 | 0%
F.E.Z1.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 2.85 | 0%
F.E.Z2.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 3.42 | 0%
F.E.Z2.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 3.42 | 0%
F.E.Z2.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 3.04 | 0%
F.E.Z3.LV.BF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-10-21 | 2025-10-28 | 2025-10-21 | 2025-10-28 | 4.62 | 0%
F.E.Z5.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 6.73 | 0%
F.E.Z6.FF.2F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 3.27 | 0%
F.E.Z8.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-10-21 | 2025-10-28 | 2025-10-21 | 2025-10-28 | 6.42 | 0%
F.E.Z1.F1.BF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.73 | 2025-10-21 | 2025-11-11 | 2025-10-21 | 2025-11-11 | 3.12 | 0%
F.E.Z1.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 5 | 0%
F.E.Z3.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-10-22 | 2025-11-12 | 2025-10-22 | 2025-11-12 | 4.38 | 0%
F.E.Z6.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-10-22 | 2025-11-12 | 2025-10-22 | 2025-11-12 | 3.27 | 0%
F.E.Z9.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 2.85 | 0%
F.E.Z9.HV.GF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 2.77 | 0%
F.E.Z9.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 2.81 | 0%
F.E.Z9.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 2.81 | 0%
F.E.Z9.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 6.77 | 0%
F.E.Z4.F2.2F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-10-22 | 2025-11-12 | 2025-10-22 | 2025-11-12 | 3.62 | 0%
F.E.Z5.F2.2F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-10-22 | 2025-11-12 | 2025-10-22 | 2025-11-12 | 4.46 | 0%
F.E.Z8.F1.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For Public Spaces | 0.27 | 2025-10-22 | 2025-10-29 | 2025-10-22 | 2025-10-29 | 3.35 | 0%
F.E.Z1.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 6.27 | 0%
F.E.Z1.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 2.77 | 0%
F.E.Z1.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 2.65 | 0%
R.E.4B.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 5.81 | 0%
R.E.4B.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 5.81 | 0%
R.E.4B.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 5.81 | 0%
F.E.Z2.F1.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 2.73 | 0%
F.E.Z2.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 2.81 | 0%
F.E.Z2.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 2.85 | 0%
F.E.Z2.F1.LG.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 3.77 | 0%
F.E.Z6.HV.2F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 2.69 | 0%
F.E.Z8.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 3.12 | 0%
F.E.Z8.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 3.46 | 0%
F.E.Z8.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 3.69 | 0%
F.E.Z8.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 7 | 0%
F.E.Z9.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 2.81 | 0%
F.E.Z8.F1.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.73 | 2025-10-23 | 2025-11-13 | 2025-10-23 | 2025-11-13 | 3.23 | 0%
R.E.6B.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 5.96 | 0%
R.E.6B.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 5.96 | 0%
R.E.6B.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-10-23 | 2025-10-30 | 2025-10-23 | 2025-10-30 | 5.96 | 0%
F.E.Z1.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 1.85 | 0%
F.E.Z1.AR.GF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2.08 | 0%
F.E.Z1.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 4.92 | 0%
F.E.Z1.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 7.08 | 0%
F.E.Z1.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-25 | 2025-11-15 | 2025-10-25 | 2025-11-15 | 2.92 | 0%
F.E.Z3.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 3.15 | 0%
F.E.Z3.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 3.96 | 0%
F.E.Z6.AR.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2.5 | 0%
F.E.Z6.HV.BF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2.46 | 0%
F.E.Z6.FF.BF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2.69 | 0%
F.E.Z7.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 1.31 | 0%
F.E.Z8.AR.1F.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 3.58 | 0%
F.E.Z8.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-10-25 | 2025-11-15 | 2025-10-25 | 2025-11-15 | 2.85 | 0%
F.E.Z8.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-25 | 2025-11-15 | 2025-10-25 | 2025-11-15 | 2.85 | 0%
F.E.Z8.HV.1F.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-25 | 2025-11-15 | 2025-10-25 | 2025-11-15 | 2.92 | 0%
F.E.Z8.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-10-25 | 2025-11-15 | 2025-10-25 | 2025-11-15 | 3.54 | 0%
F.E.Z9.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2.58 | 0%
F.E.Z9.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 2.81 | 0%
F.E.Z9.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-10-25 | 2025-11-01 | 2025-10-25 | 2025-11-01 | 3.73 | 0%
R.E.SS.ST.FO.EX.004 | Review and Approve Shop Drawings For Excavation and Setting out | 0.73 | 2025-10-25 | 2025-11-15 | 2025-10-25 | 2025-11-15 | 6.38 | 0%
F.E.Z1.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-10-26 | 2025-11-02 | 2025-10-26 | 2025-11-02 | 1.69 | 0%
F.E.Z1.HV.RF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-26 | 2025-11-02 | 2025-10-26 | 2025-11-02 | 2.69 | 0%
F.E.Z1.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-10-26 | 2025-11-02 | 2025-10-26 | 2025-11-02 | 2.42 | 0%
F.E.Z1.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 1.77 | 0%
F.E.Z2.F1.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 2.77 | 0%
F.E.Z5.F2.3F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 3.62 | 0%
F.E.Z7.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-26 | 2025-11-02 | 2025-10-26 | 2025-11-02 | 3.35 | 0%
F.E.Z7.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 1.62 | 0%
F.E.Z8.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 4.85 | 0%
F.E.Z8.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 4.85 | 0%
F.E.Z8.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 4.88 | 0%
F.E.Z8.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 7.31 | 0%
F.E.Z1.F1.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 2.73 | 0%
F.E.Z6.F2.2F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Guest Rooms | 0.73 | 2025-10-26 | 2025-11-16 | 2025-10-26 | 2025-11-16 | 2.96 | 0%
F.E.Z6.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-10-27 | 2025-11-17 | 2025-10-27 | 2025-11-17 | 6.5 | 0%
F.E.Z8.AR.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-10-27 | 2025-11-03 | 2025-10-27 | 2025-11-03 | 2.96 | 0%
F.E.Z8.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-10-27 | 2025-11-17 | 2025-10-27 | 2025-11-17 | 6.42 | 0%
F.E.Z6.F2.2F.RP.004 | Review and Approve Shop Drawings For RCP For Guest Rooms | 0.73 | 2025-10-27 | 2025-11-17 | 2025-10-27 | 2025-11-17 | 3.31 | 0%
F.E.Z7.F1.GF.RP.002 | Submission of Shop Drawings For RCP For Public Spaces | 0.27 | 2025-10-27 | 2025-11-03 | 2025-10-27 | 2025-11-03 | 2.23 | 0%
R.E.5B.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-10-27 | 2025-11-03 | 2025-10-27 | 2025-11-03 | 5.42 | 0%
R.E.5B.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-10-27 | 2025-11-03 | 2025-10-27 | 2025-11-03 | 5.42 | 0%
R.E.5B.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-10-27 | 2025-11-03 | 2025-10-27 | 2025-11-03 | 5.42 | 0%
F.E.Z1.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 5.38 | 0%
R.E.4B.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.15 | 0%
R.E.4B.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.15 | 0%
R.E.4B.HV.GF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.12 | 0%
R.E.4B.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.31 | 0%
R.E.4B.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.31 | 0%
R.E.4B.HV.1F.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.27 | 0%
R.E.GE.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 2.12 | 0%
F.E.Z3.LV.2F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 3.85 | 0%
F.E.Z6.F2.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 3.62 | 0%
F.E.Z6.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 2.88 | 0%
F.E.Z8.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 3 | 0%
F.E.Z8.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 3.08 | 0%
F.E.Z8.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 3.42 | 0%
F.E.Z7.F1.GF.WL.002 | Submission of Shop Drawings For Wall Finishes For Public Spaces | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 1.92 | 0%
F.E.Z7.F1.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing For Public Spaces | 0.73 | 2025-10-28 | 2025-11-18 | 2025-10-28 | 2025-11-18 | 2.04 | 0%
R.E.5B.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 5.81 | 0%
R.E.5B.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 5.81 | 0%
R.E.5B.HV.GF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 5.77 | 0%
R.E.5B.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.08 | 0%
R.E.5B.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.08 | 0%
R.E.5B.HV.1F.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.04 | 0%
R.E.6B.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.15 | 0%
R.E.6B.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.15 | 0%
R.E.6B.HV.GF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.12 | 0%
R.E.6B.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.42 | 0%
R.E.6B.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.42 | 0%
R.E.6B.HV.1F.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-10-28 | 2025-11-04 | 2025-10-28 | 2025-11-04 | 6.38 | 0%
F.E.Z1.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-10-29 | 2025-11-19 | 2025-10-29 | 2025-11-19 | 1.96 | 0%
F.E.Z2.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-10-29 | 2025-11-05 | 2025-10-29 | 2025-11-05 | 6.92 | 0%
F.E.Z3.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-10-29 | 2025-11-19 | 2025-10-29 | 2025-11-19 | 4.62 | 0%
F.E.Z8.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-10-29 | 2025-11-19 | 2025-10-29 | 2025-11-19 | 6.42 | 0%
F.E.Z1.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 5 | 0%
F.E.Z3.LV.BF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-10-30 | 2025-11-06 | 2025-10-30 | 2025-11-06 | 4.65 | 0%
F.E.Z3.LV.BF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-10-30 | 2025-11-06 | 2025-10-30 | 2025-11-06 | 4.65 | 0%
F.E.Z4.LV.2F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-10-30 | 2025-11-06 | 2025-10-30 | 2025-11-06 | 4.42 | 0%
F.E.Z5.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-10-30 | 2025-11-06 | 2025-10-30 | 2025-11-06 | 4.77 | 0%
F.E.Z9.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 2.85 | 0%
F.E.Z9.HV.GF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 2.77 | 0%
F.E.Z9.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 2.81 | 0%
F.E.Z9.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 2.81 | 0%
F.E.Z9.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 6.77 | 0%
F.E.Z8.F1.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.73 | 2025-10-30 | 2025-11-20 | 2025-10-30 | 2025-11-20 | 3.35 | 0%
F.E.Z1.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 6.08 | 0%
F.E.Z1.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 6.27 | 0%
R.E.4B.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 5.81 | 0%
R.E.4B.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 5.81 | 0%
R.E.4B.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 5.81 | 0%
F.E.Z2.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 5.73 | 0%
F.E.Z2.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 6.35 | 0%
F.E.Z2.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 6.92 | 0%
F.E.Z3.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 3.96 | 0%
F.E.Z3.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 6.92 | 0%
F.E.Z6.HV.2F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 2.69 | 0%
F.E.Z8.AR.1F.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 2.96 | 0%
F.E.Z8.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 2.81 | 0%
F.E.Z8.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-11-01 | 2025-11-08 | 2025-11-01 | 2025-11-08 | 3.12 | 0%
F.E.Z8.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 3.12 | 0%
F.E.Z8.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 7 | 0%
F.E.Z9.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 2.81 | 0%
R.E.6B.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 5.96 | 0%
R.E.6B.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 5.96 | 0%
R.E.6B.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-11-01 | 2025-11-22 | 2025-11-01 | 2025-11-22 | 5.96 | 0%
F.E.Z1.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 1.85 | 0%
F.E.Z1.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 2.08 | 0%
F.E.Z1.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 4.92 | 0%
F.E.Z1.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 7.08 | 0%
F.E.Z3.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-02 | 2025-11-09 | 2025-11-02 | 2025-11-09 | 2.88 | 0%
F.E.Z3.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 3.15 | 0%
F.E.Z3.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 3.96 | 0%
F.E.Z6.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 2.5 | 0%
F.E.Z6.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 2.46 | 0%
F.E.Z6.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 2.69 | 0%
F.E.Z7.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-11-02 | 2025-11-09 | 2025-11-02 | 2025-11-09 | 1.81 | 0%
F.E.Z7.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 1.31 | 0%
F.E.Z8.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 3.58 | 0%
F.E.Z9.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 2.58 | 0%
F.E.Z9.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 2.81 | 0%
F.E.Z9.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-11-02 | 2025-11-23 | 2025-11-02 | 2025-11-23 | 3.73 | 0%
F.E.Z1.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-10 | 1.96 | 0%
F.E.Z1.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-03 | 2025-11-24 | 2025-11-03 | 2025-11-24 | 1.69 | 0%
F.E.Z1.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-03 | 2025-11-24 | 2025-11-03 | 2025-11-24 | 2.69 | 0%
F.E.Z1.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-03 | 2025-11-24 | 2025-11-03 | 2025-11-24 | 2.42 | 0%
F.E.Z3.EL.2F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-10 | 5.31 | 0%
F.E.Z6.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-10 | 6.08 | 0%
F.E.Z7.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-03 | 2025-11-24 | 2025-11-03 | 2025-11-24 | 3.35 | 0%
R.E.SS.ST.FO.GA.002 | Submission of Shop Drawings For Foundation General arrangement | 0.27 | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-10 | 6.38 | 0%
R.E.SS.ST.FO.SR.002 | Submission of Shop Drawings For Foundation Steel Reinforcement | 0.27 | 2025-11-03 | 2025-11-10 | 2025-11-03 | 2025-11-10 | 6.38 | 0%
F.E.Z4.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-04 | 2025-11-11 | 2025-11-04 | 2025-11-11 | 4.27 | 0%
F.E.Z7.PL.BF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-11-04 | 2025-11-11 | 2025-11-04 | 2025-11-11 | 1.65 | 0%
F.E.Z8.AR.1F.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-11-04 | 2025-11-11 | 2025-11-04 | 2025-11-11 | 3 | 0%
F.E.Z8.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-04 | 2025-11-25 | 2025-11-04 | 2025-11-25 | 2.96 | 0%
F.E.Z7.F1.GF.RP.004 | Review and Approve Shop Drawings For RCP For Public Spaces | 0.73 | 2025-11-04 | 2025-11-25 | 2025-11-04 | 2025-11-25 | 2.23 | 0%
R.E.5B.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-11-04 | 2025-11-25 | 2025-11-04 | 2025-11-25 | 5.42 | 0%
R.E.5B.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-11-04 | 2025-11-25 | 2025-11-04 | 2025-11-25 | 5.42 | 0%
R.E.5B.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-11-04 | 2025-11-25 | 2025-11-04 | 2025-11-25 | 5.42 | 0%
R.E.4B.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.15 | 0%
R.E.4B.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.15 | 0%
R.E.4B.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.12 | 0%
R.E.4B.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.31 | 0%
R.E.4B.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.31 | 0%
R.E.4B.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.27 | 0%
F.E.Z3.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 3.85 | 0%
F.E.Z4.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 4.58 | 0%
F.E.Z5.LV.2F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 4.23 | 0%
F.E.Z5.AR.RF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 3.5 | 0%
F.E.Z6.F2.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 3.62 | 0%
F.E.Z9.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 2.65 | 0%
F.E.Z7.F1.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For Public Spaces | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 1.92 | 0%
R.E.5B.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 5.81 | 0%
R.E.5B.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 5.81 | 0%
R.E.5B.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 5.77 | 0%
R.E.5B.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.08 | 0%
R.E.5B.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.08 | 0%
R.E.5B.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.04 | 0%
R.E.6B.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.15 | 0%
R.E.6B.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.15 | 0%
R.E.6B.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.12 | 0%
R.E.6B.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.42 | 0%
R.E.6B.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.42 | 0%
R.E.6B.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-05 | 2025-11-26 | 2025-11-05 | 2025-11-26 | 6.38 | 0%
R.E.VL.ST.1F.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 2.04 | 0%
R.E.VL.ST.1F.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-11-05 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 2.04 | 0%
F.E.Z2.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-11-06 | 2025-11-27 | 2025-11-06 | 2025-11-27 | 6.92 | 0%
F.E.Z5.F2.3F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-11-06 | 2025-11-13 | 2025-11-06 | 2025-11-13 | 3.69 | 0%
F.E.Z7.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-06 | 2025-11-13 | 2025-11-06 | 2025-11-13 | 1.35 | 0%
F.E.Z7.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-11-06 | 2025-11-13 | 2025-11-06 | 2025-11-13 | 3.42 | 0%
R.E.4B.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.69 | 0%
R.E.4B.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.85 | 0%
F.E.Z2.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 3.19 | 0%
F.E.Z2.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.92 | 0%
F.E.Z3.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 4.88 | 0%
F.E.Z3.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-08 | 2025-11-29 | 2025-11-08 | 2025-11-29 | 4.65 | 0%
F.E.Z3.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-11-08 | 2025-11-29 | 2025-11-08 | 2025-11-29 | 4.65 | 0%
F.E.Z4.EL.LG.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 3.73 | 0%
F.E.Z4.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 6.69 | 0%
F.E.Z4.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-08 | 2025-11-29 | 2025-11-08 | 2025-11-29 | 4.42 | 0%
F.E.Z5.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 6.69 | 0%
F.E.Z5.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-08 | 2025-11-29 | 2025-11-08 | 2025-11-29 | 4.77 | 0%
F.E.Z6.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 2.27 | 0%
F.E.Z6.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 6.96 | 0%
F.E.Z7.DR.BF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 1.54 | 0%
F.E.Z7.HV.RF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 3 | 0%
F.E.Z7.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 4.58 | 0%
F.E.Z7.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 4.77 | 0%
F.E.Z1.F1.BF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Public Spaces | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 3.12 | 0%
R.E.5B.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.35 | 0%
R.E.5B.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.62 | 0%
R.E.6B.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.69 | 0%
R.E.6B.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-15 | 5.96 | 0%
F.E.Z1.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 6.08 | 0%
R.E.4B.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 5.92 | 0%
R.E.4B.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 5.92 | 0%
R.E.4B.HV.RF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 5.88 | 0%
R.E.4B.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 5.81 | 0%
F.E.Z2.F1.LG.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Public Spaces | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 4.04 | 0%
F.E.Z2.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 5.73 | 0%
F.E.Z2.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 6.35 | 0%
F.E.Z2.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 6.92 | 0%
F.E.Z3.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 3.96 | 0%
F.E.Z3.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 6.92 | 0%
F.E.Z7.AR.BF.WA.002 | Submission of Shop Drawings For Waterproofing For BOH | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 2.12 | 0%
F.E.Z8.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 2.96 | 0%
F.E.Z8.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 2.81 | 0%
F.E.Z8.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-11-09 | 2025-11-30 | 2025-11-09 | 2025-11-30 | 3.12 | 0%
R.E.6B.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 6.08 | 0%
R.E.6B.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 6.08 | 0%
R.E.6B.HV.RF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 6.04 | 0%
R.E.6B.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-09 | 2025-11-16 | 2025-11-09 | 2025-11-16 | 5.96 | 0%
F.E.Z3.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | 3.08 | 0%
F.E.Z3.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-10 | 2025-12-01 | 2025-11-10 | 2025-12-01 | 2.88 | 0%
F.E.Z4.LV.LG.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | 4.27 | 0%
F.E.Z7.HV.BF.CF.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | 1.54 | 0%
F.E.Z7.EL.BF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | 1.35 | 0%
F.E.Z7.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-11-10 | 2025-12-01 | 2025-11-10 | 2025-12-01 | 1.81 | 0%
F.E.Z1.F1.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For Public Spaces | 0.27 | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | 3.04 | 0%
F.E.Z1.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-11-11 | 2025-12-02 | 2025-11-11 | 2025-12-02 | 1.96 | 0%
F.E.Z2.F1.LG.FL.002 | Submission of Shop Drawings For Floor Finishes For Public Spaces | 0.27 | 2025-11-11 | 2025-11-18 | 2025-11-11 | 2025-11-18 | 3.58 | 0%
F.E.Z3.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-11 | 2025-12-02 | 2025-11-11 | 2025-12-02 | 5.31 | 0%
F.E.Z6.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-11-11 | 2025-12-02 | 2025-11-11 | 2025-12-02 | 6.08 | 0%
F.E.Z7.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-11 | 2025-11-18 | 2025-11-11 | 2025-11-18 | 2.31 | 0%
R.E.SS.ST.FO.GA.004 | Review and Approve Shop Drawings For Foundation General arrangement | 0.73 | 2025-11-11 | 2025-12-02 | 2025-11-11 | 2025-12-02 | 6.38 | 0%
R.E.SS.ST.FO.SR.004 | Review and Approve Shop Drawings For Foundation Steel Reinforcement | 0.73 | 2025-11-11 | 2025-12-02 | 2025-11-11 | 2025-12-02 | 6.38 | 0%
F.E.Z1.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-19 | 3.27 | 0%
F.E.Z4.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-12 | 2025-12-03 | 2025-11-12 | 2025-12-03 | 4.27 | 0%
F.E.Z7.PL.BF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-12 | 2025-12-03 | 2025-11-12 | 2025-12-03 | 1.65 | 0%
F.E.Z8.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-19 | 6.54 | 0%
F.E.Z8.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-12 | 2025-12-03 | 2025-11-12 | 2025-12-03 | 3 | 0%
R.E.5B.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-19 | 5.54 | 0%
R.E.5B.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-19 | 5.54 | 0%
R.E.5B.HV.RF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-19 | 5.5 | 0%
R.E.5B.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2025-11-12 | 2025-11-19 | 2025-11-12 | 2025-11-19 | 5.42 | 0%
F.E.Z1.AR.BF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-11-13 | 2025-11-20 | 2025-11-13 | 2025-11-20 | 2.92 | 0%
F.E.Z3.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-13 | 2025-11-20 | 2025-11-13 | 2025-11-20 | 3.65 | 0%
F.E.Z4.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-13 | 2025-12-04 | 2025-11-13 | 2025-12-04 | 4.58 | 0%
F.E.Z5.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-13 | 2025-12-04 | 2025-11-13 | 2025-12-04 | 4.23 | 0%
F.E.Z5.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-11-13 | 2025-12-04 | 2025-11-13 | 2025-12-04 | 3.5 | 0%
F.E.Z9.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-13 | 2025-11-20 | 2025-11-13 | 2025-11-20 | 2.77 | 0%
F.E.Z9.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-11-13 | 2025-11-20 | 2025-11-13 | 2025-11-20 | 3.46 | 0%
F.E.Z9.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-11-13 | 2025-12-04 | 2025-11-13 | 2025-12-04 | 2.65 | 0%
R.E.VL.ST.1F.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-11-13 | 2025-12-04 | 2025-11-13 | 2025-12-04 | 2.04 | 0%
R.E.VL.ST.1F.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-11-13 | 2025-12-04 | 2025-11-13 | 2025-12-04 | 2.04 | 0%
F.E.Z1.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-11-15 | 2025-11-22 | 2025-11-15 | 2025-11-22 | 2.96 | 0%
F.E.Z4.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2025-11-15 | 2025-11-22 | 2025-11-15 | 2025-11-22 | 4.38 | 0%
F.E.Z4.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-15 | 2025-11-22 | 2025-11-15 | 2025-11-22 | 3.62 | 0%
F.E.Z5.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-15 | 2025-11-22 | 2025-11-15 | 2025-11-22 | 3.81 | 0%
F.E.Z5.F2.3F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-11-15 | 2025-12-06 | 2025-11-15 | 2025-12-06 | 3.69 | 0%
F.E.Z6.F2.1F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-11-15 | 2025-11-22 | 2025-11-15 | 2025-11-22 | 2.23 | 0%
F.E.Z7.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-15 | 2025-12-06 | 2025-11-15 | 2025-12-06 | 1.35 | 0%
F.E.Z7.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-11-15 | 2025-12-06 | 2025-11-15 | 2025-12-06 | 3.42 | 0%
F.E.Z3.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2025-11-15 | 2025-11-22 | 2025-11-15 | 2025-11-22 | 2.35 | 0%
R.E.4B.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.69 | 0%
R.E.4B.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.85 | 0%
F.E.Z2.F1.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For Public Spaces | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 2.81 | 0%
F.E.Z2.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 8.04 | 0%
F.E.Z2.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 3.19 | 0%
F.E.Z2.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.92 | 0%
F.E.Z3.LV.2F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 3.58 | 0%
F.E.Z3.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 4.88 | 0%
F.E.Z4.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 4.58 | 0%
F.E.Z4.EL.LG.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 3.73 | 0%
F.E.Z4.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 6.69 | 0%
F.E.Z5.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 6.69 | 0%
F.E.Z6.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 2.85 | 0%
F.E.Z6.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 2.27 | 0%
F.E.Z6.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 6.96 | 0%
F.E.Z7.DR.BF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 1.54 | 0%
F.E.Z7.HV.RF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 3 | 0%
F.E.Z7.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 4.58 | 0%
F.E.Z7.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 4.77 | 0%
F.E.Z8.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 5.85 | 0%
F.E.Z1.F1.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 3.12 | 0%
F.E.Z6.F2.2F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.27 | 2025-11-16 | 2025-11-23 | 2025-11-16 | 2025-11-23 | 3.85 | 0%
R.E.5B.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.35 | 0%
R.E.5B.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.62 | 0%
R.E.6B.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.69 | 0%
R.E.6B.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-16 | 2025-12-07 | 2025-11-16 | 2025-12-07 | 5.96 | 0%
R.E.4B.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 5.92 | 0%
R.E.4B.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 5.92 | 0%
R.E.4B.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 5.88 | 0%
R.E.4B.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 5.81 | 0%
F.E.Z2.F1.LG.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 4.04 | 0%
F.E.Z5.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-24 | 2.38 | 0%
F.E.Z7.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-11-17 | 2025-11-24 | 2025-11-17 | 2025-11-24 | 3.62 | 0%
F.E.Z7.AR.BF.WA.004 | Review and Approve Shop Drawings For Waterproofing For BOH | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 2.12 | 0%
R.E.6B.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 6.08 | 0%
R.E.6B.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 6.08 | 0%
R.E.6B.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 6.04 | 0%
R.E.6B.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-17 | 2025-12-08 | 2025-11-17 | 2025-12-08 | 5.96 | 0%
F.E.Z3.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-18 | 2025-12-09 | 2025-11-18 | 2025-12-09 | 3.08 | 0%
F.E.Z4.LV.LG.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-18 | 2025-11-25 | 2025-11-18 | 2025-11-25 | 4.31 | 0%
F.E.Z4.LV.LG.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-18 | 2025-11-25 | 2025-11-18 | 2025-11-25 | 4.31 | 0%
F.E.Z4.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-18 | 2025-11-25 | 2025-11-18 | 2025-11-25 | 3.35 | 0%
F.E.Z4.LV.2F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-18 | 2025-11-25 | 2025-11-18 | 2025-11-25 | 4.15 | 0%
F.E.Z4.LV.LG.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-11-18 | 2025-12-09 | 2025-11-18 | 2025-12-09 | 4.27 | 0%
F.E.Z5.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-18 | 2025-11-25 | 2025-11-18 | 2025-11-25 | 4.5 | 0%
F.E.Z6.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-18 | 2025-11-25 | 2025-11-18 | 2025-11-25 | 6.35 | 0%
F.E.Z7.HV.BF.CF.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-18 | 2025-12-09 | 2025-11-18 | 2025-12-09 | 1.54 | 0%
F.E.Z7.EL.BF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-18 | 2025-12-09 | 2025-11-18 | 2025-12-09 | 1.35 | 0%
F.E.Z1.F1.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.73 | 2025-11-18 | 2025-12-09 | 2025-11-18 | 2025-12-09 | 3.04 | 0%
F.E.Z2.F1.LG.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.73 | 2025-11-19 | 2025-12-10 | 2025-11-19 | 2025-12-10 | 3.58 | 0%
F.E.Z3.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-26 | 3.12 | 0%
F.E.Z3.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-26 | 3.12 | 0%
F.E.Z3.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-26 | 3.73 | 0%
F.E.Z3.EX.GE.PO.002 | Submission of Shop Drawings For Pools and Water Features | 0.27 | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-26 | 5.85 | 0%
F.E.Z4.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-26 | 4.54 | 0%
F.E.Z7.AR.BF.RP.002 | Submission of Shop Drawings For RCP For BOH | 0.27 | 2025-11-19 | 2025-11-26 | 2025-11-19 | 2025-11-26 | 2.15 | 0%
F.E.Z7.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-19 | 2025-12-10 | 2025-11-19 | 2025-12-10 | 2.31 | 0%
F.E.Z1.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-20 | 2025-12-11 | 2025-11-20 | 2025-12-11 | 3.27 | 0%
F.E.Z4.EL.2F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-20 | 2025-11-27 | 2025-11-20 | 2025-11-27 | 4.65 | 0%
F.E.Z5.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-20 | 2025-11-27 | 2025-11-20 | 2025-11-27 | 3.62 | 0%
F.E.Z8.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-11-20 | 2025-12-11 | 2025-11-20 | 2025-12-11 | 6.54 | 0%
R.E.5B.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2025-11-20 | 2025-12-11 | 2025-11-20 | 2025-12-11 | 5.54 | 0%
R.E.5B.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2025-11-20 | 2025-12-11 | 2025-11-20 | 2025-12-11 | 5.54 | 0%
R.E.5B.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2025-11-20 | 2025-12-11 | 2025-11-20 | 2025-12-11 | 5.5 | 0%
R.E.5B.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2025-11-20 | 2025-12-11 | 2025-11-20 | 2025-12-11 | 5.42 | 0%
F.E.Z1.AR.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-29 | 2.65 | 0%
F.E.Z1.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-11-22 | 2025-12-13 | 2025-11-22 | 2025-12-13 | 2.92 | 0%
R.E.GE.EX.GE.DR.002 | Submission of Shop Drawings For Drainage Network | 0.27 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-29 | 3.69 | 0%
R.E.GE.EX.GE.SW.002 | Submission of Shop Drawings For Storm Water Network | 0.27 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-29 | 5.54 | 0%
F.E.Z2.F1.LG.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Public Spaces | 0.27 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-29 | 3.65 | 0%
F.E.Z3.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-29 | 3.38 | 0%
F.E.Z3.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-22 | 2025-12-13 | 2025-11-22 | 2025-12-13 | 3.65 | 0%
F.E.Z7.AR.BF.WL.002 | Submission of Shop Drawings For Wall Finishes For BOH | 0.27 | 2025-11-22 | 2025-11-29 | 2025-11-22 | 2025-11-29 | 1.85 | 0%
F.E.Z9.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-11-22 | 2025-12-13 | 2025-11-22 | 2025-12-13 | 2.77 | 0%
F.E.Z9.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-11-22 | 2025-12-13 | 2025-11-22 | 2025-12-13 | 3.46 | 0%
F.E.Z1.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-23 | 2025-12-14 | 2025-11-23 | 2025-12-14 | 2.96 | 0%
F.E.Z4.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-23 | 2025-11-30 | 2025-11-23 | 2025-11-30 | 4 | 0%
F.E.Z4.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2025-11-23 | 2025-12-14 | 2025-11-23 | 2025-12-14 | 4.38 | 0%
F.E.Z4.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-23 | 2025-12-14 | 2025-11-23 | 2025-12-14 | 3.62 | 0%
F.E.Z5.EL.LG.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-11-23 | 2025-11-30 | 2025-11-23 | 2025-11-30 | 3.23 | 0%
F.E.Z5.LV.3F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-23 | 2025-11-30 | 2025-11-23 | 2025-11-30 | 3.65 | 0%
F.E.Z5.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-23 | 2025-12-14 | 2025-11-23 | 2025-12-14 | 3.81 | 0%
F.E.Z6.F2.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-11-23 | 2025-12-14 | 2025-11-23 | 2025-12-14 | 2.23 | 0%
F.E.Z8.F1.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Public Spaces | 0.27 | 2025-11-23 | 2025-11-30 | 2025-11-23 | 2025-11-30 | 5.04 | 0%
F.E.Z3.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2025-11-23 | 2025-12-14 | 2025-11-23 | 2025-12-14 | 2.35 | 0%
F.E.Z1.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-11-24 | 2025-12-01 | 2025-11-24 | 2025-12-01 | 2.58 | 0%
F.E.Z2.F1.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 2.81 | 0%
F.E.Z2.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 8.04 | 0%
F.E.Z3.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 3.58 | 0%
F.E.Z4.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 4.58 | 0%
F.E.Z5.LV.2F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-11-24 | 2025-12-01 | 2025-11-24 | 2025-12-01 | 3.96 | 0%
F.E.Z6.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 2.85 | 0%
F.E.Z8.AR.BF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-11-24 | 2025-12-01 | 2025-11-24 | 2025-12-01 | 3.27 | 0%
F.E.Z8.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 5.85 | 0%
F.E.Z6.F2.2F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Guest Rooms | 0.73 | 2025-11-24 | 2025-12-15 | 2025-11-24 | 2025-12-15 | 3.85 | 0%
R.E.4B.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 5.81 | 0%
R.E.4B.AR.1F.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 5.96 | 0%
F.E.Z3.LV.BF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 4.15 | 0%
F.E.Z3.LV.2F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 3.27 | 0%
F.E.Z4.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 4.27 | 0%
F.E.Z5.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-11-25 | 2025-12-16 | 2025-11-25 | 2025-12-16 | 2.38 | 0%
F.E.Z7.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-25 | 2025-12-16 | 2025-11-25 | 2025-12-16 | 3.62 | 0%
F.E.Z9.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 5.23 | 0%
R.E.5B.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 5.46 | 0%
R.E.5B.AR.1F.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 5.73 | 0%
R.E.6B.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 5.81 | 0%
R.E.6B.AR.1F.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-25 | 2025-12-02 | 2025-11-25 | 2025-12-02 | 6.08 | 0%
R.E.4B.AR.RF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-12-03 | 5.92 | 0%
F.E.Z4.LV.LG.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-26 | 2025-12-17 | 2025-11-26 | 2025-12-17 | 4.31 | 0%
F.E.Z4.LV.LG.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-11-26 | 2025-12-17 | 2025-11-26 | 2025-12-17 | 4.31 | 0%
F.E.Z4.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-26 | 2025-12-17 | 2025-11-26 | 2025-12-17 | 3.35 | 0%
F.E.Z4.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-26 | 2025-12-17 | 2025-11-26 | 2025-12-17 | 4.15 | 0%
F.E.Z5.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-12-03 | 4 | 0%
F.E.Z5.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-26 | 2025-12-17 | 2025-11-26 | 2025-12-17 | 4.5 | 0%
F.E.Z6.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-11-26 | 2025-12-17 | 2025-11-26 | 2025-12-17 | 6.35 | 0%
F.E.Z7.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-12-03 | 4.58 | 0%
F.E.Z8.F1.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For Public Spaces | 0.27 | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-12-03 | 3.5 | 0%
R.E.6B.AR.RF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-26 | 2025-12-03 | 2025-11-26 | 2025-12-03 | 6.08 | 0%
F.E.Z1.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-12-04 | 6.04 | 0%
F.E.Z3.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-27 | 2025-12-18 | 2025-11-27 | 2025-12-18 | 3.12 | 0%
F.E.Z3.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-11-27 | 2025-12-18 | 2025-11-27 | 2025-12-18 | 3.12 | 0%
F.E.Z3.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-11-27 | 2025-12-18 | 2025-11-27 | 2025-12-18 | 3.73 | 0%
F.E.Z3.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.73 | 2025-11-27 | 2025-12-18 | 2025-11-27 | 2025-12-18 | 5.85 | 0%
F.E.Z4.LV.2F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-12-04 | 3.85 | 0%
F.E.Z4.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-27 | 2025-12-18 | 2025-11-27 | 2025-12-18 | 4.54 | 0%
F.E.Z5.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-27 | 2025-12-04 | 2025-11-27 | 2025-12-04 | 4.19 | 0%
F.E.Z7.AR.BF.RP.004 | Review and Approve Shop Drawings For RCP For BOH | 0.73 | 2025-11-27 | 2025-12-18 | 2025-11-27 | 2025-12-18 | 2.15 | 0%
F.E.Z2.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z3.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.15 | 0%
F.E.Z3.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.35 | 0%
F.E.Z3.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.5 | 0%
F.E.Z3.F2.2F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.12 | 0%
F.E.Z3.AR.2F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.35 | 0%
F.E.Z3.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.35 | 0%
F.E.Z3.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.46 | 0%
F.E.Z3.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z4.AR.LG.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.AR.2F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-29 | 2025-12-20 | 2025-11-29 | 2025-12-20 | 4.65 | 0%
F.E.Z5.AR.LG.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.LV.LG.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 4.58 | 0%
F.E.Z5.F2.GF.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z5.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.96 | 0%
F.E.Z5.F2.1F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z5.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 4.5 | 0%
F.E.Z5.AR.2F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.LV.2F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 4.5 | 0%
F.E.Z5.F2.3F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z5.AR.3F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.LV.3F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 4.5 | 0%
F.E.Z5.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 4.5 | 0%
F.E.Z5.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.81 | 0%
F.E.Z5.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z5.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-11-29 | 2025-12-20 | 2025-11-29 | 2025-12-20 | 3.62 | 0%
F.E.Z7.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 1.54 | 0%
F.E.Z7.HV.BF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 1.31 | 0%
F.E.Z7.FF.BF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 1.62 | 0%
F.E.Z7.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.88 | 0%
F.E.Z7.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 5.42 | 0%
F.E.Z8.AR.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 3.27 | 0%
F.E.Z8.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 7.08 | 0%
F.E.Z4.F2.LG.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z4.F2.GF.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z4.F2.1F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z4.F2.2F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z5.F2.LG.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z5.F2.2F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-11-29 | 2025-12-06 | 2025-11-29 | 2025-12-06 | 6.62 | 0%
F.E.Z1.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-11-30 | 2025-12-21 | 2025-11-30 | 2025-12-21 | 2.65 | 0%
R.E.GE.EX.GE.DR.004 | Review and Approve Shop Drawings For Drainage Network | 0.73 | 2025-11-30 | 2025-12-21 | 2025-11-30 | 2025-12-21 | 3.69 | 0%
R.E.GE.EX.GE.SW.004 | Review and Approve Shop Drawings For Storm Water Network | 0.73 | 2025-11-30 | 2025-12-21 | 2025-11-30 | 2025-12-21 | 5.54 | 0%
F.E.Z2.F1.LG.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.73 | 2025-11-30 | 2025-12-21 | 2025-11-30 | 2025-12-21 | 3.65 | 0%
F.E.Z3.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-11-30 | 2025-12-21 | 2025-11-30 | 2025-12-21 | 3.38 | 0%
F.E.Z7.AR.BF.WL.004 | Review and Approve Shop Drawings For Wall Finishes For BOH | 0.73 | 2025-11-30 | 2025-12-21 | 2025-11-30 | 2025-12-21 | 1.85 | 0%
F.E.Z8.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2025-11-30 | 2025-12-07 | 2025-11-30 | 2025-12-07 | 7.58 | 0%
F.E.Z6.F2.2F.FL.002 | Submission of Shop Drawings For Floor Finishes For Guest Rooms | 0.27 | 2025-11-30 | 2025-12-07 | 2025-11-30 | 2025-12-07 | 2.81 | 0%
R.E.5B.AR.RF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2025-11-30 | 2025-12-07 | 2025-11-30 | 2025-12-07 | 5.54 | 0%
R.E.VL.ST.RF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-11-30 | 2025-12-07 | 2025-11-30 | 2025-12-07 | 2.04 | 0%
R.E.VL.ST.RF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-11-30 | 2025-12-07 | 2025-11-30 | 2025-12-07 | 2.04 | 0%
R.E.4B.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.77 | 0%
R.E.4B.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.92 | 0%
R.E.4B.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.92 | 0%
F.E.Z2.F1.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Public Spaces | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 2.88 | 0%
F.E.Z4.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-01 | 2025-12-22 | 2025-12-01 | 2025-12-22 | 4 | 0%
F.E.Z5.EL.LG.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-01 | 2025-12-22 | 2025-12-01 | 2025-12-22 | 3.23 | 0%
F.E.Z5.LV.3F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-01 | 2025-12-22 | 2025-12-01 | 2025-12-22 | 3.65 | 0%
F.E.Z8.F1.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.73 | 2025-12-01 | 2025-12-22 | 2025-12-01 | 2025-12-22 | 5.04 | 0%
R.E.5B.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.42 | 0%
R.E.5B.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.69 | 0%
R.E.5B.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.65 | 0%
R.E.6B.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 5.77 | 0%
R.E.6B.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 6.04 | 0%
R.E.6B.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2025-12-01 | 2025-12-08 | 2025-12-01 | 2025-12-08 | 6.08 | 0%
F.E.Z1.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-09 | 5 | 0%
F.E.Z1.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-12-02 | 2025-12-23 | 2025-12-02 | 2025-12-23 | 2.58 | 0%
F.E.Z4.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-09 | 3.69 | 0%
F.E.Z5.LV.3F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-09 | 3.69 | 0%
F.E.Z5.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-02 | 2025-12-23 | 2025-12-02 | 2025-12-23 | 3.96 | 0%
F.E.Z8.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-12-02 | 2025-12-23 | 2025-12-02 | 2025-12-23 | 3.27 | 0%
F.E.Z7.F1.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For Public Spaces | 0.27 | 2025-12-02 | 2025-12-09 | 2025-12-02 | 2025-12-09 | 2.58 | 0%
F.E.Z1.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-10 | 1.65 | 0%
F.E.Z1.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-10 | 3.42 | 0%
F.E.Z1.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-10 | 3.42 | 0%
R.E.4B.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 5.81 | 0%
R.E.4B.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 5.96 | 0%
F.E.Z3.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 4.15 | 0%
F.E.Z3.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 3.27 | 0%
F.E.Z4.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 4.27 | 0%
F.E.Z5.EL.2F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-10 | 4.23 | 0%
F.E.Z5.LV.2F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-10 | 3.65 | 0%
F.E.Z8.AR.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-12-03 | 2025-12-10 | 2025-12-03 | 2025-12-10 | 3.15 | 0%
F.E.Z9.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 5.23 | 0%
R.E.5B.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 5.46 | 0%
R.E.5B.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 5.73 | 0%
R.E.6B.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 5.81 | 0%
R.E.6B.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-03 | 2025-12-24 | 2025-12-03 | 2025-12-24 | 6.08 | 0%
R.E.4B.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-04 | 2025-12-25 | 2025-12-04 | 2025-12-25 | 5.92 | 0%
F.E.Z4.LV.LG.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-04 | 2025-12-11 | 2025-12-04 | 2025-12-11 | 4.38 | 0%
F.E.Z5.AR.RF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-12-04 | 2025-12-11 | 2025-12-04 | 2025-12-11 | 2.54 | 0%
F.E.Z5.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2025-12-04 | 2025-12-25 | 2025-12-04 | 2025-12-25 | 4 | 0%
F.E.Z7.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-04 | 2025-12-25 | 2025-12-04 | 2025-12-25 | 4.58 | 0%
F.E.Z8.F1.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.73 | 2025-12-04 | 2025-12-25 | 2025-12-04 | 2025-12-25 | 3.5 | 0%
R.E.6B.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-04 | 2025-12-25 | 2025-12-04 | 2025-12-25 | 6.08 | 0%
F.E.Z1.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2025-12-06 | 2025-12-27 | 2025-12-06 | 2025-12-27 | 6.04 | 0%
F.E.Z4.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-06 | 2025-12-13 | 2025-12-06 | 2025-12-13 | 3.54 | 0%
F.E.Z4.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-06 | 2025-12-27 | 2025-12-06 | 2025-12-27 | 3.85 | 0%
F.E.Z5.LV.3F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-06 | 2025-12-13 | 2025-12-06 | 2025-12-13 | 3.58 | 0%
F.E.Z5.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-06 | 2025-12-27 | 2025-12-06 | 2025-12-27 | 4.19 | 0%
F.E.Z2.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z3.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.15 | 0%
F.E.Z3.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.35 | 0%
F.E.Z3.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.5 | 0%
F.E.Z3.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.12 | 0%
F.E.Z3.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.35 | 0%
F.E.Z3.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.35 | 0%
F.E.Z3.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.46 | 0%
F.E.Z3.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z4.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z4.AR.LG.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z4.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z4.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z4.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z4.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-07 | 2025-12-14 | 2025-12-07 | 2025-12-14 | 4 | 0%
F.E.Z5.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-07 | 2025-12-14 | 2025-12-07 | 2025-12-14 | 4 | 0%
F.E.Z5.AR.LG.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.LG.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 4.58 | 0%
F.E.Z5.F2.GF.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z5.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.96 | 0%
F.E.Z5.F2.1F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z5.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 4.5 | 0%
F.E.Z5.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 4.5 | 0%
F.E.Z5.F2.3F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z5.AR.3F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.3F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 4.5 | 0%
F.E.Z5.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z5.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 4.5 | 0%
F.E.Z5.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.81 | 0%
F.E.Z5.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z6.AR.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-12-07 | 2025-12-14 | 2025-12-07 | 2025-12-14 | 2.35 | 0%
F.E.Z7.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 1.54 | 0%
F.E.Z7.HV.BF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 1.31 | 0%
F.E.Z7.FF.BF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 1.62 | 0%
F.E.Z7.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.88 | 0%
F.E.Z7.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 5.42 | 0%
F.E.Z8.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 3.27 | 0%
F.E.Z8.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 7.08 | 0%
F.E.Z4.F2.LG.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z4.F2.GF.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z4.F2.1F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z4.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z5.F2.LG.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z5.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2025-12-07 | 2025-12-28 | 2025-12-07 | 2025-12-28 | 6.62 | 0%
F.E.Z1.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-15 | 2.58 | 0%
F.E.Z3.LV.2F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-15 | 3.54 | 0%
F.E.Z4.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-15 | 4.19 | 0%
F.E.Z5.LV.LG.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-08 | 2025-12-15 | 2025-12-08 | 2025-12-15 | 3.35 | 0%
F.E.Z8.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2025-12-08 | 2025-12-29 | 2025-12-08 | 2025-12-29 | 7.58 | 0%
F.E.Z6.F2.2F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Guest Rooms | 0.73 | 2025-12-08 | 2025-12-29 | 2025-12-08 | 2025-12-29 | 2.81 | 0%
R.E.5B.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2025-12-08 | 2025-12-29 | 2025-12-08 | 2025-12-29 | 5.54 | 0%
R.E.VL.ST.RF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-12-08 | 2025-12-29 | 2025-12-08 | 2025-12-29 | 2.04 | 0%
R.E.VL.ST.RF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-12-08 | 2025-12-29 | 2025-12-08 | 2025-12-29 | 2.04 | 0%
R.E.4B.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.77 | 0%
R.E.4B.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.92 | 0%
R.E.4B.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.92 | 0%
F.E.Z2.F1.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 2.88 | 0%
F.E.Z1.F1.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Public Spaces | 0.27 | 2025-12-09 | 2025-12-16 | 2025-12-09 | 2025-12-16 | 2.73 | 0%
F.E.Z7.F1.GF.FL.002 | Submission of Shop Drawings For Floor Finishes For Public Spaces | 0.27 | 2025-12-09 | 2025-12-16 | 2025-12-09 | 2025-12-16 | 1.73 | 0%
R.E.5B.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.42 | 0%
R.E.5B.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.69 | 0%
R.E.5B.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.65 | 0%
R.E.6B.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 5.77 | 0%
R.E.6B.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 6.04 | 0%
R.E.6B.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2025-12-09 | 2025-12-30 | 2025-12-09 | 2025-12-30 | 6.08 | 0%
F.E.Z1.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-12-10 | 2025-12-31 | 2025-12-10 | 2025-12-31 | 5 | 0%
R.E.4B.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.31 | 0%
R.E.4B.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.46 | 0%
R.E.4B.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.46 | 0%
F.E.Z2.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 3.69 | 0%
F.E.Z4.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-10 | 2025-12-31 | 2025-12-10 | 2025-12-31 | 3.69 | 0%
F.E.Z5.LV.3F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-10 | 2025-12-31 | 2025-12-10 | 2025-12-31 | 3.69 | 0%
F.E.Z8.AR.1F.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 2.92 | 0%
F.E.Z7.F1.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For Public Spaces | 0.73 | 2025-12-10 | 2025-12-31 | 2025-12-10 | 2025-12-31 | 2.58 | 0%
R.E.5B.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 4.96 | 0%
R.E.5B.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.23 | 0%
R.E.5B.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.19 | 0%
R.E.6B.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.31 | 0%
R.E.6B.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.58 | 0%
R.E.6B.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2025-12-10 | 2025-12-17 | 2025-12-10 | 2025-12-17 | 5.62 | 0%
F.E.Z1.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-12-11 | 2026-01-01 | 2025-12-11 | 2026-01-01 | 1.65 | 0%
F.E.Z1.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-11 | 2026-01-01 | 2025-12-11 | 2026-01-01 | 3.42 | 0%
F.E.Z1.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-11 | 2026-01-01 | 2025-12-11 | 2026-01-01 | 3.42 | 0%
F.E.Z2.EL.LG.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-11 | 2025-12-18 | 2025-12-11 | 2025-12-18 | 3.73 | 0%
F.E.Z5.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-11 | 2026-01-01 | 2025-12-11 | 2026-01-01 | 4.23 | 0%
F.E.Z5.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-11 | 2026-01-01 | 2025-12-11 | 2026-01-01 | 3.65 | 0%
F.E.Z7.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-12-11 | 2025-12-18 | 2025-12-11 | 2025-12-18 | 3.19 | 0%
F.E.Z8.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2025-12-11 | 2026-01-01 | 2025-12-11 | 2026-01-01 | 3.15 | 0%
F.E.Z1.AR.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-12-13 | 2025-12-20 | 2025-12-13 | 2025-12-20 | 2.62 | 0%
F.E.Z1.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-13 | 2025-12-20 | 2025-12-13 | 2025-12-20 | 3.46 | 0%
F.E.Z1.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-13 | 2025-12-20 | 2025-12-13 | 2025-12-20 | 3.46 | 0%
F.E.Z4.LV.LG.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-13 | 2026-01-03 | 2025-12-13 | 2026-01-03 | 4.38 | 0%
F.E.Z5.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-12-13 | 2026-01-03 | 2025-12-13 | 2026-01-03 | 2.54 | 0%
F.E.Z6.F2.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-12-13 | 2025-12-20 | 2025-12-13 | 2025-12-20 | 2.15 | 0%
F.E.Z4.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-14 | 2026-01-04 | 2025-12-14 | 2026-01-04 | 3.54 | 0%
F.E.Z5.LV.3F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-14 | 2026-01-04 | 2025-12-14 | 2026-01-04 | 3.58 | 0%
F.E.Z5.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-15 | 2026-01-05 | 2025-12-15 | 2026-01-05 | 4 | 0%
F.E.Z5.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-15 | 2026-01-05 | 2025-12-15 | 2026-01-05 | 4 | 0%
F.E.Z6.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-12-15 | 2026-01-05 | 2025-12-15 | 2026-01-05 | 2.35 | 0%
R.E.SS.ST.CL.SR.002 | Submission of Shop Drawings For Columns Steel Reinforcement | 0.27 | 2025-12-15 | 2025-12-22 | 2025-12-15 | 2025-12-22 | 6.38 | 0%
F.E.Z1.EL.BF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 2.88 | 0%
F.E.Z1.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-12-16 | 2026-01-06 | 2025-12-16 | 2026-01-06 | 2.58 | 0%
F.E.Z3.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-16 | 2026-01-06 | 2025-12-16 | 2026-01-06 | 3.54 | 0%
F.E.Z4.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 3.58 | 0%
F.E.Z4.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 3.58 | 0%
F.E.Z4.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-16 | 2026-01-06 | 2025-12-16 | 2026-01-06 | 4.19 | 0%
F.E.Z5.LV.LG.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 3.38 | 0%
F.E.Z5.LV.LG.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 3.38 | 0%
F.E.Z5.LV.LG.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-16 | 2026-01-06 | 2025-12-16 | 2026-01-06 | 3.35 | 0%
F.E.Z7.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 3.31 | 0%
R.E.VL.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 2.62 | 0%
R.E.VL.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 2.62 | 0%
R.E.VL.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2025-12-16 | 2025-12-23 | 2025-12-16 | 2025-12-23 | 2.62 | 0%
R.E.GE.EX.GE.PW.002 | Submission of Shop Drawings For Potable Water Network | 0.27 | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-24 | 4.54 | 0%
R.E.GE.EX.GE.FF.002 | Submission of Shop Drawings For Fire Fighting Network | 0.27 | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-24 | 4.54 | 0%
F.E.Z1.F1.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.73 | 2025-12-17 | 2026-01-07 | 2025-12-17 | 2026-01-07 | 2.73 | 0%
F.E.Z7.F1.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For Public Spaces | 0.73 | 2025-12-17 | 2026-01-07 | 2025-12-17 | 2026-01-07 | 1.73 | 0%
F.E.Z8.F1.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Public Spaces | 0.27 | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-24 | 3.58 | 0%
F.E.Z1.LV.BF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.96 | 0%
F.E.Z1.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.27 | 0%
R.E.4B.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.31 | 0%
R.E.4B.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.46 | 0%
R.E.4B.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.46 | 0%
F.E.Z2.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 3.69 | 0%
F.E.Z6.LV.BF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.73 | 0%
F.E.Z6.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.54 | 0%
F.E.Z7.LV.BF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.58 | 0%
F.E.Z7.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.58 | 0%
F.E.Z7.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.23 | 0%
F.E.Z7.EX.GE.LP.002 | Submission of Shop Drawings For LPG System Installation | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 4.58 | 0%
F.E.Z7.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 5.04 | 0%
F.E.Z8.AR.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-12-18 | 2025-12-25 | 2025-12-18 | 2025-12-25 | 3.23 | 0%
F.E.Z8.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 2.92 | 0%
R.E.5B.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 4.96 | 0%
R.E.5B.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.23 | 0%
R.E.5B.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.19 | 0%
R.E.6B.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.31 | 0%
R.E.6B.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.58 | 0%
R.E.6B.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2025-12-18 | 2026-01-08 | 2025-12-18 | 2026-01-08 | 5.62 | 0%
R.E.GE.EX.GE.ED.002 | Submission of Shop Drawings For Electricity Distribution Network | 0.27 | 2025-12-20 | 2025-12-27 | 2025-12-20 | 2025-12-27 | 4.54 | 0%
F.E.Z2.LV.LG.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-20 | 2025-12-27 | 2025-12-20 | 2025-12-27 | 3.77 | 0%
F.E.Z2.LV.LG.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-20 | 2025-12-27 | 2025-12-20 | 2025-12-27 | 3.77 | 0%
F.E.Z2.EL.LG.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-20 | 2026-01-10 | 2025-12-20 | 2026-01-10 | 3.73 | 0%
F.E.Z5.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-20 | 2025-12-27 | 2025-12-20 | 2025-12-27 | 2.77 | 0%
F.E.Z7.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2025-12-20 | 2026-01-10 | 2025-12-20 | 2026-01-10 | 3.19 | 0%
F.E.Z9.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-20 | 2025-12-27 | 2025-12-20 | 2025-12-27 | 2.88 | 0%
F.E.Z1.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-12-21 | 2026-01-11 | 2025-12-21 | 2026-01-11 | 2.62 | 0%
F.E.Z1.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-21 | 2026-01-11 | 2025-12-21 | 2026-01-11 | 3.46 | 0%
F.E.Z1.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-21 | 2026-01-11 | 2025-12-21 | 2026-01-11 | 3.46 | 0%
F.E.Z5.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-21 | 2025-12-28 | 2025-12-21 | 2025-12-28 | 3.85 | 0%
F.E.Z6.LV.2F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-21 | 2025-12-28 | 2025-12-21 | 2025-12-28 | 3.19 | 0%
F.E.Z6.LV.2F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-21 | 2025-12-28 | 2025-12-21 | 2025-12-28 | 3.19 | 0%
F.E.Z6.F2.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-12-21 | 2026-01-11 | 2025-12-21 | 2026-01-11 | 2.15 | 0%
R.E.GE.EX.GE.LV.002 | Submission of Shop Drawings For ELV Network | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 4.54 | 0%
F.E.Z2.EL.BF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 3 | 0%
F.E.Z6.F2.2F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 2.73 | 0%
R.E.SS.ST.ST.GA.002 | Submission of Shop Drawings For Stairs General arrangement | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 6.38 | 0%
R.E.SS.ST.ST.SR.002 | Submission of Shop Drawings For Stairs Steel Reinforcement | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 6.38 | 0%
R.E.SS.ST.GF.GA.002 | Submission of Shop Drawings For Slab & beams General arrangement | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 6.38 | 0%
R.E.SS.ST.GF.SR.002 | Submission of Shop Drawings For Slab & Beams Steel Reinforcement | 0.27 | 2025-12-22 | 2025-12-29 | 2025-12-22 | 2025-12-29 | 6.38 | 0%
F.E.Z4.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-30 | 3.69 | 0%
F.E.Z5.EL.3F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-23 | 2025-12-30 | 2025-12-23 | 2025-12-30 | 3.58 | 0%
R.E.SS.ST.CL.SR.004 | Review and Approve Shop Drawings For Columns Steel Reinforcement | 0.73 | 2025-12-23 | 2026-01-13 | 2025-12-23 | 2026-01-13 | 6.38 | 0%
F.E.Z1.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 2.88 | 0%
F.E.Z3.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-24 | 2025-12-31 | 2025-12-24 | 2025-12-31 | 3.62 | 0%
F.E.Z4.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 3.58 | 0%
F.E.Z4.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 3.58 | 0%
F.E.Z5.LV.LG.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 3.38 | 0%
F.E.Z5.LV.LG.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 3.38 | 0%
F.E.Z7.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 3.31 | 0%
R.E.VL.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 2.62 | 0%
R.E.VL.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 2.62 | 0%
R.E.VL.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2025-12-24 | 2026-01-14 | 2025-12-24 | 2026-01-14 | 2.62 | 0%
R.E.GE.EX.GE.PW.004 | Review and Approve Shop Drawings For Potable Water Network | 0.73 | 2025-12-25 | 2026-01-15 | 2025-12-25 | 2026-01-15 | 4.54 | 0%
R.E.GE.EX.GE.FF.004 | Review and Approve Shop Drawings For Fire Fighting Network | 0.73 | 2025-12-25 | 2026-01-15 | 2025-12-25 | 2026-01-15 | 4.54 | 0%
F.E.Z2.LV.LG.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-25 | 2026-01-01 | 2025-12-25 | 2026-01-01 | 3.81 | 0%
F.E.Z2.LV.LG.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-25 | 2026-01-01 | 2025-12-25 | 2026-01-01 | 3.81 | 0%
F.E.Z4.LV.2F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-25 | 2026-01-01 | 2025-12-25 | 2026-01-01 | 3.62 | 0%
F.E.Z7.AR.BF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details For BOH | 0.27 | 2025-12-25 | 2026-01-01 | 2025-12-25 | 2026-01-01 | 1.85 | 0%
F.E.Z7.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-25 | 2026-01-01 | 2025-12-25 | 2026-01-01 | 3.35 | 0%
F.E.Z7.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-25 | 2026-01-01 | 2025-12-25 | 2026-01-01 | 3.35 | 0%
F.E.Z8.F1.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.73 | 2025-12-25 | 2026-01-15 | 2025-12-25 | 2026-01-15 | 3.58 | 0%
F.E.Z1.LV.BF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-27 | 2026-01-03 | 2025-12-27 | 2026-01-03 | 3 | 0%
F.E.Z1.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-12-27 | 2026-01-03 | 2025-12-27 | 2026-01-03 | 1.58 | 0%
F.E.Z1.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.96 | 0%
F.E.Z1.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.27 | 0%
F.E.Z4.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-27 | 2026-01-03 | 2025-12-27 | 2026-01-03 | 3.62 | 0%
F.E.Z6.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.73 | 0%
F.E.Z6.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.54 | 0%
F.E.Z7.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.58 | 0%
F.E.Z7.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.58 | 0%
F.E.Z7.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.23 | 0%
F.E.Z7.EX.GE.LP.004 | Review and Approve Shop Drawings For LPG System Installation | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 4.58 | 0%
F.E.Z7.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 5.04 | 0%
F.E.Z8.AR.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2025-12-27 | 2026-01-03 | 2025-12-27 | 2026-01-03 | 3.04 | 0%
F.E.Z8.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2025-12-27 | 2026-01-17 | 2025-12-27 | 2026-01-17 | 3.23 | 0%
F.E.Z1.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-28 | 2026-01-04 | 2025-12-28 | 2026-01-04 | 3.5 | 0%
F.E.Z1.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2025-12-28 | 2026-01-04 | 2025-12-28 | 2026-01-04 | 6.12 | 0%
R.E.GE.EX.GE.ED.004 | Review and Approve Shop Drawings For Electricity Distribution Network | 0.73 | 2025-12-28 | 2026-01-18 | 2025-12-28 | 2026-01-18 | 4.54 | 0%
F.E.Z2.LV.LG.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-28 | 2026-01-18 | 2025-12-28 | 2026-01-18 | 3.77 | 0%
F.E.Z2.LV.LG.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-28 | 2026-01-18 | 2025-12-28 | 2026-01-18 | 3.77 | 0%
F.E.Z5.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2025-12-28 | 2026-01-04 | 2025-12-28 | 2026-01-04 | 5.65 | 0%
F.E.Z5.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-28 | 2026-01-18 | 2025-12-28 | 2026-01-18 | 2.77 | 0%
F.E.Z6.F2.1F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-12-28 | 2026-01-04 | 2025-12-28 | 2026-01-04 | 6.15 | 0%
F.E.Z9.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-28 | 2026-01-18 | 2025-12-28 | 2026-01-18 | 2.88 | 0%
F.E.Z6.F2.GF.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-12-28 | 2026-01-04 | 2025-12-28 | 2026-01-04 | 6.15 | 0%
F.E.Z6.F2.2F.ID.002 | Submission of Shop Drawings For ID Details For Guest Rooms | 0.27 | 2025-12-28 | 2026-01-04 | 2025-12-28 | 2026-01-04 | 6.15 | 0%
F.E.Z2.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-29 | 2026-01-05 | 2025-12-29 | 2026-01-05 | 3.46 | 0%
F.E.Z2.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-29 | 2026-01-05 | 2025-12-29 | 2026-01-05 | 3.46 | 0%
F.E.Z5.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-29 | 2026-01-05 | 2025-12-29 | 2026-01-05 | 2.81 | 0%
F.E.Z5.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-29 | 2026-01-19 | 2025-12-29 | 2026-01-19 | 3.85 | 0%
F.E.Z6.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-29 | 2026-01-19 | 2025-12-29 | 2026-01-19 | 3.19 | 0%
F.E.Z6.LV.2F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2025-12-29 | 2026-01-19 | 2025-12-29 | 2026-01-19 | 3.19 | 0%
F.E.Z8.EL.BF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2025-12-29 | 2026-01-05 | 2025-12-29 | 2026-01-05 | 3.31 | 0%
R.E.GE.EX.GE.LV.004 | Review and Approve Shop Drawings For ELV Network | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 4.54 | 0%
F.E.Z2.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 3 | 0%
F.E.Z6.LV.2F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2025-12-30 | 2026-01-06 | 2025-12-30 | 2026-01-06 | 3.23 | 0%
F.E.Z6.LV.2F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2025-12-30 | 2026-01-06 | 2025-12-30 | 2026-01-06 | 3.23 | 0%
F.E.Z6.F2.2F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Guest Rooms | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 2.73 | 0%
R.E.SS.ST.ST.GA.004 | Review and Approve Shop Drawings For Stairs General arrangement | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 6.38 | 0%
R.E.SS.ST.ST.SR.004 | Review and Approve Shop Drawings For Stairs Steel Reinforcement | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 6.38 | 0%
R.E.SS.ST.GF.GA.004 | Review and Approve Shop Drawings For Slab & beams General arrangement | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 6.38 | 0%
R.E.SS.ST.GF.SR.004 | Review and Approve Shop Drawings For Slab & Beams Steel Reinforcement | 0.73 | 2025-12-30 | 2026-01-20 | 2025-12-30 | 2026-01-20 | 6.38 | 0%
F.E.Z4.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2025-12-31 | 2026-01-21 | 2025-12-31 | 2026-01-21 | 3.69 | 0%
F.E.Z5.EL.3F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2025-12-31 | 2026-01-21 | 2025-12-31 | 2026-01-21 | 3.58 | 0%
F.E.Z7.AR.BF.FL.002 | Submission of Shop Drawings For Floor Finishes For BOH | 0.27 | 2025-12-31 | 2026-01-07 | 2025-12-31 | 2026-01-07 | 1.65 | 0%
F.E.Z8.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2025-12-31 | 2026-01-07 | 2025-12-31 | 2026-01-07 | 3.15 | 0%
F.E.Z8.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2025-12-31 | 2026-01-07 | 2025-12-31 | 2026-01-07 | 3.15 | 0%
F.E.Z2.LV.BF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 3.04 | 0%
F.E.Z2.LV.BF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 3.04 | 0%
F.E.Z3.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-01 | 2026-01-22 | 2026-01-01 | 2026-01-22 | 3.62 | 0%
F.E.Z8.EX.GE.PO.002 | Submission of Shop Drawings For Pools and Water Features | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 5.31 | 0%
F.E.Z7.F1.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For Public Spaces | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 1.65 | 0%
R.E.VL.PL.GF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 4.38 | 0%
R.E.VL.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 4.38 | 0%
R.E.VL.HV.GF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 4.35 | 0%
R.E.VL.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 4.27 | 0%
R.E.SS.AR.GF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 6.38 | 0%
R.E.SS.AR.GF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 6.38 | 0%
R.E.SS.AR.GF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2026-01-01 | 2026-01-08 | 2026-01-01 | 2026-01-08 | 6.38 | 0%
F.E.Z2.LV.LG.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-03 | 2026-01-24 | 2026-01-03 | 2026-01-24 | 3.81 | 0%
F.E.Z2.LV.LG.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-03 | 2026-01-24 | 2026-01-03 | 2026-01-24 | 3.81 | 0%
F.E.Z4.LV.2F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-03 | 2026-01-24 | 2026-01-03 | 2026-01-24 | 3.62 | 0%
F.E.Z6.AR.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2026-01-03 | 2026-01-10 | 2026-01-03 | 2026-01-10 | 2.31 | 0%
F.E.Z6.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-03 | 2026-01-10 | 2026-01-03 | 2026-01-10 | 2.65 | 0%
F.E.Z7.AR.BF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details For BOH | 0.73 | 2026-01-03 | 2026-01-24 | 2026-01-03 | 2026-01-24 | 1.85 | 0%
F.E.Z7.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-03 | 2026-01-24 | 2026-01-03 | 2026-01-24 | 3.35 | 0%
F.E.Z7.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-03 | 2026-01-24 | 2026-01-03 | 2026-01-24 | 3.35 | 0%
F.E.Z8.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-01-03 | 2026-01-10 | 2026-01-03 | 2026-01-10 | 3.65 | 0%
F.E.Z8.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-03 | 2026-01-10 | 2026-01-03 | 2026-01-10 | 3.65 | 0%
F.E.Z9.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-03 | 2026-01-10 | 2026-01-03 | 2026-01-10 | 2.96 | 0%
F.E.Z1.LV.BF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 3.08 | 0%
F.E.Z1.LV.BF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 3.08 | 0%
F.E.Z1.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-04 | 2026-01-25 | 2026-01-04 | 2026-01-25 | 3 | 0%
F.E.Z1.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2026-01-04 | 2026-01-25 | 2026-01-04 | 2026-01-25 | 1.58 | 0%
R.E.4B.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 7.65 | 0%
F.E.Z2.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 3.5 | 0%
F.E.Z2.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 3.5 | 0%
F.E.Z4.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-04 | 2026-01-25 | 2026-01-04 | 2026-01-25 | 3.62 | 0%
F.E.Z8.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2026-01-04 | 2026-01-25 | 2026-01-04 | 2026-01-25 | 3.04 | 0%
R.E.5B.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 7.54 | 0%
R.E.6B.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-01-04 | 2026-01-11 | 2026-01-04 | 2026-01-11 | 7.69 | 0%
F.E.Z1.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-05 | 2026-01-26 | 2026-01-05 | 2026-01-26 | 3.5 | 0%
F.E.Z1.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2026-01-05 | 2026-01-26 | 2026-01-05 | 2026-01-26 | 6.12 | 0%
R.E.GE.EX.GE.EX.002 | Submission of Shop Drawings For External Lighting | 0.27 | 2026-01-05 | 2026-01-12 | 2026-01-05 | 2026-01-12 | 5.23 | 0%
R.E.GE.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2026-01-05 | 2026-01-12 | 2026-01-05 | 2026-01-12 | 6.27 | 0%
F.E.Z5.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-01-05 | 2026-01-26 | 2026-01-05 | 2026-01-26 | 5.65 | 0%
F.E.Z6.F2.1F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2026-01-05 | 2026-01-26 | 2026-01-05 | 2026-01-26 | 6.15 | 0%
F.E.Z6.F2.GF.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2026-01-05 | 2026-01-26 | 2026-01-05 | 2026-01-26 | 6.15 | 0%
F.E.Z6.F2.2F.ID.004 | Review and Approve Shop Drawings For ID Details For Guest Rooms | 0.73 | 2026-01-05 | 2026-01-26 | 2026-01-05 | 2026-01-26 | 6.15 | 0%
F.E.Z2.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-06 | 2026-01-27 | 2026-01-06 | 2026-01-27 | 3.46 | 0%
F.E.Z2.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-06 | 2026-01-27 | 2026-01-06 | 2026-01-27 | 3.46 | 0%
F.E.Z5.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-06 | 2026-01-27 | 2026-01-06 | 2026-01-27 | 2.81 | 0%
F.E.Z8.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-06 | 2026-01-27 | 2026-01-06 | 2026-01-27 | 3.31 | 0%
F.E.Z3.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 6.31 | 0%
F.E.Z4.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 6.31 | 0%
F.E.Z6.LV.2F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-07 | 2026-01-28 | 2026-01-07 | 2026-01-28 | 3.23 | 0%
F.E.Z6.LV.2F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-07 | 2026-01-28 | 2026-01-07 | 2026-01-28 | 3.23 | 0%
F.E.Z7.EX.GE.IR.002 | Submission of Shop Drawings For Irrigation Network | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 4.62 | 0%
F.E.Z7.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 5.23 | 0%
F.E.Z8.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 3.69 | 0%
F.E.Z8.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 3.69 | 0%
F.E.Z8.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 3.08 | 0%
F.E.Z7.AR.BF.FL.004 | Review and Approve Shop Drawings For Floor Finishes For BOH | 0.73 | 2026-01-08 | 2026-01-29 | 2026-01-08 | 2026-01-29 | 1.65 | 0%
F.E.Z8.LV.BF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-01-08 | 2026-01-15 | 2026-01-08 | 2026-01-15 | 3.35 | 0%
F.E.Z8.LV.BF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-08 | 2026-01-15 | 2026-01-08 | 2026-01-15 | 3.35 | 0%
F.E.Z8.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-08 | 2026-01-29 | 2026-01-08 | 2026-01-29 | 3.15 | 0%
F.E.Z8.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-08 | 2026-01-29 | 2026-01-08 | 2026-01-29 | 3.15 | 0%
R.E.SS.DR.GF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2026-01-08 | 2026-01-15 | 2026-01-08 | 2026-01-15 | 6.58 | 0%
R.E.SS.HV.GF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2026-01-08 | 2026-01-15 | 2026-01-08 | 2026-01-15 | 6.58 | 0%
F.E.Z2.LV.BF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 3.08 | 0%
F.E.Z2.LV.BF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 3.08 | 0%
F.E.Z2.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 3.04 | 0%
F.E.Z2.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 3.04 | 0%
F.E.Z5.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 6.23 | 0%
F.E.Z8.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 3.19 | 0%
F.E.Z8.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 3.19 | 0%
F.E.Z8.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 5.31 | 0%
F.E.Z9.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 3 | 0%
F.E.Z9.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 3 | 0%
F.E.Z7.F1.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For Public Spaces | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 1.65 | 0%
R.E.VL.AR.1F.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 2.62 | 0%
R.E.VL.AR.1F.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 2.62 | 0%
R.E.VL.AR.1F.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2026-01-10 | 2026-01-17 | 2026-01-10 | 2026-01-17 | 2.62 | 0%
R.E.VL.PL.GF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 4.38 | 0%
R.E.VL.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 4.38 | 0%
R.E.VL.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 4.35 | 0%
R.E.VL.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 4.27 | 0%
R.E.SS.AR.GF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 6.38 | 0%
R.E.SS.AR.GF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 6.38 | 0%
R.E.SS.AR.GF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2026-01-10 | 2026-01-31 | 2026-01-10 | 2026-01-31 | 6.38 | 0%
F.E.Z6.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-11 | 2026-01-18 | 2026-01-11 | 2026-01-18 | 2.77 | 0%
F.E.Z6.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2026-01-11 | 2026-02-01 | 2026-01-11 | 2026-02-01 | 2.31 | 0%
F.E.Z6.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-11 | 2026-02-01 | 2026-01-11 | 2026-02-01 | 2.65 | 0%
F.E.Z8.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-11 | 2026-02-01 | 2026-01-11 | 2026-02-01 | 3.65 | 0%
F.E.Z8.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-11 | 2026-02-01 | 2026-01-11 | 2026-02-01 | 3.65 | 0%
F.E.Z9.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-11 | 2026-02-01 | 2026-01-11 | 2026-02-01 | 2.96 | 0%
F.E.Z1.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 3.08 | 0%
F.E.Z1.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 3.08 | 0%
R.E.4B.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 7.65 | 0%
F.E.Z2.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 3.5 | 0%
F.E.Z2.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 3.5 | 0%
R.E.5B.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 7.54 | 0%
R.E.6B.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-01-12 | 2026-02-02 | 2026-01-12 | 2026-02-02 | 7.69 | 0%
R.E.GE.EX.GE.EX.004 | Review and Approve Shop Drawings For External Lighting | 0.73 | 2026-01-13 | 2026-02-03 | 2026-01-13 | 2026-02-03 | 5.23 | 0%
R.E.GE.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2026-01-13 | 2026-02-03 | 2026-01-13 | 2026-02-03 | 6.27 | 0%
F.E.Z6.EL.BF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-13 | 2026-01-20 | 2026-01-13 | 2026-01-20 | 2.5 | 0%
F.E.Z6.EL.2F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-13 | 2026-01-20 | 2026-01-13 | 2026-01-20 | 2.96 | 0%
F.E.Z7.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-13 | 2026-01-20 | 2026-01-13 | 2026-01-20 | 2.96 | 0%
F.E.Z8.LV.BF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-13 | 2026-01-20 | 2026-01-13 | 2026-01-20 | 3.38 | 0%
F.E.Z8.LV.BF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-13 | 2026-01-20 | 2026-01-13 | 2026-01-20 | 3.38 | 0%
F.E.Z1.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-14 | 2026-01-21 | 2026-01-14 | 2026-01-21 | 1.92 | 0%
R.E.4B.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2026-01-14 | 2026-01-21 | 2026-01-14 | 2026-01-21 | 4.69 | 0%
R.E.5B.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2026-01-14 | 2026-01-21 | 2026-01-14 | 2026-01-21 | 4.54 | 0%
R.E.6B.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2026-01-14 | 2026-01-21 | 2026-01-14 | 2026-01-21 | 4.88 | 0%
F.E.Z1.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-22 | 6.04 | 0%
F.E.Z3.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 6.31 | 0%
F.E.Z4.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 6.31 | 0%
F.E.Z6.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-15 | 2026-01-22 | 2026-01-15 | 2026-01-22 | 2.42 | 0%
F.E.Z7.EX.GE.IR.004 | Review and Approve Shop Drawings For Irrigation Network | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 4.62 | 0%
F.E.Z7.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 5.23 | 0%
F.E.Z8.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 3.69 | 0%
F.E.Z8.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 3.69 | 0%
F.E.Z8.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-15 | 2026-02-05 | 2026-01-15 | 2026-02-05 | 3.08 | 0%
F.E.Z6.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-01-17 | 2026-01-24 | 2026-01-17 | 2026-01-24 | 6 | 0%
F.E.Z8.LV.BF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-17 | 2026-02-07 | 2026-01-17 | 2026-02-07 | 3.35 | 0%
F.E.Z8.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-17 | 2026-02-07 | 2026-01-17 | 2026-02-07 | 3.35 | 0%
R.E.SS.DR.GF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2026-01-17 | 2026-02-07 | 2026-01-17 | 2026-02-07 | 6.58 | 0%
R.E.SS.HV.GF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2026-01-17 | 2026-02-07 | 2026-01-17 | 2026-02-07 | 6.58 | 0%
F.E.Z2.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 3.08 | 0%
F.E.Z2.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 3.08 | 0%
F.E.Z5.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 6.23 | 0%
F.E.Z8.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 3.19 | 0%
F.E.Z8.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 3.19 | 0%
F.E.Z9.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 3 | 0%
F.E.Z9.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 3 | 0%
R.E.VL.AR.1F.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 2.62 | 0%
R.E.VL.AR.1F.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 2.62 | 0%
R.E.VL.AR.1F.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2026-01-18 | 2026-02-08 | 2026-01-18 | 2026-02-08 | 2.62 | 0%
F.E.Z6.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-26 | 2.81 | 0%
F.E.Z6.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-26 | 2.81 | 0%
F.E.Z6.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-19 | 2026-02-09 | 2026-01-19 | 2026-02-09 | 2.77 | 0%
R.E.VL.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-26 | 4.38 | 0%
R.E.VL.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-26 | 4.38 | 0%
R.E.VL.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2026-01-19 | 2026-01-26 | 2026-01-19 | 2026-01-26 | 4.54 | 0%
F.E.Z6.LV.BF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-27 | 2.65 | 0%
R.E.SS.EL.GF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-27 | 6.38 | 0%
F.E.Z5.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-28 | 2.46 | 0%
F.E.Z6.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-21 | 2026-02-11 | 2026-01-21 | 2026-02-11 | 2.5 | 0%
F.E.Z6.EL.2F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-21 | 2026-02-11 | 2026-01-21 | 2026-02-11 | 2.96 | 0%
F.E.Z7.AR.BF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details For BOH | 0.27 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-28 | 1.62 | 0%
F.E.Z7.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-21 | 2026-02-11 | 2026-01-21 | 2026-02-11 | 2.96 | 0%
F.E.Z8.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-28 | 4.46 | 0%
F.E.Z8.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-21 | 2026-02-11 | 2026-01-21 | 2026-02-11 | 3.38 | 0%
F.E.Z8.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-21 | 2026-02-11 | 2026-01-21 | 2026-02-11 | 3.38 | 0%
F.E.Z1.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-22 | 2026-02-14 | 2026-01-22 | 2026-02-14 | 1.92 | 0%
R.E.4B.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-29 | 5.19 | 0%
R.E.4B.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2026-01-22 | 2026-02-14 | 2026-01-22 | 2026-02-14 | 4.69 | 0%
F.E.Z6.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-29 | 2.58 | 0%
F.E.Z6.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-22 | 2026-01-29 | 2026-01-22 | 2026-01-29 | 2.58 | 0%
R.E.5B.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2026-01-22 | 2026-02-14 | 2026-01-22 | 2026-02-14 | 4.54 | 0%
R.E.6B.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2026-01-22 | 2026-02-14 | 2026-01-22 | 2026-02-14 | 4.88 | 0%
F.E.Z1.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-01-24 | 2026-01-31 | 2026-01-24 | 2026-01-31 | 2.08 | 0%
F.E.Z1.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-01-24 | 2026-02-15 | 2026-01-24 | 2026-02-15 | 6.04 | 0%
F.E.Z6.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-24 | 2026-02-15 | 2026-01-24 | 2026-02-15 | 2.42 | 0%
R.E.SS.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2026-01-24 | 2026-01-31 | 2026-01-24 | 2026-01-31 | 6.42 | 0%
F.E.Z6.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-01-25 | 2026-02-16 | 2026-01-25 | 2026-02-16 | 6 | 0%
F.E.Z6.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 5.15 | 0%
R.E.VL.PL.1F.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 3.58 | 0%
R.E.VL.DR.1F.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 3.58 | 0%
R.E.VL.HV.1F.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 3.54 | 0%
R.E.VL.EL.1F.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 3.46 | 0%
F.E.Z1.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.12 | 0%
F.E.Z1.AR.BF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z1.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z1.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z3.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z6.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 4.85 | 0%
F.E.Z6.AR.BF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z6.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z6.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z6.AR.2F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z6.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-01-27 | 2026-02-18 | 2026-01-27 | 2026-02-18 | 2.81 | 0%
F.E.Z6.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-01-27 | 2026-02-18 | 2026-01-27 | 2026-02-18 | 2.81 | 0%
F.E.Z7.AR.BF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z7.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
F.E.Z7.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-01-27 | 2026-02-03 | 2026-01-27 | 2026-02-03 | 5.38 | 0%
R.E.VL.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-01-27 | 2026-02-18 | 2026-01-27 | 2026-02-18 | 4.38 | 0%
R.E.VL.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2026-01-27 | 2026-02-18 | 2026-01-27 | 2026-02-18 | 4.38 | 0%
R.E.VL.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2026-01-27 | 2026-02-18 | 2026-01-27 | 2026-02-18 | 4.54 | 0%
F.E.Z6.LV.BF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-28 | 2026-02-04 | 2026-01-28 | 2026-02-04 | 2.69 | 0%
F.E.Z6.LV.BF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-28 | 2026-02-04 | 2026-01-28 | 2026-02-04 | 2.69 | 0%
F.E.Z6.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-28 | 2026-02-19 | 2026-01-28 | 2026-02-19 | 2.65 | 0%
F.E.Z7.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2026-01-28 | 2026-02-04 | 2026-01-28 | 2026-02-04 | 5.08 | 0%
R.E.SS.EL.GF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2026-01-28 | 2026-02-19 | 2026-01-28 | 2026-02-19 | 6.38 | 0%
F.E.Z5.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-29 | 2026-02-21 | 2026-01-29 | 2026-02-21 | 2.46 | 0%
F.E.Z7.AR.BF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details For BOH | 0.73 | 2026-01-29 | 2026-02-21 | 2026-01-29 | 2026-02-21 | 1.62 | 0%
F.E.Z8.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-01-29 | 2026-02-21 | 2026-01-29 | 2026-02-21 | 4.46 | 0%
R.E.4B.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2026-01-31 | 2026-02-22 | 2026-01-31 | 2026-02-22 | 5.19 | 0%
F.E.Z6.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-01-31 | 2026-02-07 | 2026-01-31 | 2026-02-07 | 2.62 | 0%
F.E.Z6.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-01-31 | 2026-02-07 | 2026-01-31 | 2026-02-07 | 2.62 | 0%
F.E.Z6.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-01-31 | 2026-02-22 | 2026-01-31 | 2026-02-22 | 2.58 | 0%
F.E.Z6.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-01-31 | 2026-02-22 | 2026-01-31 | 2026-02-22 | 2.58 | 0%
F.E.Z7.EL.BF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-31 | 2026-02-07 | 2026-01-31 | 2026-02-07 | 1.69 | 0%
F.E.Z7.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-01-31 | 2026-02-07 | 2026-01-31 | 2026-02-07 | 1.69 | 0%
F.E.Z1.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-02-01 | 2026-02-23 | 2026-02-01 | 2026-02-23 | 2.08 | 0%
R.E.SS.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2026-02-01 | 2026-02-23 | 2026-02-01 | 2026-02-23 | 6.42 | 0%
F.E.Z1.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-02-02 | 2026-02-09 | 2026-02-02 | 2026-02-09 | 2.12 | 0%
F.E.Z1.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-02-02 | 2026-02-09 | 2026-02-02 | 2026-02-09 | 2.12 | 0%
R.E.SS.HV.GF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2026-02-02 | 2026-02-09 | 2026-02-02 | 2026-02-09 | 6.38 | 0%
R.E.SS.FF.GF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2026-02-02 | 2026-02-09 | 2026-02-02 | 2026-02-09 | 6.81 | 0%
F.E.Z6.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2026-02-03 | 2026-02-25 | 2026-02-03 | 2026-02-25 | 5.15 | 0%
F.E.Z7.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-02-03 | 2026-02-10 | 2026-02-03 | 2026-02-10 | 5.42 | 0%
R.E.VL.AR.RF.BW.002 | Submission of Shop Drawings For Blockwork | 0.27 | 2026-02-03 | 2026-02-10 | 2026-02-03 | 2026-02-10 | 2.62 | 0%
R.E.VL.AR.RF.CP.002 | Submission of Shop Drawings For Coordination Plan | 0.27 | 2026-02-03 | 2026-02-10 | 2026-02-03 | 2026-02-10 | 2.62 | 0%
R.E.VL.AR.RF.BU.002 | Submission of Shop Drawings For Builders Works | 0.27 | 2026-02-03 | 2026-02-10 | 2026-02-03 | 2026-02-10 | 2.62 | 0%
R.E.VL.PL.1F.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2026-02-03 | 2026-02-25 | 2026-02-03 | 2026-02-25 | 3.58 | 0%
R.E.VL.DR.1F.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2026-02-03 | 2026-02-25 | 2026-02-03 | 2026-02-25 | 3.58 | 0%
R.E.VL.HV.1F.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2026-02-03 | 2026-02-25 | 2026-02-03 | 2026-02-25 | 3.54 | 0%
R.E.VL.EL.1F.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2026-02-03 | 2026-02-25 | 2026-02-03 | 2026-02-25 | 3.46 | 0%
F.E.Z1.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.12 | 0%
F.E.Z1.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z1.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z1.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z3.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z6.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 4.85 | 0%
F.E.Z6.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z6.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z6.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z6.AR.2F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z7.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z7.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
F.E.Z7.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 5.38 | 0%
R.E.4B.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-02-05 | 2026-02-14 | 2026-02-05 | 2026-02-14 | 3.73 | 0%
F.E.Z6.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-02-05 | 2026-02-28 | 2026-02-05 | 2026-02-28 | 2.69 | 0%
F.E.Z6.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-02-05 | 2026-02-28 | 2026-02-05 | 2026-02-28 | 2.69 | 0%
F.E.Z7.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2026-02-05 | 2026-02-28 | 2026-02-05 | 2026-02-28 | 5.08 | 0%
R.E.5B.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-02-05 | 2026-02-14 | 2026-02-05 | 2026-02-14 | 3.46 | 0%
R.E.6B.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-02-05 | 2026-02-14 | 2026-02-05 | 2026-02-14 | 3.88 | 0%
R.E.SS.AR.GF.RP.002 | Submission of Shop Drawings For Ceiling | 0.27 | 2026-02-05 | 2026-02-14 | 2026-02-05 | 2026-02-14 | 6.85 | 0%
F.E.Z7.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-02-07 | 2026-02-15 | 2026-02-07 | 2026-02-15 | 4.5 | 0%
F.E.Z6.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-02-08 | 2026-03-02 | 2026-02-08 | 2026-03-02 | 2.62 | 0%
F.E.Z6.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-02-08 | 2026-03-02 | 2026-02-08 | 2026-03-02 | 2.62 | 0%
F.E.Z7.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-02-08 | 2026-02-16 | 2026-02-08 | 2026-02-16 | 1.88 | 0%
F.E.Z7.EL.BF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-02-08 | 2026-03-02 | 2026-02-08 | 2026-03-02 | 1.69 | 0%
F.E.Z7.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-02-08 | 2026-03-02 | 2026-02-08 | 2026-03-02 | 1.69 | 0%
R.E.SS.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-02-09 | 2026-02-17 | 2026-02-09 | 2026-02-17 | 9 | 0%
F.E.Z1.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-02-10 | 2026-03-04 | 2026-02-10 | 2026-03-04 | 2.12 | 0%
F.E.Z1.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-02-10 | 2026-03-04 | 2026-02-10 | 2026-03-04 | 2.12 | 0%
R.E.SS.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-02-10 | 2026-02-18 | 2026-02-10 | 2026-02-18 | 6.46 | 0%
R.E.SS.HV.GF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2026-02-10 | 2026-03-04 | 2026-02-10 | 2026-03-04 | 6.38 | 0%
R.E.SS.FF.GF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2026-02-10 | 2026-03-04 | 2026-02-10 | 2026-03-04 | 6.81 | 0%
F.E.Z7.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-02-11 | 2026-03-05 | 2026-02-11 | 2026-03-05 | 5.42 | 0%
R.E.VL.AR.RF.BW.004 | Review and Approve Shop Drawings For Blockwork | 0.73 | 2026-02-11 | 2026-03-05 | 2026-02-11 | 2026-03-05 | 2.62 | 0%
R.E.VL.AR.RF.CP.004 | Review and Approve Shop Drawings For Coordination Plan | 0.73 | 2026-02-11 | 2026-03-05 | 2026-02-11 | 2026-03-05 | 2.62 | 0%
R.E.VL.AR.RF.BU.004 | Review and Approve Shop Drawings For Builders Works | 0.73 | 2026-02-11 | 2026-03-05 | 2026-02-11 | 2026-03-05 | 2.62 | 0%
F.E.Z7.LV.BF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-02-14 | 2026-02-21 | 2026-02-14 | 2026-02-21 | 1.73 | 0%
F.E.Z9.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2026-02-14 | 2026-02-21 | 2026-02-14 | 2026-02-21 | 3.5 | 0%
F.E.Z9.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-02-14 | 2026-02-21 | 2026-02-14 | 2026-02-21 | 4.73 | 0%
R.E.VL.AR.1F.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-02-14 | 2026-02-21 | 2026-02-14 | 2026-02-21 | 3.58 | 0%
R.E.VL.HV.1F.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2026-02-14 | 2026-02-21 | 2026-02-14 | 2026-02-21 | 3.58 | 0%
R.E.VL.FF.1F.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2026-02-14 | 2026-02-21 | 2026-02-14 | 2026-02-21 | 3.73 | 0%
R.E.4B.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-02-15 | 2026-03-08 | 2026-02-15 | 2026-03-08 | 3.73 | 0%
F.E.Z7.EX.GE.PO.002 | Submission of Shop Drawings For Pools and Water Features | 0.27 | 2026-02-15 | 2026-02-22 | 2026-02-15 | 2026-02-22 | 3.92 | 0%
R.E.5B.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-02-15 | 2026-03-08 | 2026-02-15 | 2026-03-08 | 3.46 | 0%
R.E.6B.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-02-15 | 2026-03-08 | 2026-02-15 | 2026-03-08 | 3.88 | 0%
R.E.SS.AR.GF.RP.004 | Review and Approve Shop Drawings For Ceiling | 0.73 | 2026-02-15 | 2026-03-08 | 2026-02-15 | 2026-03-08 | 6.85 | 0%
F.E.Z7.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-02-16 | 2026-03-09 | 2026-02-16 | 2026-03-09 | 4.5 | 0%
F.E.Z8.AR.BF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-23 | 4.77 | 0%
F.E.Z8.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-23 | 4.77 | 0%
F.E.Z8.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-23 | 4.77 | 0%
F.E.Z9.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-23 | 4.5 | 0%
F.E.Z7.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-02-17 | 2026-02-24 | 2026-02-17 | 2026-02-24 | 1.96 | 0%
F.E.Z7.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-02-17 | 2026-02-24 | 2026-02-17 | 2026-02-24 | 1.96 | 0%
F.E.Z7.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-02-17 | 2026-03-10 | 2026-02-17 | 2026-03-10 | 1.88 | 0%
R.E.4B.AR.RF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-02-18 | 2026-02-25 | 2026-02-18 | 2026-02-25 | 3.58 | 0%
R.E.5B.AR.RF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-02-18 | 2026-02-25 | 2026-02-18 | 2026-02-25 | 3.31 | 0%
R.E.6B.AR.RF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-02-18 | 2026-02-25 | 2026-02-18 | 2026-02-25 | 3.73 | 0%
R.E.SS.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-02-18 | 2026-02-25 | 2026-02-18 | 2026-02-25 | 6.46 | 0%
R.E.SS.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-02-18 | 2026-02-25 | 2026-02-18 | 2026-02-25 | 9.23 | 0%
R.E.SS.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-02-18 | 2026-03-11 | 2026-02-18 | 2026-03-11 | 9 | 0%
R.E.SS.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-02-19 | 2026-03-12 | 2026-02-19 | 2026-03-12 | 6.46 | 0%
F.E.Z7.LV.BF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-02-21 | 2026-02-28 | 2026-02-21 | 2026-02-28 | 1.85 | 0%
F.E.Z7.LV.BF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-02-21 | 2026-02-28 | 2026-02-21 | 2026-02-28 | 1.85 | 0%
R.E.VL.PL.RF.WS.002 | Submission of Shop Drawings For Water Supply Network | 0.27 | 2026-02-21 | 2026-02-28 | 2026-02-21 | 2026-02-28 | 2.73 | 0%
R.E.VL.DR.RF.FW.002 | Submission of Shop Drawings For Drainage & Drainage Details | 0.27 | 2026-02-21 | 2026-02-28 | 2026-02-21 | 2026-02-28 | 2.73 | 0%
R.E.VL.HV.RF.CH.002 | Submission of Shop Drawings For Chilled Water Network | 0.27 | 2026-02-21 | 2026-02-28 | 2026-02-21 | 2026-02-28 | 2.69 | 0%
R.E.VL.EL.RF.PW.002 | Submission of Shop Drawings For Power | 0.27 | 2026-02-21 | 2026-02-28 | 2026-02-21 | 2026-02-28 | 2.62 | 0%
F.E.Z7.LV.BF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-02-22 | 2026-03-15 | 2026-02-22 | 2026-03-15 | 1.73 | 0%
F.E.Z9.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2026-02-22 | 2026-03-15 | 2026-02-22 | 2026-03-15 | 3.5 | 0%
F.E.Z9.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-02-22 | 2026-03-15 | 2026-02-22 | 2026-03-15 | 4.73 | 0%
R.E.VL.AR.1F.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-02-22 | 2026-03-15 | 2026-02-22 | 2026-03-15 | 3.58 | 0%
R.E.VL.HV.1F.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2026-02-22 | 2026-03-15 | 2026-02-22 | 2026-03-15 | 3.58 | 0%
R.E.VL.FF.1F.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2026-02-22 | 2026-03-15 | 2026-02-22 | 2026-03-15 | 3.73 | 0%
F.E.Z7.EX.GE.PO.004 | Review and Approve Shop Drawings For Pools and Water Features | 0.73 | 2026-02-23 | 2026-03-16 | 2026-02-23 | 2026-03-16 | 3.92 | 0%
R.E.SS.AR.GF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-03-02 | 7.27 | 0%
R.E.SS.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-02-23 | 2026-03-02 | 2026-02-23 | 2026-03-02 | 7.27 | 0%
F.E.Z8.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-24 | 2026-03-17 | 2026-02-24 | 2026-03-17 | 4.77 | 0%
F.E.Z8.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-24 | 2026-03-17 | 2026-02-24 | 2026-03-17 | 4.77 | 0%
F.E.Z8.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-02-24 | 2026-03-17 | 2026-02-24 | 2026-03-17 | 4.77 | 0%
F.E.Z9.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2026-02-24 | 2026-03-17 | 2026-02-24 | 2026-03-17 | 4.5 | 0%
F.E.Z2.AR.BF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-02-25 | 2026-03-04 | 2026-02-25 | 2026-03-04 | 4.46 | 0%
F.E.Z2.AR.LG.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-02-25 | 2026-03-04 | 2026-02-25 | 2026-03-04 | 4.46 | 0%
F.E.Z2.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-02-25 | 2026-03-04 | 2026-02-25 | 2026-03-04 | 4.46 | 0%
F.E.Z7.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-02-25 | 2026-03-18 | 2026-02-25 | 2026-03-18 | 1.96 | 0%
F.E.Z7.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-02-25 | 2026-03-18 | 2026-02-25 | 2026-03-18 | 1.96 | 0%
R.E.4B.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-02-26 | 2026-03-19 | 2026-02-26 | 2026-03-19 | 3.58 | 0%
R.E.5B.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-02-26 | 2026-03-19 | 2026-02-26 | 2026-03-19 | 3.31 | 0%
R.E.6B.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-02-26 | 2026-03-19 | 2026-02-26 | 2026-03-19 | 3.73 | 0%
R.E.SS.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-02-26 | 2026-03-19 | 2026-02-26 | 2026-03-19 | 6.46 | 0%
R.E.SS.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-02-26 | 2026-03-19 | 2026-02-26 | 2026-03-19 | 9.23 | 0%
F.E.Z8.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-02-28 | 2026-03-07 | 2026-02-28 | 2026-03-07 | 4.08 | 0%
F.E.Z7.LV.BF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-03-01 | 2026-03-25 | 2026-03-01 | 2026-03-25 | 1.85 | 0%
F.E.Z7.LV.BF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-03-01 | 2026-03-25 | 2026-03-01 | 2026-03-25 | 1.85 | 0%
R.E.VL.PL.RF.WS.004 | Review and Approve Shop Drawings For Water Supply Network | 0.73 | 2026-03-01 | 2026-03-25 | 2026-03-01 | 2026-03-25 | 2.73 | 0%
R.E.VL.DR.RF.FW.004 | Review and Approve Shop Drawings For Drainage & Drainage Details | 0.73 | 2026-03-01 | 2026-03-25 | 2026-03-01 | 2026-03-25 | 2.73 | 0%
R.E.VL.HV.RF.CH.004 | Review and Approve Shop Drawings For Chilled Water Network | 0.73 | 2026-03-01 | 2026-03-25 | 2026-03-01 | 2026-03-25 | 2.69 | 0%
R.E.VL.EL.RF.PW.004 | Review and Approve Shop Drawings For Power | 0.73 | 2026-03-01 | 2026-03-25 | 2026-03-01 | 2026-03-25 | 2.62 | 0%
R.E.VL.AR.RF.RW.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-03-01 | 2026-03-08 | 2026-03-01 | 2026-03-08 | 5.92 | 0%
R.E.VL.FA.GE.FA.002 | Submission of Shop Drawings For Façade | 0.27 | 2026-03-03 | 2026-03-10 | 2026-03-03 | 2026-03-10 | 3.38 | 0%
R.E.SS.AR.GF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-03-03 | 2026-03-28 | 2026-03-03 | 2026-03-28 | 7.27 | 0%
R.E.SS.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-03 | 2026-03-28 | 2026-03-03 | 2026-03-28 | 7.27 | 0%
F.E.Z2.AR.BF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-03-05 | 2026-03-30 | 2026-03-05 | 2026-03-30 | 4.46 | 0%
F.E.Z2.AR.LG.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-03-05 | 2026-03-30 | 2026-03-05 | 2026-03-30 | 4.46 | 0%
F.E.Z2.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-03-05 | 2026-03-30 | 2026-03-05 | 2026-03-30 | 4.46 | 0%
F.E.Z8.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-03-08 | 2026-04-01 | 2026-03-08 | 2026-04-01 | 4.08 | 0%
R.E.VL.AR.RF.RW.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-03-09 | 2026-04-02 | 2026-03-09 | 2026-04-02 | 5.92 | 0%
R.E.VL.AR.RF.WA.002 | Submission of Shop Drawings For Waterproofing | 0.27 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-17 | 2.73 | 0%
R.E.VL.HV.RF.DU.002 | Submission of Shop Drawings For Ducting | 0.27 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-17 | 2.73 | 0%
R.E.VL.FF.RF.FN.002 | Submission of Shop Drawings For Firefighting Network | 0.27 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-17 | 2.88 | 0%
R.E.VL.FA.GE.FA.004 | Review and Approve Shop Drawings For Façade | 0.73 | 2026-03-11 | 2026-04-05 | 2026-03-11 | 2026-04-05 | 3.38 | 0%
R.E.4B.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 3.5 | 0%
R.E.4B.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.46 | 0%
R.E.4B.AR.GF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.69 | 0%
R.E.4B.AR.1F.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 3.65 | 0%
R.E.4B.AR.1F.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.62 | 0%
R.E.4B.AR.1F.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.85 | 0%
R.E.4B.AR.RF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 3.85 | 0%
R.E.5B.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.12 | 0%
R.E.5B.AR.GF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.35 | 0%
R.E.5B.AR.1F.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 3.42 | 0%
R.E.5B.AR.1F.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.38 | 0%
R.E.5B.AR.1F.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.62 | 0%
R.E.5B.AR.RF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 3.69 | 0%
R.E.6B.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.46 | 0%
R.E.6B.AR.GF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.69 | 0%
R.E.6B.AR.1F.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 3.77 | 0%
R.E.6B.AR.1F.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.73 | 0%
R.E.6B.AR.1F.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 2.96 | 0%
R.E.6B.AR.RF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-19 | 4.15 | 0%
R.E.5B.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-14 | 2026-03-24 | 2026-03-14 | 2026-03-24 | 3.12 | 0%
R.E.6B.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-14 | 2026-03-24 | 2026-03-14 | 2026-03-24 | 3.46 | 0%
R.E.VL.AR.GF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-14 | 2026-03-24 | 2026-03-14 | 2026-03-24 | 2.81 | 0%
R.E.VL.AR.GF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-14 | 2026-03-24 | 2026-03-14 | 2026-03-24 | 3.04 | 0%
R.E.VL.AR.1F.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-14 | 2026-03-24 | 2026-03-14 | 2026-03-24 | 2.81 | 0%
R.E.VL.AR.1F.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-14 | 2026-03-24 | 2026-03-14 | 2026-03-24 | 3.04 | 0%
R.E.4B.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-16 | 2026-03-26 | 2026-03-16 | 2026-03-26 | 3.46 | 0%
R.E.5B.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-16 | 2026-03-26 | 2026-03-16 | 2026-03-26 | 3.27 | 0%
R.E.6B.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-03-16 | 2026-03-26 | 2026-03-16 | 2026-03-26 | 3.69 | 0%
R.E.VL.AR.RF.WL.002 | Submission of Shop Drawings For Wall Finishes | 0.27 | 2026-03-16 | 2026-03-26 | 2026-03-16 | 2026-03-26 | 2.69 | 0%
R.E.4B.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-18 | 2026-03-29 | 2026-03-18 | 2026-03-29 | 3.62 | 0%
R.E.4B.AR.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-18 | 2026-03-29 | 2026-03-18 | 2026-03-29 | 3.73 | 0%
R.E.5B.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-18 | 2026-03-29 | 2026-03-18 | 2026-03-29 | 3.31 | 0%
R.E.5B.AR.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-18 | 2026-03-29 | 2026-03-18 | 2026-03-29 | 3.5 | 0%
R.E.6B.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-18 | 2026-03-29 | 2026-03-18 | 2026-03-29 | 3.69 | 0%
R.E.6B.AR.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-03-18 | 2026-03-29 | 2026-03-18 | 2026-03-29 | 3.85 | 0%
R.E.VL.AR.RF.WA.004 | Review and Approve Shop Drawings For Waterproofing | 0.73 | 2026-03-18 | 2026-04-12 | 2026-03-18 | 2026-04-12 | 2.73 | 0%
R.E.VL.HV.RF.DU.004 | Review and Approve Shop Drawings For Ducting | 0.73 | 2026-03-18 | 2026-04-12 | 2026-03-18 | 2026-04-12 | 2.73 | 0%
R.E.VL.FF.RF.FN.004 | Review and Approve Shop Drawings For Firefighting Network | 0.73 | 2026-03-18 | 2026-04-12 | 2026-03-18 | 2026-04-12 | 2.88 | 0%
R.E.4B.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 3.5 | 0%
R.E.4B.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.46 | 0%
R.E.4B.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.69 | 0%
R.E.4B.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 3.65 | 0%
R.E.4B.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.62 | 0%
R.E.4B.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.85 | 0%
R.E.4B.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 3.85 | 0%
R.E.5B.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.12 | 0%
R.E.5B.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.35 | 0%
R.E.5B.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 3.42 | 0%
R.E.5B.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.38 | 0%
R.E.5B.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.62 | 0%
R.E.5B.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 3.69 | 0%
R.E.6B.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.46 | 0%
R.E.6B.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.69 | 0%
R.E.6B.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 3.77 | 0%
R.E.6B.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.73 | 0%
R.E.6B.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2.96 | 0%
R.E.6B.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 4.15 | 0%
R.E.5B.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-25 | 2026-04-15 | 2026-03-25 | 2026-04-15 | 3.12 | 0%
R.E.6B.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-25 | 2026-04-15 | 2026-03-25 | 2026-04-15 | 3.46 | 0%
R.E.VL.AR.RF.RP.002 | Submission of Shop Drawings For RCP | 0.27 | 2026-03-25 | 2026-04-01 | 2026-03-25 | 2026-04-01 | 2.73 | 0%
R.E.VL.AR.GF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-25 | 2026-04-15 | 2026-03-25 | 2026-04-15 | 2.81 | 0%
R.E.VL.AR.GF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-25 | 2026-04-15 | 2026-03-25 | 2026-04-15 | 3.04 | 0%
R.E.VL.AR.1F.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-25 | 2026-04-15 | 2026-03-25 | 2026-04-15 | 2.81 | 0%
R.E.VL.AR.1F.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-03-25 | 2026-04-15 | 2026-03-25 | 2026-04-15 | 3.04 | 0%
R.E.4B.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-28 | 2026-04-18 | 2026-03-28 | 2026-04-18 | 3.46 | 0%
R.E.5B.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-28 | 2026-04-18 | 2026-03-28 | 2026-04-18 | 3.27 | 0%
R.E.6B.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-03-28 | 2026-04-18 | 2026-03-28 | 2026-04-18 | 3.69 | 0%
R.E.VL.AR.RF.WL.004 | Review and Approve Shop Drawings For Wall Finishes | 0.73 | 2026-03-28 | 2026-04-18 | 2026-03-28 | 2026-04-18 | 2.69 | 0%
R.E.4B.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 3.62 | 0%
R.E.4B.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 3.73 | 0%
R.E.5B.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 3.31 | 0%
R.E.5B.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 3.5 | 0%
R.E.6B.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 3.69 | 0%
R.E.6B.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 3.85 | 0%
R.E.5B.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-09 | 3.04 | 0%
R.E.6B.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-09 | 3.04 | 0%
R.E.VL.LI.GE.EL.002 | Submission of Shop Drawings For Elevator | 0.27 | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-09 | 3.04 | 0%
R.E.VL.AR.RF.RP.004 | Review and Approve Shop Drawings For RCP | 0.73 | 2026-04-02 | 2026-04-23 | 2026-04-02 | 2026-04-23 | 2.73 | 0%
R.E.VL.AR.GF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-14 | 3.15 | 0%
R.E.VL.AR.1F.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-14 | 3.15 | 0%
R.E.4B.AR.RF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-11 | 2026-04-18 | 2026-04-11 | 2026-04-18 | 3.31 | 0%
R.E.5B.AR.RF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-11 | 2026-04-18 | 2026-04-11 | 2026-04-18 | 3.12 | 0%
R.E.5B.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2026-04-11 | 2026-05-02 | 2026-04-11 | 2026-05-02 | 3.04 | 0%
R.E.6B.AR.RF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-11 | 2026-04-18 | 2026-04-11 | 2026-04-18 | 3.54 | 0%
R.E.6B.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2026-04-11 | 2026-05-02 | 2026-04-11 | 2026-05-02 | 3.04 | 0%
R.E.VL.LI.GE.EL.004 | Review and Approve Shop Drawings For Elevator | 0.73 | 2026-04-11 | 2026-05-02 | 2026-04-11 | 2026-05-02 | 3.04 | 0%
R.E.4B.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.08 | 0%
R.E.4B.AR.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.23 | 0%
R.E.GE.EX.GE.HA.002 | Submission of Shop Drawings For Hard Landscaping & Furniture | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.88 | 0%
R.E.5B.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 2.73 | 0%
R.E.5B.AR.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3 | 0%
R.E.6B.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.08 | 0%
R.E.6B.AR.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.35 | 0%
R.E.VL.AR.GF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.15 | 0%
R.E.VL.AR.1F.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 3.15 | 0%
R.E.VL.AR.GF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-04-15 | 2026-05-06 | 2026-04-15 | 2026-05-06 | 3.15 | 0%
R.E.VL.AR.1F.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-04-15 | 2026-05-06 | 2026-04-15 | 2026-05-06 | 3.15 | 0%
R.E.SS.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-04-15 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 4.88 | 0%
R.E.VL.AR.RF.WI.002 | Submission of Shop Drawings For Windows Schedule & Details | 0.27 | 2026-04-16 | 2026-04-23 | 2026-04-16 | 2026-04-23 | 3.19 | 0%
R.E.4B.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-19 | 2026-05-10 | 2026-04-19 | 2026-05-10 | 3.31 | 0%
R.E.5B.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-19 | 2026-05-10 | 2026-04-19 | 2026-05-10 | 3.12 | 0%
R.E.6B.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-19 | 2026-05-10 | 2026-04-19 | 2026-05-10 | 3.54 | 0%
R.E.VL.AR.RF.FL.002 | Submission of Shop Drawings For Floor Finishes | 0.27 | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-04-29 | 2.65 | 0%
R.E.4B.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.08 | 0%
R.E.4B.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.23 | 0%
R.E.GE.EX.GE.HA.004 | Review and Approve Shop Drawings For Hard Landscaping & Furniture | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.88 | 0%
R.E.5B.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 2.73 | 0%
R.E.5B.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3 | 0%
R.E.6B.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.08 | 0%
R.E.6B.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.35 | 0%
R.E.VL.AR.GF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.15 | 0%
R.E.VL.AR.1F.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 3.15 | 0%
R.E.SS.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 4.88 | 0%
R.E.4B.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-04-25 | 2026-05-02 | 2026-04-25 | 2026-05-02 | 3.69 | 0%
R.E.VL.AR.GF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-25 | 2026-05-02 | 2026-04-25 | 2026-05-02 | 3.15 | 0%
R.E.VL.AR.1F.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-04-25 | 2026-05-02 | 2026-04-25 | 2026-05-02 | 3.15 | 0%
R.E.VL.AR.RF.WI.004 | Review and Approve Shop Drawings For Windows Schedule & Details | 0.73 | 2026-04-25 | 2026-05-16 | 2026-04-25 | 2026-05-16 | 3.19 | 0%
R.E.SS.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-04-25 | 2026-05-02 | 2026-04-25 | 2026-05-02 | 4.73 | 0%
R.E.SS.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-04-27 | 2026-05-04 | 2026-04-27 | 2026-05-04 | 4.73 | 0%
R.E.SS.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-04-27 | 2026-05-04 | 2026-04-27 | 2026-05-04 | 4.73 | 0%
R.E.VL.AR.RF.FL.004 | Review and Approve Shop Drawings For Floor Finishes | 0.73 | 2026-04-30 | 2026-05-21 | 2026-04-30 | 2026-05-21 | 2.65 | 0%
R.E.4B.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-03 | 2026-05-24 | 2026-05-03 | 2026-05-24 | 3.69 | 0%
R.E.VL.AR.GF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-05-03 | 2026-05-24 | 2026-05-03 | 2026-05-24 | 3.15 | 0%
R.E.VL.AR.1F.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-05-03 | 2026-05-24 | 2026-05-03 | 2026-05-24 | 3.15 | 0%
R.E.SS.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-05-03 | 2026-05-24 | 2026-05-03 | 2026-05-24 | 4.73 | 0%
R.E.4B.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-05-04 | 2026-05-11 | 2026-05-04 | 2026-05-11 | 3.69 | 0%
R.E.SS.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-05-05 | 2026-05-30 | 2026-05-05 | 2026-05-30 | 4.73 | 0%
R.E.SS.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-05-05 | 2026-05-30 | 2026-05-05 | 2026-05-30 | 4.73 | 0%
R.E.5B.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 3.12 | 0%
R.E.6B.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 3.54 | 0%
R.E.4B.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-05-09 | 2026-05-16 | 2026-05-09 | 2026-05-16 | 3.73 | 0%
R.E.4B.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-05-09 | 2026-05-16 | 2026-05-09 | 2026-05-16 | 3.73 | 0%
R.E.VL.AR.RF.DR.002 | Submission of Shop Drawings For Doors Schedule & Details | 0.27 | 2026-05-11 | 2026-05-18 | 2026-05-11 | 2026-05-18 | 2.62 | 0%
R.E.4B.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-05-12 | 2026-06-06 | 2026-05-12 | 2026-06-06 | 3.69 | 0%
R.E.5B.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-16 | 2026-06-09 | 2026-05-16 | 2026-06-09 | 3.12 | 0%
R.E.6B.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-16 | 2026-06-09 | 2026-05-16 | 2026-06-09 | 3.54 | 0%
R.E.4B.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-05-17 | 2026-06-10 | 2026-05-17 | 2026-06-10 | 3.73 | 0%
R.E.4B.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-05-17 | 2026-06-10 | 2026-05-17 | 2026-06-10 | 3.73 | 0%
R.E.5B.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-05-17 | 2026-05-24 | 2026-05-17 | 2026-05-24 | 3.23 | 0%
R.E.6B.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-05-17 | 2026-05-24 | 2026-05-17 | 2026-05-24 | 3.54 | 0%
R.E.4B.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 2.88 | 0%
R.E.4B.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 2.96 | 0%
R.E.5B.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 2.54 | 0%
R.E.5B.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 2.73 | 0%
R.E.6B.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 3 | 0%
R.E.6B.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 3.08 | 0%
R.E.VL.AR.RF.DR.004 | Review and Approve Shop Drawings For Doors Schedule & Details | 0.73 | 2026-05-19 | 2026-06-13 | 2026-05-19 | 2026-06-13 | 2.62 | 0%
R.E.VL.EL.1F.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-20 | 2026-05-31 | 2026-05-20 | 2026-05-31 | 3.15 | 0%
R.E.5B.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-05-21 | 2026-06-01 | 2026-05-21 | 2026-06-01 | 3.23 | 0%
R.E.5B.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-05-21 | 2026-06-01 | 2026-05-21 | 2026-06-01 | 3.23 | 0%
R.E.6B.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-05-21 | 2026-06-01 | 2026-05-21 | 2026-06-01 | 3.54 | 0%
R.E.6B.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-05-21 | 2026-06-01 | 2026-05-21 | 2026-06-01 | 3.54 | 0%
R.E.VL.EL.GF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-05-21 | 2026-06-01 | 2026-05-21 | 2026-06-01 | 3.15 | 0%
R.E.4B.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-05-24 | 2026-06-03 | 2026-05-24 | 2026-06-03 | 5.58 | 0%
R.E.5B.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-05-24 | 2026-06-03 | 2026-05-24 | 2026-06-03 | 5.58 | 0%
R.E.6B.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-05-24 | 2026-06-03 | 2026-05-24 | 2026-06-03 | 5.58 | 0%
R.E.VL.KE.GE.FA.002 | Submission of Shop Drawings For Kitchen & Laundry Equipment | 0.27 | 2026-05-24 | 2026-06-03 | 2026-05-24 | 2026-06-03 | 5.58 | 0%
R.E.5B.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-05-25 | 2026-06-18 | 2026-05-25 | 2026-06-18 | 3.23 | 0%
R.E.6B.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-05-25 | 2026-06-18 | 2026-05-25 | 2026-06-18 | 3.54 | 0%
R.E.4B.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-31 | 2026-06-21 | 2026-05-31 | 2026-06-21 | 2.88 | 0%
R.E.4B.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-31 | 2026-06-21 | 2026-05-31 | 2026-06-21 | 2.96 | 0%
R.E.5B.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-31 | 2026-06-21 | 2026-05-31 | 2026-06-21 | 2.54 | 0%
R.E.5B.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-31 | 2026-06-21 | 2026-05-31 | 2026-06-21 | 2.73 | 0%
R.E.6B.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-31 | 2026-06-21 | 2026-05-31 | 2026-06-21 | 3 | 0%
R.E.6B.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-05-31 | 2026-06-21 | 2026-05-31 | 2026-06-21 | 3.08 | 0%
R.E.4B.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-01 | 2026-06-08 | 2026-06-01 | 2026-06-08 | 2.96 | 0%
R.E.4B.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-01 | 2026-06-08 | 2026-06-01 | 2026-06-08 | 3 | 0%
R.E.5B.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-01 | 2026-06-08 | 2026-06-01 | 2026-06-08 | 2.62 | 0%
R.E.5B.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-01 | 2026-06-08 | 2026-06-01 | 2026-06-08 | 2.73 | 0%
R.E.6B.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-01 | 2026-06-08 | 2026-06-01 | 2026-06-08 | 3 | 0%
R.E.VL.EL.1F.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-06-01 | 2026-06-22 | 2026-06-01 | 2026-06-22 | 3.15 | 0%
R.E.4B.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-02 | 2026-06-09 | 2026-06-02 | 2026-06-09 | 3.42 | 0%
R.E.5B.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-02 | 2026-06-23 | 2026-06-02 | 2026-06-23 | 3.23 | 0%
R.E.5B.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-02 | 2026-06-23 | 2026-06-02 | 2026-06-23 | 3.23 | 0%
R.E.6B.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-02 | 2026-06-09 | 2026-06-02 | 2026-06-09 | 3.08 | 0%
R.E.6B.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-02 | 2026-06-23 | 2026-06-02 | 2026-06-23 | 3.54 | 0%
R.E.6B.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-02 | 2026-06-23 | 2026-06-02 | 2026-06-23 | 3.54 | 0%
R.E.VL.EL.GF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-06-02 | 2026-06-23 | 2026-06-02 | 2026-06-23 | 3.15 | 0%
R.E.5B.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-03 | 2026-06-10 | 2026-06-03 | 2026-06-10 | 3.23 | 0%
R.E.4B.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-06-04 | 2026-06-25 | 2026-06-04 | 2026-06-25 | 5.58 | 0%
R.E.5B.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-06-04 | 2026-06-25 | 2026-06-04 | 2026-06-25 | 5.58 | 0%
R.E.6B.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-06-04 | 2026-06-25 | 2026-06-04 | 2026-06-25 | 5.58 | 0%
R.E.VL.LV.GF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-04 | 2026-06-11 | 2026-06-04 | 2026-06-11 | 3.15 | 0%
R.E.VL.LV.1F.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-04 | 2026-06-11 | 2026-06-04 | 2026-06-11 | 3.15 | 0%
R.E.VL.KE.GE.FA.004 | Review and Approve Shop Drawings For Kitchen & Laundry Equipment | 0.73 | 2026-06-04 | 2026-06-25 | 2026-06-04 | 2026-06-25 | 5.58 | 0%
R.E.4B.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 3 | 0%
R.E.4B.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 3 | 0%
R.E.4B.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 3.04 | 0%
R.E.4B.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 3.04 | 0%
R.E.5B.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 2.65 | 0%
R.E.5B.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 2.65 | 0%
R.E.6B.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 3 | 0%
R.E.6B.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 3 | 0%
R.E.5B.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-08 | 2026-06-15 | 2026-06-08 | 2026-06-15 | 2.77 | 0%
R.E.5B.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-08 | 2026-06-15 | 2026-06-08 | 2026-06-15 | 2.77 | 0%
R.E.6B.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-08 | 2026-06-15 | 2026-06-08 | 2026-06-15 | 3.08 | 0%
R.E.6B.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-08 | 2026-06-15 | 2026-06-08 | 2026-06-15 | 3.08 | 0%
R.E.4B.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-09 | 2026-06-30 | 2026-06-09 | 2026-06-30 | 2.96 | 0%
R.E.4B.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-09 | 2026-06-30 | 2026-06-09 | 2026-06-30 | 3 | 0%
R.E.5B.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-09 | 2026-06-30 | 2026-06-09 | 2026-06-30 | 2.62 | 0%
R.E.5B.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-09 | 2026-06-30 | 2026-06-09 | 2026-06-30 | 2.73 | 0%
R.E.6B.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-09 | 2026-06-30 | 2026-06-09 | 2026-06-30 | 3 | 0%
R.E.VL.LV.GF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 3.15 | 0%
R.E.VL.LV.GF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 3.15 | 0%
R.E.VL.LV.1F.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 3.15 | 0%
R.E.VL.LV.1F.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 3.15 | 0%
R.E.4B.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-10 | 2026-06-17 | 2026-06-10 | 2026-06-17 | 3 | 0%
R.E.4B.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-10 | 2026-06-17 | 2026-06-10 | 2026-06-17 | 3.04 | 0%
R.E.4B.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-10 | 2026-07-01 | 2026-06-10 | 2026-07-01 | 3.42 | 0%
R.E.5B.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-10 | 2026-06-17 | 2026-06-10 | 2026-06-17 | 2.65 | 0%
R.E.6B.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-10 | 2026-06-17 | 2026-06-10 | 2026-06-17 | 3 | 0%
R.E.6B.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-10 | 2026-07-01 | 2026-06-10 | 2026-07-01 | 3.08 | 0%
R.E.5B.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-11 | 2026-07-02 | 2026-06-11 | 2026-07-02 | 3.23 | 0%
R.E.VL.EL.RF.LI.002 | Submission of Shop Drawings For Lighting | 0.27 | 2026-06-11 | 2026-06-18 | 2026-06-11 | 2026-06-18 | 2.62 | 0%
R.E.5B.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-13 | 2026-06-20 | 2026-06-13 | 2026-06-20 | 2.77 | 0%
R.E.VL.LV.GF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-13 | 2026-07-04 | 2026-06-13 | 2026-07-04 | 3.15 | 0%
R.E.VL.LV.1F.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-13 | 2026-07-04 | 2026-06-13 | 2026-07-04 | 3.15 | 0%
R.E.4B.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 3 | 0%
R.E.4B.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 3 | 0%
R.E.4B.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 3.04 | 0%
R.E.4B.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 3.04 | 0%
R.E.5B.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 2.65 | 0%
R.E.5B.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 2.65 | 0%
R.E.6B.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 3 | 0%
R.E.6B.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-14 | 2026-07-05 | 2026-06-14 | 2026-07-05 | 3 | 0%
R.E.VL.LV.GF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-14 | 2026-06-21 | 2026-06-14 | 2026-06-21 | 3.15 | 0%
R.E.VL.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-14 | 2026-06-21 | 2026-06-14 | 2026-06-21 | 3.15 | 0%
R.E.6B.LV.1F.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-15 | 2026-06-22 | 2026-06-15 | 2026-06-22 | 3 | 0%
R.E.5B.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-16 | 2026-07-07 | 2026-06-16 | 2026-07-07 | 2.77 | 0%
R.E.5B.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-16 | 2026-07-07 | 2026-06-16 | 2026-07-07 | 2.77 | 0%
R.E.6B.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-16 | 2026-07-07 | 2026-06-16 | 2026-07-07 | 3.08 | 0%
R.E.6B.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-16 | 2026-07-07 | 2026-06-16 | 2026-07-07 | 3.08 | 0%
R.E.GE.EX.GE.SG.002 | Submission of Shop Drawings For Signage and Wayfinding | 0.27 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 2.62 | 0%
R.E.VL.LV.GF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-17 | 2026-07-08 | 2026-06-17 | 2026-07-08 | 3.15 | 0%
R.E.VL.LV.GF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-17 | 2026-07-08 | 2026-06-17 | 2026-07-08 | 3.15 | 0%
R.E.VL.LV.1F.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-06-17 | 2026-07-08 | 2026-06-17 | 2026-07-08 | 3.15 | 0%
R.E.VL.LV.1F.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-06-17 | 2026-07-08 | 2026-06-17 | 2026-07-08 | 3.15 | 0%
R.E.4B.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-18 | 2026-07-09 | 2026-06-18 | 2026-07-09 | 3 | 0%
R.E.4B.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-18 | 2026-07-09 | 2026-06-18 | 2026-07-09 | 3.04 | 0%
R.E.5B.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-18 | 2026-07-09 | 2026-06-18 | 2026-07-09 | 2.65 | 0%
R.E.6B.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-18 | 2026-07-09 | 2026-06-18 | 2026-07-09 | 3 | 0%
R.E.6B.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-06-20 | 2026-06-27 | 2026-06-20 | 2026-06-27 | 3 | 0%
R.E.VL.EL.RF.LI.004 | Review and Approve Shop Drawings For Lighting | 0.73 | 2026-06-20 | 2026-07-11 | 2026-06-20 | 2026-07-11 | 2.62 | 0%
R.E.5B.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-21 | 2026-07-12 | 2026-06-21 | 2026-07-12 | 2.77 | 0%
R.E.VL.LV.RF.TN.002 | Submission of Shop Drawings For Telecom Network | 0.27 | 2026-06-21 | 2026-06-28 | 2026-06-21 | 2026-06-28 | 2.62 | 0%
R.E.VL.LV.GF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-22 | 2026-07-13 | 2026-06-22 | 2026-07-13 | 3.15 | 0%
R.E.VL.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-22 | 2026-07-13 | 2026-06-22 | 2026-07-13 | 3.15 | 0%
R.E.GE.EX.GE.SO.002 | Submission of Shop Drawings For Soft Landscaping | 0.27 | 2026-06-23 | 2026-06-30 | 2026-06-23 | 2026-06-30 | 2.65 | 0%
R.E.6B.LV.1F.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-23 | 2026-07-14 | 2026-06-23 | 2026-07-14 | 3 | 0%
R.E.GE.EX.GE.SG.004 | Review and Approve Shop Drawings For Signage and Wayfinding | 0.73 | 2026-06-25 | 2026-07-16 | 2026-06-25 | 2026-07-16 | 2.62 | 0%
R.E.VL.LV.RF.FS.002 | Submission of Shop Drawings For Fire Alarm System | 0.27 | 2026-06-25 | 2026-07-02 | 2026-06-25 | 2026-07-02 | 2.62 | 0%
R.E.VL.LV.RF.SC.002 | Submission of Shop Drawings For Security | 0.27 | 2026-06-25 | 2026-07-02 | 2026-06-25 | 2026-07-02 | 2.62 | 0%
R.E.6B.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-06-28 | 2026-07-19 | 2026-06-28 | 2026-07-19 | 3 | 0%
R.E.VL.LV.RF.TN.004 | Review and Approve Shop Drawings For Telecom Network | 0.73 | 2026-06-29 | 2026-07-20 | 2026-06-29 | 2026-07-20 | 2.62 | 0%
R.E.GE.EX.GE.SO.004 | Review and Approve Shop Drawings For Soft Landscaping | 0.73 | 2026-07-01 | 2026-07-22 | 2026-07-01 | 2026-07-22 | 2.65 | 0%
R.E.VL.LV.RF.FS.004 | Review and Approve Shop Drawings For Fire Alarm System | 0.73 | 2026-07-04 | 2026-07-25 | 2026-07-04 | 2026-07-25 | 2.62 | 0%
R.E.VL.LV.RF.SC.004 | Review and Approve Shop Drawings For Security | 0.73 | 2026-07-04 | 2026-07-25 | 2026-07-04 | 2026-07-25 | 2.62 | 0%
R.E.VL.LV.RF.IC.002 | Submission of Shop Drawings For ICT | 0.27 | 2026-07-05 | 2026-07-12 | 2026-07-05 | 2026-07-12 | 2.62 | 0%
R.E.VL.LV.RF.IC.004 | Review and Approve Shop Drawings For ICT | 0.73 | 2026-07-13 | 2026-08-03 | 2026-07-13 | 2026-08-03 | 2.62 | 0%
R.E.4B.AR.GF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.4B.AR.1F.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.4B.AR.RF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.5B.AR.GF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.5B.AR.1F.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.5B.AR.RF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.6B.AR.GF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.6B.AR.1F.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.6B.AR.RF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 3.19 | 0%
R.E.VL.AR.GF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-25 | 2026-08-01 | 2026-07-25 | 2026-08-01 | 3.04 | 0%
R.E.VL.AR.1F.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-25 | 2026-08-01 | 2026-07-25 | 2026-08-01 | 3.04 | 0%
R.E.VL.AR.RF.ID.002 | Submission of Shop Drawings For ID Details | 0.27 | 2026-07-25 | 2026-08-01 | 2026-07-25 | 2026-08-01 | 3.04 | 0%
R.E.4B.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.4B.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.4B.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.5B.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.5B.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.5B.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.6B.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.6B.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.6B.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-07-28 | 2026-08-18 | 2026-07-28 | 2026-08-18 | 3.19 | 0%
R.E.4B.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-02 | 2026-08-09 | 2026-08-02 | 2026-08-09 | 3.19 | 0%
R.E.4B.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-02 | 2026-08-09 | 2026-08-02 | 2026-08-09 | 3.19 | 0%
R.E.4B.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-02 | 2026-08-09 | 2026-08-02 | 2026-08-09 | 3.19 | 0%
R.E.VL.AR.GF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-08-02 | 2026-08-23 | 2026-08-02 | 2026-08-23 | 3.04 | 0%
R.E.VL.AR.1F.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-08-02 | 2026-08-23 | 2026-08-02 | 2026-08-23 | 3.04 | 0%
R.E.VL.AR.RF.ID.004 | Review and Approve Shop Drawings For ID Details | 0.73 | 2026-08-02 | 2026-08-23 | 2026-08-02 | 2026-08-23 | 3.04 | 0%
R.E.5B.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.5B.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.5B.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.6B.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.6B.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.6B.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.VL.AR.GF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.VL.AR.1F.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.VL.AR.RF.SG.002 | Submission of Shop Drawings For Signage | 0.27 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 3.04 | 0%
R.E.4B.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-10 | 2026-08-31 | 2026-08-10 | 2026-08-31 | 3.19 | 0%
R.E.4B.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-10 | 2026-08-31 | 2026-08-10 | 2026-08-31 | 3.19 | 0%
R.E.4B.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-10 | 2026-08-31 | 2026-08-10 | 2026-08-31 | 3.19 | 0%
R.E.5B.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.5B.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.5B.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.6B.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.6B.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.6B.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.VL.AR.GF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.VL.AR.1F.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%
R.E.VL.AR.RF.SG.004 | Review and Approve Shop Drawings For Signage | 0.73 | 2026-08-15 | 2026-09-05 | 2026-08-15 | 2026-09-05 | 3.04 | 0%

## Building Summary (hidden)
#REF! | [12 empty] | 2025-07-10
Based on Each Buildings
Building Name | Overall Planned No. | Planned Uptill Today | Forecast Planned Uptill Today | Balance 1st submission to GHD | Submitted Uptill Today GHD | PMC Consultant Status | [5 empty] | Approved A, B & E | % Approved Vs Overall Planned | Under Review of UCC | Returned by UCC To Revise | Balance 1st submission to UCC
|  |  |  | TBS |  | A | B | C | D | I | UR |  |  | P | R | TBS
GENERAL | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAIN BUILDING | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IJKL | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IJKL | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ABCD | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
EFGH | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IJKL | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IJKL | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LMNO | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PQRS | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
SITE | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
% | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!

## Monthly Performance (hidden)
#REF!
Monthly Performance
Total No. of Submissions: |  |  |  | #REF!
|  |  |  | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
Status | Discipline | Graph | Period | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31
Planned | ALL |  | All Discipline Monthly Planned No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Planned | ALL | Graph | Cumulative Planned No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Planned | ALL |  | All Discipline Cumulative Planned % | bar: 2024-08-01 to 2025-07-01
Submitted | ALL |  | All Discipline Monthly Submitted No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Submitted | ALL | Graph | Cumulative Submitted No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Submitted | ALL |  | All Discipline Cumulative Submitted % | bar: 2024-08-01 to 2025-07-01
Approved | ALL |  | All Discipline Monthly Approved No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Approved | ALL | Graph | Cumulative Approved No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Approved | ALL |  | All Discipline Cumulative Approved % | bar: 2024-08-01 to 2025-07-01
Revise & Resubmit | ALL |  | All Discipline Monthly Revise & Resubmit | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Revise & Resubmit | ALL | Graph | Cumulative Revise & Resubmit No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Revise & Resubmit | ALL |  | All Discipline Cumulative Revise & Resubmit % | bar: 2024-08-01 to 2025-07-01
Under Review | ALL |  | All Discipline Monthly Under Review No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Under Review | ALL | Graph | Cumulative Under Review No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Under Review | ALL |  | All Discipline Cumulative Under Review % | bar: 2024-08-01 to 2025-07-01
Balance 1st Submission | ALL |  | All Discipline Monthly Balance 1st Submission No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Balance 1st Submission | ALL |  | All Discipline Cumulative Balance 1st Submission No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Balance 1st Submission | ALL |  | All Discipline Cumulative Balance 1st Submission % | bar: 2024-08-01 to 2025-07-01

## SC Performance (hidden)
DESIGN AND BUILD OF NEOM HIGH DENSITY OFFICES, NEOM, KSA
DDS Summary for Subcontractors/TED Perfomance
Discipline
Originator | URB
From Date | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01
To Date | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31
Monthly Planned No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Monthly Submitted No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Monthly Approved No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Monthly Revise & Resubmit | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Monthly Under Review No. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Consultant Performance (hidden)
#REF!
Summary for Consultants Performance
Consultant | V3
From | 2024-08-01
To | 2025-07-10
Total No. of Submissions | #REF!
Commented |  |  | Under Review
Replied within 14 Days | #REF! | 99.25% | Under Review Within 14 Days | #REF! | 99.25%
Replied within 28 Days | #REF! | 100% | Under Review More than 28 Days | #REF! | 100%
Total Commented | #REF! | #REF! | Total Under Review | #REF! | #REF!
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-07 | B
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[10 empty] | 2023-12-10 | C
[7 empty] | Cover Sheet | ELE | 2023-12-09
[7 empty] | List of Drawings | ELE | 2023-12-09
[7 empty] | GROUND FLOOR - LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | FIRST FLOOR - LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | SECOND FLOOR - LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | THIRD FLOOR - LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | ROOF FLOOR - LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | GROUND FLOOR - EMERGENCY LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | FIRST FLOOR - EMERGENCY LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | SECOND FLOOR - EMERGENCY EMERGENCY LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | THIRD FLOOR - EMERGENCY LIGHTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | GROUND FLOOR - POWER SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | FIRST FLOOR - POWER SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | SECOND FLOOR - POWER SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | THIRD FLOOR - POWER SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | GROUND FLOOR - HVAC FEEDING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | FIRST FLOOR - HVAC FEEDING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | SECOND FLOOR - HVAC FEEDING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | THIRD FLOOR - HVAC FEEDING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | GROUND FLOOR - FEEDER ROUTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | FIRST FLOOR - FEEDER ROUTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | SECOND FLOOR - FEEDER ROUTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | THIRD FLOOR - FEEDER ROUTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | ROOF FLOOR - FEEDER ROUTING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | GROUND FLOOR -EARTHING SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | ROOF FLOOR - LIGHTINING PROTECTION SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | POWER SINGLE LINE DIAGRAM | ELE | 2023-12-09
[7 empty] | EMERGENCY LIGHTING RISER | ELE | 2023-12-09
[7 empty] | FAS SYSTEM - RISER DIAGRAM | ELE | 2023-12-09
[7 empty] | LIGHTING FIXTURE SCHEDUEL | ELE | 2023-12-09
[7 empty] | FEEDER DATA SCHEDUEL | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 1 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 2 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 3 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 4 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 5 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 6 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 7 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 8 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 9 | ELE | 2023-12-09
[7 empty] | PANEL BOARDS SCHEDUEL 10 | ELE | 2023-12-09
[7 empty] | ROOF FLOOR - PHOTOVOLTAIC SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | GROUND FLOOR- FAS SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | FIRST FLOOR- FAS SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | SECOND FLOOR- FAS SYSTEM LAYOUT | ELE | 2023-12-09
[7 empty] | THIRD FLOOR- FAS SYSTEM LAYOUT | ELE | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-ARC-DRG-300106 | WALL SECTION 01 | ARC | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-ARC-DRG-300107 | WALL SECTION 02 | ARC | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-ARC-DRG-400103 | ELEVATOR DETAILS | ARC | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-ARC-DRG-400104 | RAMPS DETAIL | ARC | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-ARC-DRG-800102 | WINDOW TYPES | ARC | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-000001 | COVER SHEETGENERAL | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-000002 | LIST OF DRAWINGSGENERAL | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100101 | GROUND FLOOR PLAN01-GENERAL ARRANGEMENT PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100102 | FIRST FLOOR PLAN01-GENERAL ARRANGEMENT PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100103 | SECOND FLOOR PLAN01-GENERAL ARRANGEMENT PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100104 | THIRD FLOOR PLAN01-GENERAL ARRANGEMENT PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100105 | GROUND FLOOR PLANSETTING OUT PLAN | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100106 | FIRST FLOOR PLANSETTING OUT PLAN | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100107 | SECOND FLOOR PLANSETTING OUT PLAN | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100108 | THIRD FLOOR PLANSETTING OUT PLAN | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100109 | GROUND FLOOR PLANFLOOR FINISES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100110 | FIRST FLOOR PLANFLOOR FINISES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100111 | SECOND FLOOR PLANFLOOR FINISES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100112 | THIRD FLOOR PLANFLOOR FINISES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100113 | GROUND FLOOR PLANWALL FINISHES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100114 | FIRST FLOOR PLANWALL FINISHES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100115 | SECOND FLOOR PLANWALL FINISHES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100116 | THIRD FLOOR PLANWALL FINISHES PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100117 | GROUND FLOOR PLANSMALL POWER PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100118 | FIRST FLOOR PLANSMALL POWER PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100119 | SECOND FLOOR PLANSMALL POWER PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-100120 | THIRD FLOOR PLANSMALL POWER PLANS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200101 | GROUND CEILING PLANRCP | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200102 | FIRST CEILING PLANRCP | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200103 | SECOND CEILING PLANRCP | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200104 | THIRD CEILING PLANRCP | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200105 | GROUND CEILING PLANCEILING LAYOUT | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200106 | FIRST CEILING PLANCEILING LAYOUT | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200107 | SECOND CEILING PLANCEILING LAYOUT | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-200108 | THIRD CEILING PLANCEILING LAYOUT | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300101 | Male Toilets 01ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300102 | Male Toilets 02ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300103 | Female Toilets 01ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300104 | Female Toilets 02ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300105 | Recepttion Area 01ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300106 | Reception Area 02ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300107 | MEETING ROOM ELEVATIONSENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300108 | PHONE BOOTHENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300109 | FOCUS ROOM - ELEVATIONSENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-300110 | CLOSE OFFICE - ELEVATIONSENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800101 | GLASS PARTITION DETAIL 01ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800102 | GLASS PARTITION DETAIL 02ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800103 | GLASS PARTITION DETAIL 03ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800104 | GLASS PARTITION DETAIL 04ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800105 | GLASS PARTITION DETAIL 05ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800106 | GLASS PARTITION DETAIL 06ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800107 | GLASS PARTITION DETAIL 07ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800108 | GLASS PARTITION DETAIL 08ENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800109 | DOOR TYPESDOORS & WINDOWS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800110 | FLOORING DETAILSENLARGED DETAILS | IDN | 2023-12-09
[6 empty] | 14-621850-4800000856-URB-IND-DRG-800111 | SANITARYWARE SCHEDULESSCHEDULES | IDN | 2023-12-09

## Sheet4 (hidden)
WS-WSH-687-3230-UBJ-SDW-ST-200-0000001_PDF | 00 | 4 | FAENA HOTEL- PART 2D EXCAVATION PLAN AND SECTIONS | Shop Drawing | B-Approved with Comments | Approved with Comments | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-26 | 2024-11-30 12:18 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000002_PDF | 00 | 4 | FAENA HOTEL- PART 2F EXCAVATION PLAN | Shop Drawing | B-Approved with Comments | Approved with Comments | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-26 14:48 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000003_PDF | 00 | 4 | FAENA HOTEL- PART 2F EXCAVATION PLAN | Shop Drawing | B-Approved with Comments | Approved with Comments | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-26 14:48 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000004_PDF | 00 | 4 | FAENA HOTEL- PART 2F EXCAVATION SECTIONS DETAILS | Shop Drawing | B-Approved with Comments | Approved with Comments | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-26 14:48 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000005_PDF | 02 | 13 | WS-687-FAENA HOTEL- PART 2B EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-12 | 2024-12-12 14:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000006_PDF | 02 | 12 | WS-687-FAENA HOTEL- PART 2B EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-12 | 2024-12-12 14:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000007_PDF | 02 | 5 | FAENA HOTEL- PART 2B EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-12 | 2024-12-12 14:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000008_PDF | 02 | 12 | WS-687-FAENA HOTEL- PART 2B EXCAVATION SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-12 | 2024-12-12 14:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000009_PDF | 01 | 8 | WS-687-FAENA HOTEL- PART 2E EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-15 17:26 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000010_PDF | 01 | 7 | WS-687-FAENA HOTEL- PART 2E EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-15 17:26 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000011_PDF | 01 | 7 | WS-687-FAENA HOTEL- PART 2E EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-15 17:26 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000012_PDF | 01 | 7 | WS-687-FAENA HOTEL- PART 2E EXCAVATION SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-15 17:26 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000013_PDF | 01 | 9 | WS-687-FAENA HOTEL- PART 2E EXCAVATION SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-15 17:26 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000014_PDF | 01 | 5 | WS-687-FAENA HOTEL- PART 2H EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-11 | 2024-12-11 09:50 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000015_PDF | 01 | 5 | FAENA HOTEL- PART 2H EXCAVATION SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-11 | 2024-12-11 09:50 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000016_PDF | 00 | 2 | FAENA HOTEL- PART 2A EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-26 | 2024-12-26 09:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000017_PDF | 00 | 2 | FAENA HOTEL- PART 2A EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-26 | 2024-12-26 09:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000018_PDF | 00 | 2 | FAENA HOTEL- PART 2A EXCAVATION PLAN SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-26 | 2024-12-26 09:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100001_PDF | 00 | 5 | FAENA HOTEL- PART 2D FOUNDATIONS LEVEL GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100001A_PDF | 00 | 2 | FAENA HOTEL- PART 2D FOUNDATIONS LEVEL GENERAL ARRANGEMENT SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100002_PDF | 00 | 4 | FAENA HOTEL- PART 2F FOUNDATIONS LEVEL GENERAL ARRANGEMENT | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:11 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100002_PDF | 00 | 3 | FAENA HOTEL- PART 2F FOUNDATIONS LEVEL GENERAL ARRANGEMENT | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:11 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100003_PDF | 00 | 3 | FAENA HOTEL- PART 2F FOUNDATIONS LEVEL GENERAL ARRANGEMENT | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:11 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100004_PDF | 00 | 3 | FAENA HOTEL- PART 2F FOUNDATIONS LEVEL GENERAL ARRANGEMENT SECTIONS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:11 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100005_PDF | 01 | 9 | FAENA HOTEL- PART 2B GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 11:19 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100006_PDF | 01 | 8 | FAENA HOTEL- PART 2B GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 11:19 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100007_PDF | 01 | 8 | FAENA HOTEL- PART 2B GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 11:19 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100008_PDF | 01 | 9 | FAENA HOTEL- PART 2B GENERAL ARRANGEMENT SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 11:19 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100009_PDF | 01 | 6 | FAENA HOTEL- PART 2E GENERAL ARRANGMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 10:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100010_PDF | 01 | 5 | FAENA HOTEL- PART 2E GENERAL ARRANGMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 10:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100011_PDF | 01 | 5 | FAENA HOTEL- PART 2E GENERAL ARRANGMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 10:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100012_PDF | 01 | 5 | FAENA HOTEL- PART 2E GENERAL ARRANGEMENT SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 10:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100013_PDF | 01 | 5 | FAENA HOTEL- PART 2E GENERAL ARRANGEMENT SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 10:57 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100014_PDF | 01 | 6 | WS-687-FAENA HOTEL- PART 2H GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-11 | 2024-12-11 09:59 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100015_PDF | 01 | 5 | WS-687-FAENA HOTEL- PART 2H GENERAL ARRANGEMENT SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-11 | 2024-12-11 09:59 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100016_PDF | 00 | 3 | FAENA HOTEL- PART 2A GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-26 | 2024-12-26 11:35 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100017_PDF | 00 | 2 | FAENA HOTEL- PART 2A GENERAL ARRANGEMENT PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-26 | 2024-12-26 11:35 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100018_PDF | 00 | 3 | FAENA HOTEL- PART 2A GENERAL ARRANGEMENT SECTIONS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-26 | 2024-12-26 11:35 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110001_PDF | 00 | 4 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110001_PDF | 00 | 3 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110002_PDF | 00 | 3 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110003_PDF | 00 | 3 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110004_PDF | 00 | 3 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110005_PDF | 00 | 3 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110006_PDF | 00 | 3 | FAENA HOTEL- PART 2D FOUNDATIONS LEVELFOOTINGS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110007_PDF | 00 | 3 | FAENA HOTEL- PART 2D KEY PLAN COLUMNS STARTERS DETAIL | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110008_PDF | 00 | 3 | FAENA HOTEL- PART 2D COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110009_PDF | 00 | 3 | FAENA HOTEL- PART 2D COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110010_PDF | 00 | 3 | FAENA HOTEL- PART 2D COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110011_PDF | 00 | 3 | FAENA HOTEL- PART 2D COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110012_PDF | 00 | 3 | FAENA HOTEL- PART 2D COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110013_PDF | 00 | 3 | FAENA HOTEL- PART 2D COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-30 17:37 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110014_PDF | 00 | 3 | FAENA HOTEL- PART 2F KEY PLAN FOOTINGS DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110015_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110016_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110017_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110018_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110019_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110020_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110021_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110022_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110023_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110024_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110025_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:13 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110026_PDF | 00 | 2 | FAENA HOTEL- PART 2F FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110027_PDF | 00 | 2 | FAENA HOTEL- PART 2F STRIP FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110028_PDF | 00 | 2 | FAENA HOTEL- PART 2F STRIP FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110029_PDF | 00 | 2 | FAENA HOTEL- PART 2F KEY PLAN COLUMNS STARTERS DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110030_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110031_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110032_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110033_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110034_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110035_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110036_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110037_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110038_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110039_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110040_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110041_PDF | 00 | 2 | FAENA HOTEL- PART 2F COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-16 | 2024-12-16 16:14 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110042_PDF | 00 | 3 | FAENA HOTEL- PART 2B BOTTOM B1 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:16 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110043_PDF | 00 | 2 | FAENA HOTEL- PART 2B BOTTOM B1 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110044_PDF | 00 | 2 | FAENA HOTEL- PART 2B BOTTOM B1 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110045_PDF | 00 | 2 | FAENA HOTEL- PART 2B BOTTOM B2 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110046_PDF | 00 | 2 | FAENA HOTEL- PART 2B BOTTOM B2 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110047_PDF | 00 | 2 | FAENA HOTEL- PART 2B BOTTOM B2 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110048_PDF | 00 | 2 | FAENA HOTEL- PART 2B TOP T1 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110049_PDF | 00 | 2 | FAENA HOTEL- PART 2B TOP T1 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110050_PDF | 00 | 2 | FAENA HOTEL- PART 2B TOP T1 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110051_PDF | 00 | 2 | FAENA HOTEL- PART 2B TOP T2 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110052_PDF | 00 | 2 | FAENA HOTEL- PART 2B TOP T2 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110053_PDF | 00 | 2 | FAENA HOTEL- PART 2B TOP T2 REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110054_PDF | 00 | 2 | FAENA HOTEL- PART 2B KEY PLAN FOOTINGS DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110055_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110056_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110057_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110058_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110059_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110060_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110061_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110062_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110063_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110064_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110065_PDF | 00 | 2 | FAENA HOTEL- PART 2B FOOTINGS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110066_PDF | 00 | 2 | FAENA HOTEL- PART 2B SUMPIT REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110067_PDF | 00 | 2 | FAENA HOTEL- PART 2B SUMPIT REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110068_PDF | 00 | 2 | FAENA HOTEL- PART 2B SUMPIT REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110069_PDF | 00 | 2 | FAENA HOTEL- PART 2B SUMPIT REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110070_PDF | 00 | 2 | FAENA HOTEL- PART 2B KEY PLAN STARTERS & BEAMS DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110071_PDF | 00 | 2 | FAENA HOTEL- PART 2B BEAMS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110072_PDF | 00 | 2 | FAENA HOTEL- PART 2B WALLS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110073_PDF | 00 | 2 | FAENA HOTEL- PART 2B WALLS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110074_PDF | 00 | 2 | FAENA HOTEL- PART 2B SECTIONS DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110075_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110076_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110077_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110078_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110079_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110080_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110081_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110082_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110083_PDF | 00 | 2 | FAENA HOTEL- PART 2B COLUMNS STARTERS REINFORCEMENT DETAILS | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-15 | 2024-12-16 11:15 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-300-0000009_PDF | 00 | 2 | WS-687-FAENA HOTEL- TOWER CRANE FOOTING & EXCAVATION PLAN | Shop Drawing | For Review | In Progress | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-21 | 2024-12-21 10:10 | #REF!
WS-WSI-687-0000-UBJ-SDW-CE-200-0000001_PDF | 00 | 6 | WS-687 Faena Hotel & BR - ENABLING WORKS SITE HOARDING PLAN | Shop Drawing | B-Approved with Comments | Approved with Comments | CE-Civil Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-27 | 2024-11-30 17:53 | #REF!
WS-WSI-687-0000-UBJ-SDW-CE-200-0000001_PDF | 00 | 5 | WS-687 Faena Hotel & BR - ENABLING WORKS SITE HOARDING PLAN | Shop Drawing | B-Approved with Comments | Approved with Comments | CE-Civil Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-27 | 2024-11-30 17:53 | #REF!
WS-WSI-687-0000-UBJ-SDW-LO-2L0-0000001_PDF | 01 | 12 | Faena Hotel & Branded Residence-Logistic Plan | Shop Drawing | B-Approved with Comments | Approved with Comments | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-11-16 | 2024-11-25 11:33 | #REF!
WS-WSI-687-0000-UBJ-SDW-ST-100-0000001_PDF | 00 | 8 | WS-687-TYPICAL MOBILE SCAFFOLDING H=15.00 M , MAX LOAD= 0.75 Kn/m2 | Shop Drawing | B-Approved with Comments | Approved with Comments | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-14 | 2024-12-14 17:56 | #REF!
WS-WSI-687-0000-UBJ-SDW-ST-200-0000016_PDF | 01 | 13 | WS-687-TYPE C-FENCE ELEVATION AND DETAIL | Shop Drawing | C-Revise and Resubmit | Revise and Resubmit | ST-Structural Engineering | DG1-Diriyah Gate Phase 1 | Albawani UCC JV | 2024-12-10 | 2024-12-22 08:48 | #REF!
WS-WSH-687-3230-UBJ-SDW-ST-200-0000016_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000017_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000018_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100016_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100017_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100018_PDF
WS-WSI-687-0000-UBJ-SDW-LO-2L0-0000001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100002_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100003_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100004_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000002_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000003_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000004_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110002_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110003_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110004_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110005_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110006_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110007_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110008_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110009_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110010_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110011_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110012_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110013_PDF
WS-WSI-687-0000-UBJ-SDW-CE-200-0000001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000005_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000006_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000007_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000008_PDF
WS-WSI-687-0000-UBJ-SDW-CE-200-0000001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100005_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100006_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100007_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100008_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000009_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000010_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000011_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000012_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000013_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100009_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100010_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100011_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100012_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100013_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000014_PDF
WS-WSH-687-3230-UBJ-SDW-ST-200-0000015_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100014_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100015_PDF
WS-WSI-687-0000-UBJ-SDW-ST-200-0000016_PDF
WS-WSI-687-0000-UBJ-SDW-ST-100-0000001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110042_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110043_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110044_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110045_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110046_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110047_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110048_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110049_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110050_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110051_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110052_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110053_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110054_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110055_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110056_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110057_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110058_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110059_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110060_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110061_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110062_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110063_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110064_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110065_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110066_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110067_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110068_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110069_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110070_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110071_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110072_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110073_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110074_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110075_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110076_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110077_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110078_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110079_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110080_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110081_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110082_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110083_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110014_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110015_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110016_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110017_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110018_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110019_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110020_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110021_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110022_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110023_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110024_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110025_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110026_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110027_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110028_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110029_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110030_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110031_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110032_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110033_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110034_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110035_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110036_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110037_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110038_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110039_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110040_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0110041_PDF
WS-WSH-687-3230-UBJ-SDW-ST-300-0000009_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100001_PDF
WS-WSH-687-3230-UBJ-SDW-ST-2B1-0100001A_PDF

## Sheet3 (hidden)
ST
AR
ID
FCD
FLS
LS
SIGN
KITCH
LAUNDRY
SPA
Vert.Transportation
EL
BM
FA
IT
SE
ME
PL
DR
LG
FP
UT
IR
SW
TL
CO
BW

## Sheet1 (hidden)
ST
AR
ID
FCD
FLS
LS
SIGN
KITCH
LAUNDRY
SPA
Vert.Transportation
UT
PL
DR
SE
FA
EL
IT
TL
FP
SW
LG
IR
ME
BM
CO
BW

## Sheet2 (hidden)
AC | Acoustics
AD | Administration
AR | Architectural
AV | Audio Visual
BM | Building Information Modelling
CA | Contract Administration
CE | Civil Engineering
CO | Commercial
DE | Design
DR | Drainage
EL | Electrical HV & LV
EN | Environmental
FC | Facade
FP | Fire Protection & Life Safety
GE | Geotechnical
HR | Human Resources
HS | Health and Safety
ID | Interior Design
IF | Infrastructure
IT | Information and Communication Technology
LI | Lighting
LO | Logistics
LS | Land Survey
ME | Mechanical
MN | Management
NS | Non-specific/Multidisciplinary
OP | Operations
PC | Programme Controls / Project Controls
PL | Plumbing
PR | Procurement
QL | Quality
RK | Risk Management
SF | Signage and Wayfinding
SS | Site Setup
ST | Structural Engineering
SU | Sustainability
TM | Traffic Management
WM | Waste Management
FA | Fire Alarm
FB | FOOD & BEVERAGE
FW | FORMWORK
TW | Temporary Work
WF | WATER FEATURE
FCD | FACADE
FLS | FIRE LIFE SAFETY
SIGN | Signage and Wayfinding
LAUND | LAUNDRY
KITCH | KITCHEN AREAS & LAUNDRIES
LAUNDRY | LAUNDRY
SPA | SPA, POOL & WELLNESS
VT | Vertical Transportation
SE | Security System
LG | LPG & FUEL OIL SYSTEM
UT | UT
IR | IRRIGATION NETWORK
SW | STORM WATER NETWORK
TL | TELECOM NETWORK
BW | BUILDERS WORK